## Commitment & Spend
Table 1: Allocation, Spend & Commitment
£ Millions
Allocation1 |  | Committed2 |  |  |  | Spend2
TOTAL | EAFRD | TOTAL |  | EAFRD |  | TOTAL |  | EAFRD
828 | 551 | 832 | 100.5% | 556 | 100.9% | 319.8678 | 38.63% | 228.6606 | 41.5%
Source: WEFO, 31-05-2019
1 Based on a planning exchange rate of £1:€1.18
2 Percentages show share of allocation

## Priority 1
Priority 1: Fostering knowledge transfer and innovation in agriculture, forestry, and rural areas
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 1a | 1 | Total public expenditure | 108.6025 | 92.14 | 22.0331
| 2 | Total public expenditure | 17.2488 | 10.99 | 3.7344
| 16 | Total public expenditure | 129.8135 | 89.8448 | 14.697
FA 1b | 16.1 | Number of EIP operational groups supported | 45 | 45 | 18
| 16.2 - 16.9 | Number of cooperation operations supported (non EIP) | 433 | 270 | 34
FA 1c | 1.1 | Number of participants in trainings | 34716 | 13000 | 11854
Source: WEFO, 31-05-2019

## Priority 2
Priority 2: Enhancing competitiveness and farm viability of all types of agriculture, promoting innovative farm technologies and the sustainable management of forests
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 2a | 1.1 | Number of participants in trainings | 10010 | 10010 | 9127.58
| 1.1 | Number of training days given | 16160 | 8008 | 6772.7756
| 1.1 | Total public expenditure for training / skills | 3.26 | 3.15 | 1.8679
| 1.2 | Number of demonstration operations / information actions supported | 1395 | 1395 | 2085.16
| 1.3 | Number of farm exchanges operations supported | 39 | 39 | 30.03
| 1.1 -1.3 | Total public expenditure | 44 | 42.65 | 12.013
| 2.1 | Number of beneficiaries advised | 2963 | 2963 | 1775.277
| 2.1 - 2.2 | Total public expenditure | 9.17 | 6.7 | 1.9698
| 4.1 | Number of holdings supported | 2431 | 721 | 354
| 4.1 | Total public expenditure | 52.9 | 39.399 | 15.2097
| 4 | Total investment | 85.82 | 98.4976 | 38.0242
| 4 | Total public expenditure | 54.08 | 39.399 | 15.2097
| 16 | Total public expenditure | 16.2 | 0.49871 | 0.046432
Source: WEFO, 31-05-2019

## Priority 3
Priority 3: Promoting food chain organisation and risk management in agriculture
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 3a | 1.1 | Number of participants in trainings | 16996 | 650 | 725
| 1.1 | Number of training days given | 6345 | 520 | 935
| 1.1 | Total public expenditure for training / skills | 43.87 | 38.7 | 6.119
| 1.2 | Number of demonstration operations / information actions supported | 91 | 91 | 135.4
| 1.1 -1.3 | Total public expenditure | 46.52 | 39.66 | 6.7777
| 2.1 | Number of beneficiaries advised | 303 | 303 | 181.8
| 2.1 - 2.2 | Total public expenditure | 0.94 | 0.86 | 0.20172
| 4.2 | Number of operations supported | 120 | 120 | 80
| 4 | Total investment | 133.09 | 133.0076 | 66.87
| 4 | Total public expenditure | 53.24 | 53.2031 | 23.1138
| 16.4 | Number of agricultural holdings supported | 165 | 509 | 99
| 16 | Number of cooperation operations supported (non EIP) | 165 | 15 | 5
| 16 | Total public expenditure | 36.21 | 9.8969 | 1.5765
Source: WEFO, 31-05-2019

## Priority 4
Priority 4: Restoring, preserving and enhancing ecosystems dependent on agriculture and forestry
Priority | Measure | Outputs | Target | Forecast | Achieved to Date
Priority 4 Agricultural Land | 1.1 | Number of participants in trainings | 1376 | 1040 | 948.32
| 1.1 | Number of training days given | 0 | 832 | 703.665
| 1.1 | Total public expenditure for training / skills | 1.04 | 0.32 | 0.40712
| 1.2 | Number of demonstration operations / information actions supported | 145 | 145 | 216.64
| 1.3 | Number of farm exchanges operations supported | 4 | 4 | 3.12
| 1.1 -1.3 | Total public expenditure | 5.27 | 4.43 | 1.4612
| 2.1 | Number of beneficiaries advised | 1684 | 758 | 454.5
| 2.1 - 2.2 | Total public expenditure | 2.46 | 2.16 | 0.73397
| 4.4 | Number of operations supported | 11120 | 5317 | 4210
| 4 | Total investment | 53.24 | 58.0565 | 34.1881
| 4 | Total public expenditure | 53.24 | 58.0565 | 34.1881
| 8.1 | Total area (ha) supported | 2498 | 4695 | 886
| 8.1 | Total public expenditure | 13.88 | 12.251 | 4.117
| 8.2 | Total area (ha) supported | 50 | 1 | 1
| 8.2 | Total public expenditure | 0.085 | 0.002 | 0.00166
| 10.1 | Total area (ha) supported | 1417210 | 1403321 | 689186
| 10.1 | Physical area (ha) supported | 635399 | 691217 | 585966
| 10.1 | Number of contracts supported | 7338 | 7117 | 7117
| 10.1 | Total public expenditure | 186.42 | 222.3245 | 126.8823
| 11.1 | Number of holdings supported | 201 | 175 | 147
| 11.1 | Total area (ha) supported | 11153 | 15018 | 15018
| 11.2 | Number of holdings supported | 341 | 561 | 446
| 11.2 | Total area (ha) supported | 57287 | 68069 | 57544
| 11 | Total public expenditure | 21.47 | 28.4536 | 15.361
| 16 | Number of cooperation operations supported (non EIP) | 25 | 25 | 8.5716
| 16 | Total public expenditure | 21.62 | 17.3727 | 1.283
Priority 4 Forest Area | 1.1 | Number of participants in trainings | 274 | 130 | 118.54
| 1.1 | Number of training days given | 104 | 104 | 87.9581
| 1.1 | Total public expenditure for training / skills | 0.34 | 0.04 | 0.050885
| 1.2 | Number of demonstration operations / information actions supported | 18 | 18 | 27.08
| 1.3 | Number of farm exchanges operations supported | 1 | 1 | 0.39
| 1.1 -1.3 | Total public expenditure | 0.87 | 0.41 | 0.18263
| 2.1 | Number of beneficiaries supported | 851 | 51 | 30.3
| 2.1 - 2.2 | Total public expenditure | 1.25 | 0.14 | 0.091736
| 8.3 | Number of beneficiaries supported | 1 | 1 | 0
| 8.3 | Total area (ha) supported | 76000 | 76000 | 0
| 8.3 | Total public expenditure | 0.26 | 0.12153 | 0
| 8.5 | Number of operations supported | 403 | 504 | 170
| 8.5 | Total area (ha) supported | 8400 | 2825 | 1041
| 8.5 | Total public expenditure | 3.21 | 3.9274 | 3.9274
| 16 | Number of cooperation operations supported (non EIP) | 10 | 10 | 3.4284
| 16 | Total public expenditure | 8.82 | 7.1882 | 0.49326
Source: WEFO, 31-05-2019

## Priority 5
Priority 5: Promoting resource efficiency and supporting the shift towards a low carbon and climate resilient economy in agriculture, food and forestry sectors
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 5b | 1.1 | Number of participants in trainings | 260 | 260 | 237.08
| 1.1 | Number of training days given | 208 | 208 | 175.9162
| 1.1 | Total public expenditure for training / skills | 0.085 | 0.08 | 0.049925
| 1.2 | Number of demonstration operations / information actions supported | 36 | 36 | 54.16
| 1.3 | Number of farm exchanges operations supported | 1 | 1 | 0.78
| 1.1 -1.3 | Total public expenditure | 1.14 | 1.11 | 0.31344
| 2.1 | Number of beneficiaries advised | 83 | 83 | 49.995
| 2.1 - 2.2 | Total public expenditure | 0.26 | 0.24 | 0.055472
| 4.1 - 4.3 | Number of operations supported | 286 | 414 | 226
| 4 | Total investment | 17.19 | 11.588 | 11.5645
| 4 | Total public expenditure | 10.74 | 4.6352 | 4.6258
| 16 | Total public expenditure | 0.25 | 0.24701 | 0.023216
FA 5c | 1.1 | Number of participants in trainings | 260 | 260 | 237.08
| 1.1 | Number of training days given | 208 | 208 | 175.9162
| 1.1 | Total public expenditure for training / skills | 0.085 | 0.08 | 0.049925
| 1.2 | Number of demonstration operations / information actions supported | 36 | 36 | 54.16
| 1.3 | Number of farm exchanges operations supported | 1 | 1 | 0.78
| 1.1 -1.3 | Total public expenditure | 1.14 | 1.11 | 0.31344
| 2.1 | Number of beneficiaries advised | 66 | 66 | 39.39
| 2.1 - 2.2 | Total public expenditure | 0.2 | 0.19 | 0.043705
| 7.2 | Number of operations supported | 197 | 2 | 0
| 7 | Total investment | 12.29 | 9.8963 | 0
| 7 | Total public expenditure | 10.24 | 3.9585 | 0
| 8.6 | Number of operations supported | 100 | 88 | 3
| 8.6 | Total investment | 13.08 | 14.5 | 0.0025
| 8.6 | Total public expenditure | 5.23 | 5.8 | 0.18768
| 16 | Number of cooperation operations supported (non EIP) | 105 | 0 | 0
| 16 | Total public expenditure | 1.24 | 0.55666 | 0.023216
FA 5d | 1.1 | Number of participants in trainings | 260 | 260 | 237.08
| 1.1 | Number of training days given | 208 | 208 | 175.9162
| 1.1 | Total public expenditure for training / skills | 0.085 | 0.08 | 0.049925
| 1.2 | Number of demonstration operations / information actions supported | 36 | 36 | 54.16
| 1.3 | Number of farm exchanges operations supported | 1 | 1 | 0.78
| 1.1 -1.3 | Total public expenditure | 1.14 | 1.11 | 0.31344
| 2.1 | Number of beneficiaries advised | 588 | 588 | 352.086
| 2.1 - 2.2 | Total public expenditure | 1.82 | 1.67 | 0.39066
| 4.1, 4.3 + 4.4 | Number of operations supported | 4893 | 9189 | 44
| 4 | Total investment | 12.5 | 5.9621 | 9.7494
| 4 | Total public expenditure | 7.84 | 2.3848 | 3.8998
| 10.1 | Total area (ha) supported | 59807.08 | 108315.61 | 2799
| 10.1 | Total public expenditure | 10.55 | 12.3322 | 5.1279
| 16 | Total public expenditure | 1.6 | 0.24701 | 0.023216
FA 5e | 1.1 | Number of participants in trainings | 260 | 260 | 237.08
| 1.1 | Number of training days given | 208 | 208 | 175.9162
| 1.1 | Total public expenditure for training / skills | 0.085 | 0.08 | 0.049925
| 1.2 | Number of demonstration operations / information actions supported | 36 | 36 | 54.16
| 1.3 | Number of farm exchanges operations supported | 1 | 1 | 0.78
| 1.1 -1.3 | Total public expenditure | 1.14 | 1.11 | 0.31344
| 2.1 | Number of beneficiaries advised | 326 | 76 | 45.753
| 2.1 - 2.2 | Total public expenditure | 0.58 | 0.22 | 0.13543
| 4.4 | Number of operations supported | 7857 | 3000 | 2923
| 4 | Total investment | 4.57 | 0.26417 | 1.8034
| 4 | Total public expenditure | 4.57 | 0.26417 | 1.8034
| 8.1 | Total area (ha) supported | 832 | 3541 | 461
| 8.1 | Total public expenditure | 3.92 | 5.9686 | 3.1237
| 8.2 | Total area (ha) supported | 50 | 0 | 0
| 8.2 | Total public expenditure | 0.006 | 0.03 | 0
| 8.3 | Number of beneficiaries supported | 0.75 | 0 | 0
| 8.3 | Total area (ha) supported | 225000 | 0 | 0
| 8.3 | Total public expenditure | 0.78 | 0.36459 | 0
| 8.4 | Number of beneficiaries supported | 184 | 156 | 144
| 8.4 | Total area (ha) supported | 1781 | 1248 | 898
| 8.4 | Total public expenditure | 3.55 | 3.1657 | 2.2479
| 8.5 | Number of operations supported | 393 | 83 | 44
| 8.5 | Total area (ha) supported | 4900 | 530 | 0
| 8.5 | Total public expenditure | 2.08 | 0.12211 | 0.0888
| 10.1 | Physical area (ha) supported | 3021.6 | 1858.67 | 1826
| 10.1 | Total public expenditure (£'m) | 0.85 | 1.0405 | 0.6818
| 16 | Number of cooperation operations supported (non EIP) | 200 | 1 | 0
| 16 | Total public expenditure | 0.4 | 0.497 | 0.023216
Source: WEFO, 31-05-2019

## Priority 6
Priority 6: Promoting social inclusion poverty reduction and economic development in rural areas
Focus Area | Measure | Outputs | Target | Forecast | Achieved to Date
FA 6a | 2.1 | Number of beneficiaries advised | 168 | 168 | 100.899
| 2.1 - 2.2 | Total public expenditure | 0.52 | 0.48 | 0.11195
| 6.4 | Number of beneficiaries supported | 340 | 276 | 2
| 6 | Total investment | 45.2 | 43.7719 | 0.16
| 6 | Total public expenditure | 17.51 | 17.5088 | 0.16228
| 8.6 | Number of operations supported | 20 | 17 | 19
| 8.6 | Total investment | 2.62 | 3.3 | 4.06
| 8.6 | Total public expenditure | 1.05 | 1.3 | 1.8855
| 16 | Number of cooperation operations supported (non EIP) | 106 | 1 | 1
| 16 | Total public expenditure | 0.26 | 0.15935 | 0.014341
| 6.4 + 8.6 | Number of jobs created | 765 | 1015 | 2
FA 6b | 1.1 | Number of participants in trainings | 4890 | 0 | 0
| 1.1 | Total public expenditure for training / skills | 3.53 | 0 | 0.18813
| 1.1 -1.3 | Total public expenditure | 7.34 | 0 | 0.18813
| 7.1 | Number of operations supported | 18 | 0 | 0
| 7.2 | Number of operations supported | 56 | 1 | 1
| 7.4 | Number of operations supported | 116 | 136 | 59
| 7.5 | Number of operations supported | 150 | 81 | 14
| 7.6 | Number of operations supported | 35 | 9 | 8
| 7.7 | Number of operations supported | 25 | 7 | 5
| 7 (exc 7.3) | Population benefiting from improved services / infrastructures | 1381745 | 1549766 | 58592
| 7 (exc 7.3) | Total public expenditure | 19.79 | 9.5801 | 5.5964
| 19 | Number of LAGs selected | 18 | 18 | 18
| 19 | Number of projects supported | 54 | 75 | 65
| 19 | Number of cooperation projects supported | 27 | 29 | 0
| 19 | Population covered by LAG | 1381745 | 1381745 | 1381745
| 19.1 | Total public expenditure | 0.043 | 0.05 | 0.051185
| 19.2 | Total public expenditure | 33.05 | 32.3 | 8.5329
| 19.3 | Total public expenditure | 3.31 | 3.4 | 0.3903
| 19.4 | Total public expenditure | 11.07 | 11.8 | 5.9939
| 16 | Number of cooperation operations supported (non EIP) | 216 | 218 | 28
| 16 | Total public expenditure | 43.16 | 53.68 | 11.1708
| 7 + 19 | Number of jobs created | 100 | 111 | 12
FA 6c | 1.1 | Number of participants in trainings | 130 | 130 | 118.54
| 1.1 | Number of training days given | 104 | 104 | 87.9581
| 1.1 | Total public expenditure for training / skills | 0.043 | 0.04 | 0.024963
| 1.1 -1.3 | Total public expenditure | 0.57 | 0.55 | 0.15672
| 7.3 | Number of operations supported | 16 | 4 | 2
| 7.3 | Population benefiting from new or improved IT infrastructures | 500000 | 13392 | 0
| 7.3 | Total public expenditure | 2.05 | 0.5 | 0.16333
Source: WEFO, 31-05-2019

## Technical Assistance
Technical Assistance
Measure | Outputs | Target | Forecast | Achieved to Date
20.1 | Total public expenditure | 28.7 | 28.7 | 11.3105
20.2 | Total public expenditure | 2.3669 | 2.3669 | 0.7319
20.2 | Number of thematic and analytical exchanges set up | 25 | 34 | 34
20.2 | Number of NRN communication tools | 230 | 753 | 753
20.2 | Number of ENRD activities in which the NRN has participated | 10 | 20 | 20
Source: WEFO, 31-05-2019

## EOIs
Scheme | Number of Scheme Rounds | Total Allocation | Applications Invited | Applications Received | Appraisals Complete | Applications Approved | Total Requested (At Full Application) | Total Approved (At Full Application) | Total Spend
Farm Business Grant Scheme | 5 | 37484623 | N/A | 2720 | 2720 | 2552 | 17800000 | 14400000 | 13574786.33
Sustainable Production Grant Scheme* | 5 | 34011401.99 | 82 | 73 | 73 | 73 | 13465001 | 13657578 | 9427673.59
Food Business Investment Scheme | 6 | 53563315 | 141 | 90 | 73 | 68 | 38427776 | 34925733 | 23113844.23
Cooperation & Supply Chain Development Scheme* | 5 | 102530568 | 75 | 64 | 59 | 48 | 97899960 | 59588318 | 12738364.89
Sustainable Management Scheme | 4 | 29443537 | 46 | 33 | 23 | 23 | 16977959 | 12375531 | 1726498.53
Rural Community Development Fund* | 7 | 32099744 | 286 | 201 | 176 | 146 | 21656270 | 18673463 | 5759713.35
Timber Business Investment Scheme | 4 | 6291637 | 71 | 50 | 35 | 33 | 4414345 | 3223637 | 2073193.66
Co-operative Forest Planning Scheme | 2 | 1200000 | 4 | 2 | 2 | 2 | 257646 | 257427 | 0
European Innovation Partnership | N/A | 2475000 | 19 | 7 | 7 | 1 | 2019100 | 2475000 | 232158.94
LEADER | N/A | 47637182 | 75 | 75 | 75 | 75 | 47625195 | 47688194 | 14968261.86
Knowledge Transfer & Innovation* | N/A | 108602543 | 16 | 14 | 14 | 14 | 72366442 | 71370512 | 22033136.28
Rural Business Investment Scheme* | N/A | 17508765.01 | 2 | 2 | 2 | 2 | 7159645 | 13508765 | 162280.65
Rural Business Advisory Service* | N/A | 15705870 | 6 | 5 | 5 | 5 | 7245704.25 | 6759790 | 3734423.08
Technical Assistance | N/A | 41800122.99 | 8 | 8 | 8 | 8 | 31466067 | 31466067 | 12042379.36
Socio-Economic Total | 38 | 530354308.99 | 831 | 3344 | 3272 | 3050 | 378781110.25 | 330370015 | 121586714.75
Source: WEFO, 31-05-2019
*Figures include Direct Applications
Scheme | Number of Scheme Rounds | Total Allocation | Total Approved (At Full Application) | Total Spend
Glastir Historic Advice | N/A | 112440 | 24540 | 0
NRW Woodlands | N/A | 1430487 | 1430487 | 0
Glastir Small Grants | 4 | 10045139 | 4045139 | 4124086.81
Glastir Advanced | 4 | 137509341 | 125118626 | 83756944.3
Glastir Woodland Creation | 6 | 13800210 | 4076248 | 6418144.57
Forest Monitoring and Risk Management Scheme | N/A | 1040000 | 486116 | 0
Glastir Woodland Restoration | 6 | 3486426 | 2180357 | 2247934.26
Legacy Schemes | N/A | 8792093.02 | 8258107 | 4846218.31
Glastir Woodland Management | N/A | 338400 | 698786 | 311400
Glastir Entry | N/A | 86324398 | 80000871 | 67426487.64
Glastir Commons | N/A | 18029847 | 18029847 | 13788846.98
Glastir Organics | 3 | 21142704 | 17428508 | 15360994.7
Agri-Environment Total | 23 | 302051485.02 | 261777632 | 198281057.57
Source: WEFO, 31-05-2019