Business Case Templates
To support better investment decisions and better procurement

The aim of the business case template family is to support your thinking, writing and engagement with stakeholders and compliance with best practice. These templates provide a framework for scoping and planning spending proposals, to support evidence based decision-making. They avoid a “one-size fits all” approach and should be used proportionately.

The two Single-Stage Business Case templates are based on the Five Case Model and follow the Better Business Cases Guidance. They have been developed by the International Better Business Case Programme.

The Five Case Model can be used for the preparation of:
- Programme Business Cases (PBC),
- Project Business Cases (three stage: SOC, OBC, FBC),
- Business Justification Cases (BJC)
- Policies and Strategies.

It is all about: Thinking, Evidencing, and Documenting. Business cases should be clear, concise, and avoid unnecessary repetition.

Which template should be used?

Consider:
- the value thresholds (see guidance below),
- the complexity and risk involved,
- whether the situation is novel or contentious,
- whether procurement is required and the scale of the procurement, and
- whether there are any dependencies, e.g. with business as usual matters or other projects?
When in doubt, consider using the higher value business case templates, which provide more structure and support. Contact your local office for advice, support and training.

TEMPLATES / For Procurements and Projects (enabling outputs, activities and infrastructure): / Single Stage Business Case - Low Value and Risk (£0 to £250k value of procurement). / Single Stage Business Case - Medium Value and Risk (£250k to £2 million value of procurement) / Three Stage Business Case (SOC, OBC, FBC) – High Value (Over £2 million value of procurement) [1] / For Overarching Programmes (outcomes to be achieved through improved services comprised of enabling projects): / Programme Business Case using the Five Case Model[2]
[1] See Better Business Case Five Case Model Project Guidance: https://gov.wales/guide-developing-project-business-case
[2] See Better Business Case Five Case Model Programme Guidance: https://gov.wales/guide-developing-programme-business-case

Questions or feedback on our templates and guidance?
Contact us at: BetterBusinessCasesMailbox@gov.wales

<Title of Investment Proposal>

OUTLINE BUSINESS CASE (OBC) – HIGH VALUE (OVER £2 MILLION VALUE OF PROCUREMENT)

SRO:
Project Manager:
Organisation:

	Name	Signature	Date
Prepared by:
Reviewed by:
Approved by:

This template is based on the Five Case Model and follows the Better Business Case Guidance. It has been developed by the International Better Business Case Programme.
Outline Business Case (OBC) template

This template should be completed in conjunction with the Better Business Cases Guide to developing the Project Business Case. The relevant steps and actions in the Guidance are provided.

The purpose of the OBC is to plan the project and to identify the preferred option and arrangements for procurement and the successful delivery of the project

Business Case heading	Action	Guidance reference
	Consider the use of a facilitated workshop for the completion of step 4 and assessment of the short-listed options (workshop 3 refers).	Step 4 – Determining potential Value for Money (VfM)
Strategic Outline Case (SOC)- Strategic and Economic Cases	Revisit the Strategic Outline Case (SOC) and confirm that the short list options remain valid. / This includes the case for change and spending objectives agreed in the strategic case section and the options appraised in the economic case section.	Action 9
Economic Case / NPSC/NPSV Findings	Prepare the economic appraisals for the short list options / These must be prepared in accordance with the HM Treasury Green Book guidance and summarised in the table provided. The net present social value (NPSV), or net present social cost (NPSC), and a benefit cost ration (BCR) must be provided for each option in the short list. / All sources and assumptions and the evidence base must be recorded.	Action 10
Benefits appraisal	Undertake benefits appraisal. / Benefits should be identified by beneficiary (recipient) and class (type) for the following categories: / Direct public sector benefits (to originating organisation) / Indirect public sector benefits (to other public sector organisations) / Wider benefits to UK society (e.g. households, individuals, businesses). / The approach to benefits appraisal should be prudent, proportionate and evidence based. All benefits should be recorded in the benefits register.	Action 11
Risk Assessment	Under risk appraisal. / Allowances for optimism bias should be reduced and replaced by measured risk (£). All risks should be recorded in the risk register	Action 12
Preferred Option / Sensitivity Analysis	Select preferred option and undertake sensitivity analysis. / Complete the summary table outlined in the HM Treasury Green Book. / The preferred option should be a balanced judgement based on the net present social value (NPSV), the Benefit Cost Ratio (BCR) and the level of risk involved; or alternatively, the lowest net present social cost (NPSC). Any unmeasured or unquantified (£) benefits must be explained in full.	Action 13
Commercial Case	Consider the use of a facilitated workshop for step 5 and developing the Deal (workshop 4 refers).	Step 5 – Preparing for the potential Deal
Procurement Strategy and route	Determine procurement strategy. / Explain how the project’s key outputs and activities will be procured in accordance with relevant procurement rules and regulations. / Reference the Organisation’s Commercial Strategy and commitment to Crown Commercial Operating Standards, as required.	Action 14
Service requirements and outputs	Determine service streams and required output. / Identify the project’s service streams and required outputs and the scope and content of a potential Deal to be made between public and private sector service providers. / Attach a copy of the advertisement, if applicable.	Action 15
Risk allocation	Outline potential risk apportionment. / Identify how the service risks in the design, build, funding and operational phases of the project may be apportioned between the public and private sectors.	Action 16
Charging mechanism	Outline potential payment mechanisms. / Identify how the project intends to make payment for its key services and outputs over the expected lifespan of the contract(s) and to tie down risks in the charging mechanism.	Action 17
Key contractual arrangements / Personnel implications / Accountancy treatment	Ascertain contractual issues and accountancy treatment. / Outline the contractual arrangements for the project, contract to be used, the key contractual issues for the Deal and its accountancy and personnel implications (if any).	Action 18
Financial Case		Step 6 - Ascertaining affordability and funding requirement
	Prepare financial model and financial appraisals	Action 19
Capital and revenue requirements	The financial appraisal for the preferred option must be prepared in accordance with the guidance provided in the HM Treasury Green Book. / Whole life costs are required. / Note: the economic and financial appraisals are treated differently.	Action 19 continued
Net effect on prices (if any)	The implications for any prices that the organisation charges for its services must be explained.	Action 19 continued
Impact on balance sheet	The impact on the organisation’s balance sheet must be explained. This includes depreciation, impairment, and any contingent liabilities or capital changes.	Action 19 continued
Impact on income and expenditure account	The impact of the organisation’s income and expenditure account must be explained, if applicable.	Action 19 continued
Overall affordability and funding	A summary of the overall affordability and funding of the project must be provided, together with an assessment of how any shortfalls in available funding will be covered.	Action 19 continued
Confirmation of stakeholder support	This must be provided where other public sector organisations are funding the project’s outputs and services.	Action 19 continued
Management Case	Consider a facilitated workshop for the completion of step 7 and planning the arrangements required for the successful delivery of the project (workshop 5 refers).	Step 7 – Planning for successful delivery
Programme and project management governance arrangements	Plan project management – strategy, frameworks and plans. / Record the risk profile assessment (RPA) and the Senior Responsible Owner (SRO) for the project. / Set out the governance arrangements, including key roles and responsibilities. / Provide an outline of the project plan, including key milestones.	Action 20
Use of specialist advisers	Specify what is required by way of external support: legal, technical and business expertise etc.	Action 20 continued
Change and Contract management arrangements	Plan change and contract management – strategy, frameworks and plans. / Explain how change will be managed.	Action 21
Benefits Realisation arrangements	Plan benefits realisation – strategy, framework and plans. / Complete the benefits register in accordance with HM Treasury Green Book guidance and attach to the business case. Confirm that the benefits register is an integral part of project management meetings.	Action 22
Risk management arrangements	Plan risk management – strategy, framework and plans. / Complete the risk register in accordance with HM Treasury Green Book guidance and attach to the business case. Confirm that the risk register is an integral part of project management meetings.	Action 23
Project assurance / Post implementation and evaluation arrangements	Plan project assurance and post evaluation – strategy, framework and plans. / Set out the arrangements for project assurance, including the use of Cabinet Office Gateway Reviews. Other sources of assurance should be considered: technical, quality etc. / Specify the probable timescales for undertaking project implementation and post evaluation reviews, including Cabinet Office Gateway Review 5 (Benefits Realisation).	Action 24
Contingency arrangements and plans	Set out the contingency plans in the event of any delays or disruptions to anticipated services.	Action 24 continued
Project Assurance	Undertake a review of the project’s ability to undertake a procurement that will deliver value for money.	Gateway 2 (Delivery Strategy)