Business Case Templates
To support better investment decisions and better procurement

The aim of the business case template family is to support your thinking, writing and engagement with stakeholders and compliance with best practice. These templates provide a framework for scoping and planning spending proposals, to support evidence based decision-making. They avoid a “one-size fits all” approach and should be used proportionately.

The two Single-Stage Business Case templates are based on the Five Case Model and follow the Better Business Cases Guidance. They have been developed by the International Better Business Case Programme.

The Five Case Model can be used for the preparation of:
- Programme Business Cases (PBC),
- Project Business Cases (three stage: SOC, OBC, FBC),
- Business Justification Cases (BJC)
- Policies and Strategies.

It is all about: Thinking, Evidencing, and Documenting. Business cases should be clear, concise, and avoid unnecessary repetition.

Which template should be used?

Consider:
- the value thresholds (see guidance below),
- the complexity and risk involved,
- whether the situation is novel or contentious,
- whether procurement is required and the scale of the procurement, and
- whether there are any dependencies, e.g. with business as usual matters or other projects?
When in doubt, consider using the higher value business case templates, which provide more structure and support. Contact your local office for advice, support and training.

TEMPLATES / For Procurements and Projects (enabling outputs, activities and infrastructure): / Single Stage Business Case - Low Value and Risk (£0 to £250k value of procurement). / Single Stage Business Case - Medium Value and Risk (£250k to £2 million value of procurement) / Three Stage Business Case (SOC, OBC, FBC) – High Value (Over £2 million value of procurement) [1] / For Overarching Programmes (outcomes to be achieved through improved services comprised of enabling projects): / Programme Business Case using the Five Case Model[2]
[1] See Better Business Case Five Case Model Project Guidance: https://gov.wales/guide-developing-project-business-case
[2] See Better Business Case Five Case Model Programme Guidance: https://gov.wales/guide-developing-programme-business-case

Questions or feedback on our templates and guidance?
Contact us at: BetterBusinessCasesMailbox@gov.wales

<Title of Investment Proposal>

STRATEGIC OUTLINE CASE (SOC) – HIGH VALUE (OVER £2 MILLION VALUE OF PROCUREMENT)

SRO:
Project Manager:
Organisation:

	Name	Signature	Date
Prepared by:
Reviewed by:
Approved by:

This template is based on the Five Case Model and follows the Better Business Case Guidance. It has been developed by the International Better Business Case Programme.
Strategic Outline Case (SOC) template

This template should be completed in conjunction with the Better Business Cases Guide to developing the Project Business Case. The relevant steps and actions in the Guidance are provided.

The purpose of the SOC is to scope the project and to identify the preferred way forward.

Business Case heading	Action	Guidance reference
Strategic assessment	Determine how the project aligns with other projects and programmes within the Organisation’s business strategy and strategic portfolio, and supports the wider public sector’s objectives.	Step 1, action 1
Programme assurance	Undertake a review of the programme.	Gate 0 (strategic assessment)
Executive Summary	4 to 5 pages maximum predicated on the Five Case Model. / In the first paragraph outline the intervention and spend for which approval is being sought.
Strategic Case	Undertake a facilitated workshop for the completion of step 2: making the case for change (workshop 1 refers). Ensure that the Senior Responsible Owner (SRO) attends along with key stakeholders and end users.	Step 2 – Making the Case for Change
Strategic Context / Organisational Overview	Provide a brief overview of the organisation(s) making the case for intervention and change.	Action 2

Business strategy and aims	Explain how the project supports the existing policies and strategies of the organisation and other programmes and projects within the strategic portfolio.	Action 2 continued
Other relevant strategies	National and regional and other organisations’ strategies refer. Keep this section to a minimum and attach relevant documents, if applicable.	Action 2 continued
The Case for Change / Spending objectives	Specify the spending objectives for the project. These should focus on the target outcomes for the intervention and be SMART. / Desired outcomes include: improved economy, efficiency, effectiveness, replacement and compliance.	Action 3
Existing arrangements	Provide a factual picture of the organisation’s current service model. Business as Usual (BAU) refers.	Action 3 continued
Business needs – current and future	Specify the organisation’s business needs in terms of the service improvements required to achieve the agreed spending objectives. Focus on the “service gaps”.	Action 3 continued
Potential scope and service requirements	Identify the potential scope for the project in terms of the operational capabilities and service changes required. / Focus on the outputs and key activities required to close the “service gaps” identified on a continuum of need: core (essential); desirable and optional.	Action 4
Main benefits	Specify the main benefits associated with the achievements of the project’s spending objectives by category, beneficiary and class. Distinguish benefits from outcomes.	Action 5
Main risks	Specify the main risks associated with the achievement of the project’s spending objectives and the proposed counter measures for avoidance, mitigation and management.	Action 5 continued
Constraints	Specify any constraints that have been placed on the project. These should not be artificially imposed.	Action 5 continued
Dependencies	Specify any dependencies outside the scope of the project upon which the success of the project is dependent.	Action 5 continued
Economic Case	Undertake a facilitated workshop for the completion of step 3 (workshop 2 refers). Ensure that the Senior Responsible Owner (SRO) attends along with key stakeholders and end users.	Step 3 – Exploring the. Preferred way forward
Critical success factors (CSFs)	Agree critical success factors. / Generic CSF’s include: strategic fit and business needs; value for money; supply side capacity and capability; affordability and achievability. Tailor accordingly.	Action 6
Long listed Options	Determine the long list options and undertake SWOT (strengths, weaknesses, opportunities, threats) analysis. / Headings must include: description, advantages, disadvantages and conclusions in terms of how well the option meets the agreed investment objectives and CSF’s for the project. / Use must be made of the Options Framework Filter in order to disaggregate options in terms of their potential scope, solution, method of service delivery, implementation and funding. / The evidence base and all sources and assumptions must be recorded.	Action 7
Preferred Way Forward	Outline the recommended preferred way forward (scope, solution, service delivery, implementation and funding) for the project.	Action 8
Shortlisted Options	Describe the short list to be examined in further detail at the Outline Business Case stage. This should include a minimum of 3 to 5 options, including: / Business as Usual (BAU) / A realistic “do minimum” based on the core requirements for the project / The recommended preferred way forward / One or more possible options based on a more and/or less ambitious combinations of the preferred way forward.	Action 8 continued
NPSC/NPSV findings	Indicative Net Present Social Value, Net Present Social Cost and Cost Benefit Ratios should be provided for the proposed SOC short list. The HM Treasury Green Book summary table should be used for this purpose. / Allowances should be made for optimism bias. / Indicative benefits must be included. / The evidence base and all relevant sources and assumptions must be recorded. / Multi Criteria Decision Analysis (MCDA) using swing weighting and a professionally qualified facilitator must be restricted to options for the scope and means of achievement within the long list.	Action 8 continued
Commercial, Financial and Management Cases	An overview of these Cases in support of the preferred way forward must be provided	See Guidance
Project assurance	Undertake a review of the project.	Gate1 (business needs)