Access Reform Programme: Steering Group Meeting 2
30 October 2019

Attendees:
Name	Organisation
Simon Pickering (Chair)	Welsh Government – Head of Landscape & Outdoor Recreation
Jont Bulbeck	Natural Resources Wales
Eifion Jones (BBNPA)	Representing the 3 National Park Authorities and 5 AONBs
Ben Sears	Welsh Local Government Association
Adrian Walls	Welsh Rights of Way Managers Working Group

Technical and secretarial support:
Name	Organisation
Tom Cosson	Welsh Government - Landscape & Outdoor Recreation
Sarah Smith	Welsh Government - Landscape & Outdoor Recreation
Helen Lewis	Welsh Government - Landscape & Outdoor Recreation
Joe Roberts	Natural Resources Wales

Key decisions and actions arising	Owner
Notes and actions from previous meeting / The minutes were agreed.
Terms of reference / It was suggested that version numbers be included for the Terms of Reference and other key documents.	Sarah
Expert Groups processes / Members requested clarification as to whether the General Election would have an impact on the EOI window / Confirmation – the General Election has no impact / The Group agreed that each stage meeting of the Expert Groups should be held within 2 weeks. / The Group agreed that the Expert Groups’ first meeting should be facilitated – these would take place end of January/beginning of February 2020. / NRW will fund the facilitator and the drafting of the Reform Proposal Paper (out of the ARAG Programme budget) / The Group agreed that members of the Expert Groups should use ‘Knowledge Hub’ in advance of their stage meetings. / The Group agreed that they were happy to receive information that has not already been submitted as part of a consultation response. It would be shared with the relevant Expert Group but no dialogue about it would be entered into. / It was agreed that Joe would make amendments to the Expert Groups Processes paper and combine it with the Terms of Reference. / The Group agreed it was beneficial to contact LAF Secretary’s now to advise them that the Options Analysis Report will be sent to LAF for comment in early autumn 2020.	Jont / Tom/Joe / Sarah
Expert Groups establishment / The Group agreed it would be beneficial to include the dates of the Expert Groups’ first meetings on the EOI application form. / The Group agreed that an induction session should be held for all Expert Groups at the end of January 2020 and potential applicants advised of this date. This session will cover; ways of working, the terms of reference and ‘Knowledge Hub’. / It was agreed that WG and NRW would carry out an initial sift of applications before the Steering Group meeting on 9 December. / The Group agreed that applicants will be informed of the outcome by 20 December. Unsuccessful candidates will be invited to express any additional views via their sector representative. / The Group agreed that the closing date for applications is 29 November 2019. / The Group agreed the Expression of Interest Form and Terms of Reference. They will be translated before being issued via the National Access Forum, Local Access Forums and to those individuals who have contacted WG directly. / The Group agreed that successful applicants will be required to sign a copy of the Terms of Reference.	Sarah / Sarah / Simon/Jont / Sarah
Policy Intents / It was agreed that the early draft policy intents (for each Expert Group) would be put on Knowledge Hub for Steering Group members to consider and comment, in order for meaningful discussion at the next meeting.	Helen
Any Other Business / Agenda items for the next meeting – Policy Intents, Expert Group Recruitment	Sarah