## Annex 1 Welsh Government
Annex 1 – Welsh Government Project Pipeline
This section of the pipeline outlines Welsh Government programmes and projects where total scheme value exceeds £15m and, if not already started, are due to begin within the next three years. It is based on current expectation of future funding. Whilst the schemes presented are our priority projects and have a high probability of being delivered as described, this does not represent a formal commitment from the Welsh Government. This reflects the potential for future uncertainties, including the future public spending outlook.
Prosperity for All: an economic action plan sets the direction for a modern and connected infrastructure designed to enable more inclusive economic growth by promoting regional strengths and tackling structural challenges. Investing in our transport infrastructure, digital connectivity and the quality of business sites and premises is essential to better connected people, places and businesses and in turn influences productivity and competitiveness.
Sector | Project/Programme | Total scheme value (est. £m) | Welsh Government support (est.£m) | Start Date | End Date | Finance and delivery | Additional information
Economic Development | Advanced Manufacturing and Research Institute (AMRI) – Deeside Enterprise Zone (EZ) | 35 | 35 | 2017 | 2022 | Financed and delivered by Welsh Government (WG). The AMRI will offer a dual site facility which encapsulates the Advanced Manufacturing Institute (AMI) proposal and includes a siteat either Deeside Industrial Park or Northern Gateway (approx. 200m2 – exact location to be confirmed) focussed on light engineering,training and collaboration and one at Broughton (approx. 4,000-4,500m2) to focus on the larger scale ‘heavy end’ advanced manufacturing. | The AMRI concept builds on a body of work undertaken by the Deeside Enterprise Zone Board which identified a clear need for an AMI in the region. AMRI A will be completed in 2020 and the plans for AMRI B are in development.
Economic Development | Culture and Sport | 100 | 80 | 2019 | 2023 | Grant funding from the WG provided to Cadw and Welsh Government Sponsored Bodies, with some match funding from partners such as Local Authorities (LA). | The programme will invest in our cultural and sport offering, to deliver infrastructure investment in sports facilities, investment in income generating programmes at Cadw, the National Museums and the National Library and essential conservation and maintenance work on our monuments and museums.
Economic Development | Development Bank of Wales | 1000 | 700 | 2017 | Ongoing | The Development Bank of Wales is a WG owned subsidiary company. | The Development Bank of Wales marks a step change in Government backed funding for Welsh businesses and will fill the gap between the finance the private sector supplies and the funding Welsh businesses demand.
Economic Development | Enterprise Zone (EZ) delivery (includes an amalgamation of Sectors projects and projects delivered elsewhere in the plan e.g. Transport projects) | 350 | 215 | 2018 | Ongoing | Finance and delivery options vary across the individual projects which are listed separately in the report. | A programme for government commitment, Enterprise Zones (EZ) Boards have been established to provide advice on the most suitable and effective mechanisms for maximising economic opportunities in each EZ and set out individual strategic plans, which have been published at www.enterprisezones. wales.gov.uk. Current significant capital projects listed in this document also achieve aims of theEZ Strategic Plans, for example the Five Mile Lane Improvement Scheme, the Deeside Advanced Manufacturing Research Institute and the Ebbw ValeTechnology Park.
Economic Development | International Convention Centre Wales | 84 | 24 | 2017 | 2024 | Financed and delivered as a joint venture with Celtic Manor Resorts Limited. | This innovative development with the Celtic Manor Hotel will make a significant addition to the built environment of Wales, be the first iconic building visitors to Wales see as they drive into Wales, provide a significant boost to the South Wales economy and promote Wales on the UK and International stage.
Economic Development | Next Generation Access Broadband | 65 | 38 | 2018 | 2021 | To be financed by WG and European Funding. | The investment builds on the successful Superfast Cymru (SFC) project by continued deployment of superfast and ultrafast broadband infrastructure to premises that do not receive a minimum of 30MBps. across Wales. For every £1 of public money invested,Superfast Cymru generates an estimated £6.70 in net economic benefits for Wales and additional investment is anticipated to extend the reach of this benefit.
Economic Development | Parc Eirin | 30 | 1 | 2018 | Ongoing | Sister company to Ely Mill and part of the Tirion Homes Group will lead the venture usingan innovative investment model to unlock capital funding and build much needed affordable and open market housing. Construction of homes to commence before the end of 2019. | The scheme will deliver 225 homes, over 50% of which will be affordable. An Innovative Housing Programme Grant has been secured to develop Energy Positive homes which will, for part of the year, be a net exporter of electricity, contributing power to the National Grid. As a result, the homes will achieve near zero carbon emissions during their operational lifetime. Parc Eirin will be the largest energy positive housing project in the UK.
Economic Development | Porth Teigr | 386 | 38 | 2013 | Ongoing | Welsh Government and private sector investment. To date the Roath Lock Studios for BBC Wales and the 40,000 sq. ft Gloworks building have been completed. A termination notice was served on Igloo Regeneration Partnership for non-development and the site is now under the control of WG. A phased development over 12 years. | This strategic mixed use development will provide up to 2m2 ft on a site of circa 38 acres. There is now a master plan in preparation for the extension of the site to Alexandra Head at the edge of the barrage. There is the potential to develop more than 1,500 new homes, in addition to the commercial space but, subject to provision of sufficient infrastructure by the public sector. Work is currently being undertaken on the potential, and cost of taking a metro link from Cardiff Central Station to Porth Teigr, and the estimated land receipts if all the WG land is sold with the benefit of a metro link.
Economic Development | Sites and Premises | 300 | 200 | 2015 | 2026 | Finance and delivered through a combination of Welsh Government led interventions, joint venture arrangements or direct funding to our public and private sector delivery partners. The programme draws in match funding from both public and private sector partners as well as EU funding. | The Sites and Premises programme underpins many of the aspirations in Prosperity for All and theEconomic Action Plan by providing Wales with a state of the art industrial unit base to provide the right sites for Welsh business to grow and develop as well as competing for international investment with the rest of the UK and globally. The Sites and Premises programme will make a significant impact within theValleys Taskforce initiative.
Economic Development | South Wales Strategic Backhaul | 25 | 13 | 2019 | 2021 | Financed by WG and Building Digital UK. | Project to install fibre and ducting all the trunk roads of South Wales east of Cardiff.
Economic Development | Tech Valleys Programme (formerly called Automotive Technology Park) | 100 | 100 | 2018 | 2027 | The programme will comprise a range of stand-alone projects delivered over the short, medium and long term; it will seek to leverage additional public and/or private sector funding. | The Tech Valleys development in Blaenau Gwent will adopt a strategic approach alongside the Valleys Taskforce, the Swansea Bay City Region and Cardiff Capital Region city deals, and the UK Industrial Strategy. It has the potential to create 1,500 high quality jobs through significant investment to stimulate inclusive growth across the South Wales Valleys. A partnership with THALES Plc to deliver a National Digital Education Centre (NDEC) commenced in 2018.
Economic Development | The Mill | 100 | 6 | 2017 | 2023 | Joint WG private sector investment. Ely Bridge Development Company, a ‘Not for Profit’ organisation founded by WG and Principality Building Society,will lead the venture using an innovative investment model to unlock capital funding and build much needed affordable and open market housing. | The Mill project will provide 800 new homes, over 50% of which will be affordable, unprecedented for this type of development. Infrastructure works and the units in Phase A are complete. The construction of Phase B has commenced and is expected to be complete in Autumn 2020.
Economic Development | Thermal Hydraulic Research and Test Facility at Menai Science Park, Anglesey | 52 | 20 | 2018 | 2026 | The WG has the opportunity to collaborate with UK Government’s Department for Business, Energy and Industrial Strategy (BEIS) to deliver the projectas part of the UK Government’s nuclear research programme. The project requires in principle funding of up to £20m which levers in £32.55m match funding from BEIS. | The Thermal Hydraulic Research and Test Facility at Menai Science Park on Anglesey is a proposal to bring a major research and testing facility to North Wales that has a legacy expectancy of up to 50 years.
Economic Development | Tourism Fund | 50 | 10 | 2019 | 2023 | A Tourism Fund comprising a mixture of grant together with loan funding provided by the Development Bank of Wales to support investment in Wales’ tourism product. | The programme will invest in Wales’ tourism offering, to deliver investment in major hotels and visitor attractions across Wales. We are aiming to increase the number of high quality four star and five star accommodation; together with investment in ‘game changing’ attractions which will attract increasing number of visitors. The investment will create jobs during the construction phases and on an ongoing basis.
Economic Development | Whiteheads | 75 | 7 | 2018 | Ongoing | Sister company to Ely Mill and part of the Tirion Homes Group will lead the venture using an innovative investment model to unlock capital funding and build much needed affordable and open market housing. | The scheme will deliver over 250 affordable homes and 250 open market homes, together with land for a new school. The remediation contract has completed, and construction is expected to commence in late 2019.
Transport
The National Transport Finance Plan is a commitment to a five-year programme of road, rail, bus and active travel investments. Decarbonisation is at the heart of decision making for infrastructure developments.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Transport | A40 West of St Clears Improvement – Llanddewi Velfrey to Penblewin | 35 | 13 | 2016 | 2022 | Project will be delivered using a Design and Build contract. Procurement of contractor to commence spring 2020. European Regional Development Fund (ERDF) funding for approx. 65% of the overall project costs confirmed in December 2016. Remainder to be funded by the Welsh Government (WG). | Improvement of a 3.1 miles length of the existing single carriageway A40 to a 2+1 configuration to improve road safety as well as journey times and reliability. Second phase of the A40 west of St Clears improvement scheme which will improve access to the ports of Fishguard and Milford Haven, as well as the Haven Waterway Enterprise Zone.
Transport | A465 Heads of the Valleys Dualling Abergavenny to Hirwaun – Section 2 (Gilwern to Brynmawr) | 336.2 | 336.2 | 2014 | 2020 | Financed by the Welsh Government. Project being delivered by the Welsh Government via Costain using a Design and Build contract. Anticipated completion is the end of 2019 for the majority of the scheme, but some sections will extend into 2020. | Improvement of 4.97 miles of the existing A465 between Gilwern and Brynmawr.
Transport | Hirwaun – Section 5 (Dowlais to A470) and Section 6 (A470 to Hirwaun) | 440 | 440 | 2019 | 2024 | Financed through the WG innovative finance initiative Mutual Investment Model (MIM). Public Local Inquiry April 2018. Due to start on site in 2020. Anticipated completion by 2023. | Improvement of a 9.94 miles length of the existing A465 between Dowlais and Hirwaun from a single three lane carriageway to dual two lane carriageway and associated grade-separated junctions.
Transport | A483 Llandeilo | 50 | 50 | 2017 | 2022 | To be financed by WG and delivered by Transport for Wales (TFW). Completion of WelTag stage two by November 2019. Preferred route/detailed design 2019-20. | The investment will assist with congestion and air quality around Llandeilo. Transport appraisals currently being reviewed.
Transport | A487 New Dyfi Bridge | 42 | 42 | 2019 | 2020 | Financed and delivered by the WG. | New 0.75 miles trunk road to the north of Machynlleth to address flooding and resilience issues.
Transport | A487Caernarfon – Bontnewydd Bypass | 135 | 135 | 2019 | 2022 | Financed and delivered by the WG. | Bypass to the south, south east, east and north east of Caernarfon. The bypass will take traffic away from the congested areas of Dinas, Bontnewydd and Caernarfon.
Transport | A55 Junctions 15 and 16 | 54 | 18 | 2021 | 2022 | Delivered by the WG with European Regional Development Fund (ERDF) funding for circa 65% of the overall project costs confirmed in December 2016. Remainder to be funded by the WG. | Grade separation of two existing roundabout junctions on the A55 to improve safety and journey time reliability
Transport | A55 Third Menai Crossing | 130 | 130 | 2022 | 2026 | Financed and delivered by the WG in partnership with external partners. | A new crossing of the Menai Strait to improve safety, journey times and network resilience.
Transport | A55/A494/A458 Flintshire Corridor | 300 | 300 | 2022 | 2025 | Financed and delivered by the WG. | Improvement of approximately 7.45 miles of carriageway between Queensferry and Northop to address traffic congestion, resilience and safety issues in the Deeside area.
Transport | A55 Abergwyngregyn to Tai’r Meibion | 23.5 | 10 | 2020 | 2021 | Delivered by the WG with ERDF funding for circa 65% of the overall project costs confirmed in December 2016. Remainder to be funded by the WG. | Improvement of 1.37 miles of the A55 to address safety and flood risks.
Transport | Cardiff Interchange | 120 | 30 | 2017 | 2023 | Bus station to be funded by WG whilst wider development being funded by Private Sector. Start on site to be confirmed. | Will deliver a new public transport integrated hub in the centre of Cardiff.
Transport | Delivery of Pinch Point Schemes | 63 | 63 | 2017 | 2021 | Financed and delivered by the WG. | Delivery of pinch point schemes across Wales to tackle road based congestion. Funding total is for schemes delivered over the next four years. The delivery of pinch point schemes will be co-ordinated by the Welsh Government largely through the trunk road agents, but also through Local Authorities (LA). Includes £33m for trunk road schemes, £15m for local road improvements and £15m for north to south over taking improvements.
Transport | Five Mile Lane Improvement Scheme | 26.5 | 26.5 | 2018 | 2019 | Financed by the WG. Delivered in partnership with Vale of Glamorgan Council. | Due for completion Autumn 2019.
Transport | Grant funding for Local Authority transport projects | 30 | 30 | 2017 | Ongoing | Applications are being invited from all LAs and awarded on a competitive basis. Match funding required for Local Transport Fund. | This is an annual grant funding process (£30m). The grant areas include: Local Transport Fund, Road Safety (capital), Safe Routes in Communities. The projects will be delivered throughout the course of the year by LAs following successful bids for funding. The level of funding varies year on year subject to budget availability and schemes put forward.
Transport | Llanwern station | 50 | 50 | 2018 | 2021 | Financed and delivered by the WG. | Delivery of a new railway station at Llanwern along with stabilising lines and a major park and ride facility. The delivery of the new station will complement the significantly important Metro programme of activity.
Transport | North East Wales Metro | TBC | TBC | 2017 | Ongoing | Work is currently ongoing to develop a programme of investments focusing initially on key employment hubs across the region. Delivering the Metro vision will require significant funding beyond 2020-21 as it will inevitably involve delivering major infrastructure improvements. North East Wales Metro will be a combination of schemes that are already identified as stand alone projects within the pipeline and new schemes as they emerge. The initial focus has been on delivering active travel and bus infrastructure improvements in Deeside and Wrexham. | The vision for North Wales and the North East Wales Metro was published in March 2017.
Transport | Rollout of Integrated Active travel routes | 60 | 50 | 2018 | 2021 | To be financed by WG, with match funding from other sources including LAs and developer contributions. | The investment will improve infrastructure and develop sustainable active travel routes in local communities across Wales. The Active Travel Act 2013 places duties on LAs and WG to promote cycling and walking activity. This funding support increased activity levels across Wales.
Transport | South Wales Integrated Transport – Metro | 738 | 738 | 2017 | 2022 | Funding includes EU and Department for Transport (DFT) contribution provided through WG. Cost profile and delivery timescale currently being planned via Transport for Wales and the ODP. | Phase 2 of a new and potentially transformational scheme to create a South East Wales Metro system through better bus, rail and walking/cycling links. Proposals for additional new transformative projects are also under development. These strategic integrated investment projects will complement Metro Phase 2 to enhance planned outcomes of this key initiative.
Environment – Flood and Coastal Risk Management
Over this three year period the Welsh Government will invest £234m in flood and coastal assets. Continued investment reduces the risks from flooding and coastal erosion to people and properties around Wales. This is in line with our commitment in Taking Wales forward to “Continue to invest in flood defence work” and in the National Strategy to “actively manage the risks that climate change presents to health, well-being and to communities”. As well as this Capital investment, continued revenue is vital in order that we can maintain the assets already in reducing the risk of asset failure and flooding.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Flood & Coastal Risk | Flood and Coastal Erosion Risk Management Programme | 121.5 | 121.5 | 2017 | 2021 | Projects are led by Natural Resources Wales (NRW) and Local Authorities (LA). The Programme continues to invest in flood and coastal erosion risk management activities prioritised to areas of greatest risk. | Coastal and Main River schemes are led by NRW and are funded 100% through Grant in Aid. Coastal erosion, ordinary watercourse (stream) and surface water schemes are led by LAs and funded either at 75% (coastal scheme) or 85% (non-coastal schemes). Capital funding through this programme can also grant fund Natural Flood Management schemes led by either NRW or LAs.
Flood & Coastal Risk | Coastal Risk Management Programme | 150 | 112.5 | 2019 | 2022 | Coastal projects led by LA with 75% Welsh Government (WG) funding contribution provided through Local Government Borrowing Initiative. | The 25 schemes to progress through to construction phase were agreed in March 2019. Some schemes are due to commence construction within this financial year with the remainder in the development phase to commence in the next two financial years. Scheme progression subject to business case approval.
Environment – Waste
The Welsh Government’s Waste Infrastructure Procurement Programme was established in 2008 to help local authorities with the affordability of securing the necessary food and residual waste treatment infrastructure to support implementation of the Welsh Government’s waste strategy – Towards Zero Waste; meet EU landfill diversion targets; meet WG statutory recycling targets; and avoid the risk of infraction fines. All local authority procurements within the programme have now reached completion, with five anaerobic digestion plants built and operating, the Trident Park energy recovery facility operating in Cardiff, and the Parc Adfer energy recovery facility in construction in Deeside. A Welsh Government revenue funding contribution is paid quarterly as part of the agreed business model, which includes operation and maintenance of the facility as well as repayment of any capital finance over the contract term.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Waste | Central Wales Food Waste Project | 14 | 1.09 | 2012 | 2027 | Contract awarded to Agrivert. Anaerobic Digestion to secure a long-term, sustainable treatment solution for 17,000 tonnes pa of food waste. £1.09m (capital procurement support). | Hub formed by Powys and Ceredigion (Pembrokeshire joined November 2014).
Waste | North East Wales Food Waste Project | 7.3 | 2.22 | 2014 | 2027 | Contract awarded to Biogen. Project will secure a long-term, sustainable treatment solution for 22,500 tonnes pa of food waste. Anaerobic Digestion facility built and operating at Rhuallt, Denbighshire. £1.09m (capital procurement support) £1.13m (pre-payment gate fee support). | Hub formed by Denbighshire, Conwy and Flintshire.
Waste | South West Wales Food Waste Project | 14 | 1.98 | 2017 | 2032 | Contract awarded to Agrivert, securing long- term treatment for 19,000 tonnes pa of food waste at the Stormy Down facility, Bridgend. £1.98m (capital procurement support). | Hub formed by Swansea and Bridgend.
Waste | Heads of the Valleys Food Waste Project | 14 | 1.84 | 2018 | 2033 | Contract awarded to Agrivert, securing long-term treatment for up to 16,000 tonnes pa of food waste at the Stormy Down facility, Bridgend. £1.84m (capital procurement support). | Hub formed by Blaenau Gwent, Torfaen, and Monmouthshire.
Waste | Cardiff Food and Organic Waste Project | 8.2 | 0.94 | 2017 | 2032 | Contract awarded to Kelda Organic. Project will secure a long-term, sustainable treatment solution for 30,000 tonnes pa of food waste. Anaerobic Digestion facility built and operating at Tremorfa, Cardiff. £0.94m (capital procurement support). | Hub formed by Cardiff and Vale of Glamorgan.
Waste | Tomorrow’s Valley Food Waste Project | 7.3 | 2.89 | 2015 | 2028 | Contract awarded to Biogen. Project will secure a long-term, sustainable treatment solution for 22,500 tonnes pa of food waste. Anaerobic Digestion facility built and operating at Bryn Pica, Rhondda Cynon Taf. £1.57m (capital procurement support) £1.32m (pre-payment gate fee support). | Hub formed by Rhondda Cynon Taf, Merthyr Tydfil and Newport.
Waste | Prosiect GwyriAD Food Waste Project | 6.2 | 2.07 | 2013 | 2028 | Contract awarded to Biogen. Anaerobic Digestion facility at Llwyn Isaf built and services started in October 2013. Contract to secure a long-term, sustainable treatment solution for 11,000 tonnes pa of food waste. £1.04m (capital procurement support) £1.03m (pre-payment gate fee support). | Gwynedd Council.
Waste | Prosiect Gwyrdd (Residual Waste) | 223 | 1.52 | 2016 | 2041 | Contract awarded to Viridor for long-term treatment of 175,000 tonnes pa of residual waste. £1.52m (capital procurement support). £106.5m (revenue gate fee support over 25 years). | Consortium formed by Cardiff, Newport, Caerphilly, Vale of Glamorgan and Monmouthshire. A merchant Energy from Waste facility is operating at Trident Park in Cardiff.
Waste | North Wales Residual Waste Treatment Project | 180 | 1.36 | 2019 | 2045 | Contract awarded to Wheelabrator Technologies for long-term treatment of 117,000 tonnes pa of residual waste. £1.36m (capital procurement support) £140.5m (revenue gate fee support over 25 years). | Consortium formed by Gwynedd, Anglesey, Conwy, Flintshire and Denbighshire. The Parc Adfer energy recovery facility is under construction in Deeside.
Waste | South West Central Wales Residual Waste Treatment Project | TBC | TBC | TBC | TBC | Project is at feasibility stage. The LAs are working with the WG to scope a potential project and options are now being considered by the authorities. The LAs are in the process of procuring a technical advisor to lead a review of technical options and market feedback. | The local authorities in South-West Wales are considering options for the long-term treatment of their residual waste.
Waste | Tomorrow’s Valley Residual Waste Treatment Project | 1.82 | 1.59 | 2016 | 2041 | Contract awarded to Viridor for long-term treatment of 90,000 tonnes pa of residual waste. £1.59m (capital procurement support) £57.75m (revenue gate fee support over 25 years). | Consortium formed by Rhondda Cynon Taf, Merthyr Tydfil, Blaenau Gwent and Torfaen.
Energy
Improving the energy efficiency of the homes of low income households is the most effective way in which we can tackle fuel poverty, whilst also reducing harmful emissions into the environment. The Welsh Government is working to improve home energy efficiency and tackle domestic fuel poverty by investing in our energy efficiency Warm Homes programme, which includes Nest and Arbed. These schemes have been designed to leverage additional funding into Wales from the UK Government’s Energy Company Obligation (ECO). In addition Arbed is supported by £23.3m of ERDF funding. The programme supports the Welsh Government’s commitment to reduce climate change, help eradicate fuel poverty, boost economic development and regeneration in Wales.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Energy | Welsh Government Warm Homes Nest | 72 | 72 | 2017 | 2021 | Following a competitive tender process British Gas were awarded the Scheme Manager role for the Nest 2 contract on 1 April 2018. | Nest will continue to be a demand-led fuel poverty scheme that targets low income households living in the most energy inefficient homes. The scheme offers a range of advice and support to help households to reduce their energy bills and improve their health and wellbeing. The support provided also includes referrals for eligible households for a package of free home energy efficiency improvements. The scheme eligibility criteria has been extended to include households with a member who suffers from prescribed physical or mental condition.
Energy | Welsh Government Warm Homes Arbed | 47 | 23 | 2017 | 2021 | Following a competitive tender process Arbed am Byth, a joint venture between Everwarm and Energy Savings Trust, was appointed in May 2018 as the scheme manager for the Abed programme. | Arbed continues to deliver an area-based fuel poverty scheme that targets homes in areas where households are more likely to be in severe fuel poverty. The scheme provides households of primarily owner occupier tenure, with free home energy improvements and advice, helping to improve the energy efficiency performance of their homes, reducing household energy bills and tackling fuel poverty, reducing carbon emissions and creating jobs and growth in the energy efficiency sector.
Energy | Welsh Government Energy Service | TBC | 70 | 2015 | Ongoing | A mature pipeline of energy efficiency, renewable energy and heat projects has been developed in the Welsh Public Sector along with Welsh community developed renewable energy projects. WG capital is being deployed through recyclable funds. Future projects within public sector will continue to draw on this fund. We continue to work to promote shared ownership opportunities and innovate financing of projects across all sectors. | The Welsh Government Energy Service draws together previous energy services – Green Growth Wales, serving the public sector and the Local Energy Service, supporting community energy schemes. The aim is to increase and accelerate projects to deliver green investment in Wales. It focuses on encouraging investment in resource efficiency, renewable energy generation and heat projects. The Welsh Government Energy Service provides a suite of interventions across sectors to meet challenging investment and carbon dioxide emissions savings. Our support and low cost financial investments help generate financial and carbon savings from energy efficiency project for the public sector and revenue streams from Welsh owned renewable energy projects.
Housing
Housing was identified as one of the six priority areas in the Welsh Government’s national strategy Prosperity for All, and we committed to actions including delivering 20,000 affordable homes, introducing a Rent to Own scheme, supporting innovative housing and responding to an ageing population. We are supporting our housing ambitions through record investment totalling £1.7bn over this government term, which includes specific investment to support the objectives we have set out. Investment in housing provides support to the Welsh economy maintaining and supporting jobs in the construction industry and also the supply chain. Providing good quality housing helps tackle poverty (including fuel poverty), and improves educational achievement.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Housing | Social Housing Grant (SHG) Programme – Main Programme | 911 | 528 | Ongoing | Ongoing | Ongoing (rolling programme of development) SHG provides funding for affordable housing schemes. Grant is paid to Registered Social Landlords (RSLs) who are responsible for appointing contractors. Local authorities are responsible for deciding which affordable housing schemes are prioritised for funding and which RSLs develop and manage the schemes. | Schemes are planned three to five years in advance with flexible start dates.
Housing | Welsh Housing Partnership (WHP) | 75 | 15 | 2018 | 2021 | WHP is made up of four RSLs, Pennant Homes, Hendre Group, Seren Group and Grwp Cynefin. The WHP is a jointly owned “Special Purpose Vehicle” owned by the four members providing properties for intermediate rent. The model is relatively novel in that the Partnership will purchase the properties and then lease them back to the associations for a period of ten years. | WHP either purchases properties from the open market either recently completed or existing dwellings.
Housing | Physical Adaptation Grant (PAG) | 47 | 47 | Ongoing | Ongoing | PAG provides funding for adaptations to RSL tenants properties. The programme is demand led and responds to specific needs for adaptations such as stairlifts, level access showers and ground floor extensions. Annual programme £8m-£11m pa. | Adaptations helps tenants remain independent in their own home, should their circumstances change and also assists with delayed transfer of care which in turn provides savings to the Health and Social Care budgets.
Housing | Integrated Care Fund (ICF) | TBC | 105 | 2018 | 2021 | ICF supports the NHS, social care, housing providers and other partners to work together to provide accommodation led solutions to health and social care. Three year programme currently in place. | The funding provides accommodation led solutions for older people, people suffering with dementia, young people with complex needs and carers, and people with learning disabilities.
Housing | Housing Finance Grant (HFG) | 122 | 60 |  | 2016 | Over 1,000 homes will be delivered by this initiative. The houses are delivered by Registered Social Landlords (RSL) partners in much the same way as the SHG programme. Our HFG funding was subject to the RSLs taking one of the endorsed borrowing products which brought new sources of finance to the Welsh sector. | Investment in housing provides support to the Welsh economy maintaining and supporting jobs in the construction industry and also the supply chain.
Housing | Housing Finance Grant 2 (HFG2) | 263 | 263 | 2017 | Ongoing | It is anticipated that over 1,500 homes will be delivered by this initiative. The second phase of HFG2 has been made available to RSLs, including Large Scale Voluntary Transfer organisations (LSVTs) and retaining stock local authorities. For RSLs and LSVTs HFG2 will be blended with SHG so that each scheme will be part funded by both grants to ensure fairness across the sector. Unlike HFG1, involvement in a collective finance product is not mandatory, but is being explored in order to drive down the price of borrowings by accessing finance from the capital markets. | Investment in housing provides support to the Welsh economy maintaining and supporting jobs in the construction industry and also the supply chain.
Housing | Innovative Housing Programme | 500 | 90 | 2018 | 2021 | The programme aims to support the development of innovative designs of housing in Wales. Following an Initial phase in 2017-18; the full programme was rolled out in 2018-19 for two years. | Investment in housing provides support to the Welsh economy maintaining and supporting jobs in the construction industry and also the supply chain. Data gathered by Chartered Institute of Housing shows that every £1.00 spent on energy efficiency saves around £0.42 in health costs, so £1m invested saves around £400,000 over ten years. The data also indicates every £1.00 spent improving homes where residents are likely to require treatment due to excess cold saves the NHS £34.19 over ten years. In other words, £1m saves £34m over ten years.
Housing | Help to Buy – Wales Shared Equity Scheme Phase II | TBC | 290 | 2016 | 2021 | Help to Buy – will require deposits from individuals and mortgage funding. The scheme opened for equity loan funding in September 2016 and will close to new investments during 2021. | The scheme is available all over Wales and open to all potential buyers of new build properties costing no more than £300,000 who have a minimum 5% deposit.
Housing | Rent to Own | TBC | 70 | 2018 | Ongoing | Capital grant of £70m will be paid to Registered Social Landlords across all of Wales to deliver new homes that will be available for Rent to Own or Shared Ownership. It is anticipated that 1,000 homes will be delivered by this scheme. | The scheme will be available across Wales and will help people access homeownership who cannot currently do so on the open market or through Help to Buy.
Housing | Welsh Housing Quality Programme Major Repairs Allowance (MRA) | 2000 | 108 | 2004 | Ongoing | MRA – £60.4m allocation of capital grant for 2018-19. Paid to local authorities to fund capital repairs to their housing stock. Dowry – £47.6m – allocation for 2018-19. Paid to LSVTs as gap funding in support of the stock transfer business plan. Dowry budget includes a provision of £3.8m to fund local authorities pre-ballot costs in the event that tenants vote against transfer. | Payments for MRA capital grant are made to individual local authorities each year subject to acceptable 30 year business plans. Payments for Dowry are made to Large Scale Voluntary Transfer (LSVT) organisations each year, subject to annual review of the LSVTs business plan. Individual dowry gap funding agreements will vary but dowry support is generally agreed on a two year rolling basis, subject to annual review of the business plan. There is an expectation for dowry to be paid for up to a period of 30 years. However, the WG is only legally committed to the two year rolling agreement.
Housing | Land for Housing Scheme | 170 | 52 | 2014 | Investment is recycled for 15 years | The scheme is open to RSLs who can apply for loan funding to secure land sites for development of affordable and/or market housing. | The loan fund is recycled throughout the term of the programme once loans are repaid. Delivered by Housing Associations, it is contributing to increasing the supply of housing by enabling RSLs to purchase land for housing development.
Housing | Wales Property Development Fund | 270 | 32 | 2017 | Investment is recycled for 15 years | This loan scheme is delivered by the Development Bank of Wales. It is targeted at Small to Medium Enterprises (SME’s) across Wales for small-medium scale property development projects. | Through the WPDF, we provide financing to SMEs for sites which have already passed the planning stages, and where the developers need capital for the construction phase. As such it is limited in being able to address some of the issues SMEs have in making some sites available for development.
Housing | Wales Stalled Sites Fund | 160 | 40 | 2018 | Investment is recycled for 17 years | This loan scheme is delivered by the Development Bank of Wales. It is targeted at SMEs across Wales for small-medium scale property development projects that are stalled-sites. | The WSSF is designed to assist in creating and promoting development opportunities to SME construction companies, and unlocking the sites which provide wider benefits to the local communities in which they are located.
Housing | Self Build Wales | 210 | 40 | 2019 | Ongoing | This loan scheme is delivered by the Development Bank of Wales. £10m is being provided as loans to local authorities for plot preparation, £30m is being provided as loans for applicants to the scheme. Funding provided in 2018-19 to assist with scheme development. Scheme due to go live in Autumn 2019. | The scheme is designed to provide loan funding to prospective self builders to build their own homes. The scheme will enable applicants to build up to 30% equity in their homes by removing the profit margins typically gained by major house builders. The scheme will also encourage SMEs back into house building.
Housing | Gypsy and Traveller sites | 26.4 | 26.4 | 2014 | 2021 | Schemes are funded by capital grant from the Welsh Government with local authorities then responsible for the maintenance and management of the sites. | There is a significant under supply of Gypsy and Traveller sites in Wales. The scheme up until 2020-21 should provide up to 170 new pitches across Wales, which could more than halve the shortfall. The required level of continued funding was reviewed in 2017 in response to approved local authority Gypsy and Traveller Accommodation assessments, which found a need for 270 new pitches across Wales, This funding programme is broadly in line with needs (with an expectation that approximately 100 pitches will be provided by private individuals) and will continue until 2021.
Regeneration
The Welsh Government’s regeneration programme, Targeted Regeneration Investment Programme, sets the direction for the allocation of up to £100m to be delivered across Wales over the next three years, 2018-21. The programme will support projects that promote economic regeneration with activities focused at individuals and areas most in need, whilst serving the aims of wider sustainable development. The new programme explicitly highlights the importance of widening prosperity, with jobs, growth and people at the heart of this approach.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Regeneration | Town Centre Loans Fund | 90 | 31 | 2014 | Ongoing | The scheme has to date approved funding of £31.5m from the Welsh Government (WG) up to 2018-19. The scheme is administered by Local Authorities (LA) and delivered through third parties. | The aim of the scheme is to act as a catalyst to bring vacant and underutilised buildings back into use and support diversification in town centres. Currently the loan scheme is supporting 30 town centres across Wales.
Regeneration | Property Loans (formally Houses into Homes and Home Improvement Loans) | 120 | 40 | 2012 | Ongoing | The schemes have to date approved funding of £40m from the WG. The funding is available over a 15 year period and should be recycled three times during this period. The scheme is administered by the LA’s. Houses into Homes started in 2012 and Home Improvement Loans started in 2014. | The aim of these schemes is to provide LA’s with capital funding to provide financial assistance to owner occupiers and private sector landlords to improve properties and bring empties back into use through the use of loans or grants. The schemes are available to all LA’s.
Regeneration | Building for the Future | 120 | 16 | 2017 | 2023 | Building for the Future will assist in the regeneration of town centres and the surrounding areas, supporting a regional or urban economic strategy by tackling derelict, under-utilised land or buildings. It will acquire, refurbish or re-develop unused buildings and land within or closely aligned to town and city centres across Wales, creating jobs and growth and contributing to the tackling poverty agenda. The programme is being delivered via a combination of £38m European Regional Development Funding (ERDF) and £16m Targeted Match Funding (TMF) supplied by the Homes and Places Division Welsh Government. | The WG will work with local authority and private sector partners to invest in prioritised empty buildings and under-utilised land sites that have worked to undermine investor confidence. Whilst support will be awarded to partners to renew buildings and develop vacant sites, funding is allocated and underpinned on the basis of there being sustainable and economic end uses. Whilst many of the 40 projects within the programe are yet to be fully appraised the key outputs, reported by partners, are as follows: 1,800 jobs accommodated 650 jobs created.
Regeneration | Targeted Regeneration Investment programme | 300 | 100 | 2018 | 2021 | Welsh Government funding matched through public and private sector funding. In most cases, projects and programmes are delivered by LA partners. | The aim of this programme is to support projects in target areas that promote economic regeneration with activities focused at individuals and areas most in need, whilst serving the aims of wider sustainable development. The programme explicitly highlights the importance of widening prosperity, with jobs, growth and people at the heart of this approach. The design of the new programme aims to align the regeneration agenda with local government reform and other emerging priorities that are being brought forward on a regional basis (for example, Valleys Taskforce) across Government. Alongside the resource available the regions have developed regional plans, identifying priorities for investments that reflect regional strengths and opportunities through collaboration.
Education
The 21st Century Schools and Education Programme is giving the Welsh Government the opportunity to address much needed improvement to our educational infrastructure which will provide the best learning environments for our pupils and are suitable for delivery of a 21st century curriculum. A significant part of the estate requires improvement either to improve building condition, to make schools more suitable for the delivery of the curriculum or to provide sufficient places while ensuring the most effective use of resources. The first wave of the programme represents an investment of more than £1.4bn to deliver band A over the five year period ending 2018-19. All 22 local authority areas will benefit which will result in the rebuild and refurbishment of over 150 schools and colleges across Wales. The second phase of the Programme, launched in April 2019, will see anticipated investment of £2.3bn across Wales. This will support an estimated 200 projects to rebuild and refurbish schools and colleges. The grant intervention rate for capital investment has been increased for the second wave, to 65% for schools; with 75% and 85% for special schools and voluntary aided schools respectively. This will ease the financial burden on local authorities. The individual scheme allocations detailed are subject to change based on an annual evaluation of each programme. The programme very much aligns with the Welsh Government’s national strategy Prosperity for All, Taking Wales Forward and Education in Wales: Our national mission as it provides appropriate environments for the delivery of excellent teaching and learning.
Sector | Project/Programme | Total scheme value (est.£m) | Welsh Government support (est.£m) | Start Date | End Date | Finance and delivery | Additional information
Education | 21st Century Schools Programme Band A – All Wales | 1400 | 700 | 2013 | 2019 | Local Authority (LA) and Welsh Government (WG) funding. Match funding of 50% provided by the Welsh Government, subject to the receipt and approval of business cases for individual projects. Whilst the majority of projects have been completed any ongoing investments are detailed within the relevant LA section. | The programme is designed to improve schools and colleges in poor condition, reduce surplus capacity and improve standards through the provision of an environment that is able to deliver a 21st century curriculum.The second wave of investment was recently announced and is being developed with our partners.This began in 2019 and includes funding through both traditional capital and £500m investment enabled through revenue funding, via the MIM.
Education | 21st Century Schools and Colleges Programme Band B – All Wales | 2300 | 1220 | 2019 | 2024 | LA and WG funding. Match funding provided by the Welsh Government will be dependant on the nature of the education facility but at a minimum of 65%. This is subject to the receipt and approval of business cases for individual projects. | The programme is designed to improve schools and colleges in poor condition, reduce surplus capacity and improve standards through the provision of an environment that is able to deliver a 21st century curriculum. Beginning in 2019 and includes funding through both traditional capital and £500m investment enabled through revenue funding, via the MIM.
The schemes listed below represent 'in principal' levels of funding for individual local authorities and colleges from the second wave funding of the All Wales 21st Century Schools and Colleges programmes. Actually levels of investment may change as business cases are approved.
Education | Anglesey 21st Century Schools and Colleges Programme | 36.14 | 23.49 | 2019 | 2024 | The WG will meet £23.49m of the total scheme cost, with the remainder from Anglesey LA.
Education | Blaenau Gwent 21st Century Schools and Colleges Programme | 19.6 | 12.74 | 2019 | 2024 | The WG will meet £12.74m of the total scheme cost, with the remainder from Blaenau Gwent LA.
Education | Bridgend 21st Century Schools and Colleges Programme | 68.2 | 45.31 | 2020 | 2024 | The WG will meet £45.31m of the total scheme cost, with the remainder from Bridgend LA.
Education | Caerphilly 21st Century Schools and Colleges Programme | 110.3 | 51.6 | 2019 | 2024 | The WG will meet £51.60m of the total scheme cost, with £26.86m from Caerphilly LA and £31.84m via MIM.
Education | Cardiff 21st Century Schools and Colleges Programme | 284 | 164.76 | 2019 | 2024 | The WG will meet £164.76m of the total scheme cost, with £74.04m from Cardiff LA and £45.20m via MIM.
Education | Carmarthenshire 21st Century Schools and Colleges Programme | 129.5 | 75.725 | 2019 | 2024 | The WG will meet £75.725m of the total scheme cost, with £36.775m from Carmarthenshire LA and £17m via MIM. | Projects approved to date in Carmarthenshire LA include Ysgol Pum Heol and Ysgol Pembrey.
Education | Ceredigion 21st Century Schools and Colleges Programme | 13.7 | 8.9 | 2019 | 2024 | The WG will meet £8.90m of the total scheme cost, with the remainder from Ceredigion LA.
Education | Conwy 21st Century Schools and Colleges Programme | 43.1 | 2.7 | 2019 | 2024 | The WG will meet £2.70m of the total scheme cost, with £1.20m from Conwy LA and £39.2m via MIM.
Education | Denbighshire 21st Century Schools and Colleges Programme | 80.5 | 56.11 | 2019 | 2024 | The WG will meet £56.11m of the total scheme cost, with the remainder from Denbighshire LA.
Education | Flintshire 21st Century Schools and Colleges Programme | 85.4 | 56.02 | 2019 | 2024 | The WG will meet £56.02m of the total scheme cost, with the remainder from Flintshire LA. | Projects approved to date in Flintshire LA include Connah’s Quay High School (Phase 3).
Education | Gwynedd 21st Century Schools and Colleges Programme | 56.1 | 37.46 | 2019 | 2024 | The WG will meet £37.46m of the total scheme cost, with the remainder from Gwynedd LA. | Projects approved to date in Gwynedd LA include Ysgol Cymerau.
Education | Merthyr Tydfil 21st Century Schools and Colleges Programme | 56.58 | 42.45 | 2019 | 2024 | The WG will meet £42.45m of the total scheme cost, with the remainder from Merthyr Tydfil LA.
Education | Monmouthshire 21st Century Schools and Colleges Programme | 45.4 | 29.6 | 2019 | 2024 | The WG will meet £29.6m of the total scheme cost, with the remainder from Monmouthshire LA.
Education | Neath Port Talbot 21st Century Schools and Colleges Programme | 67.2 | 43.68 | 2019 | 2024 | The WG will meet £43.68m of the total scheme cost, with the remainder from Neath Port Talbot LA. | Projects approved to date in Neath Port Talbot LA include Cefn Saeson Comprehensive.
Education | Newport 21st Century Schools and Colleges Programme | 70 | 45.5 | 2019 | 2024 | The WG will meet £45.5m of the total scheme cost, with the remainder from Newport LA.
Education | Pembrokeshire 21st Century Schools and Colleges Programme | 106.4 | 63.44 | 2019 | 2024 | The WG will meet £63.44m of the total scheme cost, with £35.19m from Pembrokeshire LA and £7.77m via MIM.
Education | Powys 21st Century Schools and Colleges Programme | 113.9 | 73.52 | 2019 | 2024 | The WG will meet £73.52m of the total scheme cost, with the remainder from Powys LA. | Projects approved to date in Powys LA include Ysgol Gymraeg y Trallwng.
Education | Rhondda Cynon Taf 21st Century Schools and Colleges Programme | 167.4 | 52.92 | 2019 | 2024 | The WG will meet £52.92m of the total scheme cost, with £29.00m from Rhondda Cynon Taff LA and £85.48m via MIM. | Projects approved to date in Rhondda Cynon Taf LA include New Hirwaun Primary School.
Education | Swansea 21st Century Schools and Colleges Programme | 149.7 | 93.45 | 2019 | 2024 | The WG will meet £93.45m of the total scheme cost, with £41.01m from Swansea LA and £15.23m via MIM. | Projects approved to date in Swansea LA include the EOTAS unit.
Education | Torfaen 21st Century Schools and Colleges Programme | 45.9 | 35.44 | 2019 | 2024 | The WG will meet £35.44m of the total scheme cost, with the remainder from Torfaen LA.
Education | Vale of Glamorgan 21st Century Schools and Colleges Programme | 166.8 | 76.18 | 2019 | 2024 | The WG will meet £76.18m of the total scheme cost, with £58.76m from Vale of Glamorgan LA and £31.86m via MIM | Projects approved to date in Vale of Glamorgan LA include Whitmore High School, Ysgol Bro Morgannwg and Barry Waterfront.
Education | Wrexham 21st Century Schools and Colleges Programme | 88.7 | 23.99 | 2019 | 2024 | The WG will meet £23.99m of the total scheme cost, with £12.67m from Wrexham LA and £52m via MIM.
Education | Bridgend Colleges 21st Century Schools and Colleges Programme | 30.46 | 19.8 | 2019 | 2024 | The WG will meet £19.8m of the total scheme cost, with the remainder from Bridgend College.
Education | Coleg Sir Gar 21st Century Schools and Colleges Programme | 25 | – | 2019 | 2024 | Coleg Sir Gar intend to meet their programme via MIM.
Education | Coleg Gwent 21st Century Schools and Colleges Programme | 59.4 | 2.21 | 2019 | 2024 | The WG will meet £2.21m of the total scheme cost, with £1.19m from Coleg Gwent and £56m via MIM. | Projects approved to date in Coleg Gwent LA include New Catering Facilities at the Usk Campus.
Education | Coleg y Cymoedd 21st Century Schools and Colleges Programme | 9.5 | 6.18 | 2019 | 2024 | The WG will meet £6.18m of the total scheme cost, with the remainder from Coleg y Cymoedd.
Education | Coleg Cambria 21st Century Schools and Colleges Programme | 40 | 28.87 | 2019 | 2024 | The WG will meet £28.87m of the total scheme cost, with the remainder from Coleg Cambria. | Projects approved to date in Coleg Cambria LA include Yale Technology Hub.
Education | Grwp Llandrillo Menai 21st Century Schools and Colleges Programme | 50.27 | 32.68 | 2019 | 2024 | The WG will meet £32.68m of the total scheme cost, with £17.59m from Grwp Llandrillo Menai. | Projects approved to date in Group Llandrillo Menai LA include Glynllifon Small Animal Care.
Education | Merthyr Tydfil College 21st Century Schools and Colleges Programme | 4.5 | 2.93 | 2019 | 2024 | The WG will meet £2.93m of the total scheme cost, with the remainder from Merthyr Tydfil College.
Education | Cardiff and the Vale College 21st Century Schools and Colleges Programme | 34 | – | 2019 | 2024 | Cardiff and the Vale College intend to meet their programme via MIM.
Education | Pembrokeshire College 21st Century Schools and Colleges Programme | 7.34 | 4.77 | 2019 | 2024 | The WG will meet £4.77m of the total scheme cost, with the remainder from Pembrokeshire College. | Projects approved to date in Group Llandrillo Menai LA include Animal Care facility, to create flexible classroom accommodation and engineering block remodelling.
Education | Gower College Swansea 21st Century Schools and Colleges Programme | 26.07 | 16.95 | 2019 | 2024 | The WG will meet £16.95m of the total scheme cost, with the remainder from Gower College Swansea.
Education | NPTC Group 21st Century Schools and Colleges Programme | 37.08 | 6.97 | 2019 | 2024 | The WG will meet £6.97m of the total scheme cost, with £3.75m from NPTC Group and £26.36m via MIM.
Education | St David’s College 21st Century Schools and Colleges Programme | 5.98 | 3.89 | 2019 | 2024 | The WG will meet £3.89m of the total scheme cost, with the remainder from St David’s College.
Education | Flying Start (expansion) | 57.76 | 57.76 | 2012 | 2019 | A budget of £566k has been allocated for essential maintenance works in 2018-19. | Flying Start is an integral part of the Welsh Government’s tackling poverty programmes and is featured in the new Government’s Taking Wales Forward set out to help 36,000 children aged 0-4, living in some of Wales’ most disadvantaged communities by giving them the best possible start in life. The WG is currently reviewing the way the Flying Start programme is being delivered.
Education | 21st Century Schools and Education Programme: Community Learning Centres | 30 | 15 | 2018 | 2020 | Pilot Schemes will be identified and delivered through the 21st Century Schools and Education Programme.
Health and Social Care
We are looking at investing £1.5bn in the estate of the NHS in Wales over this government term in all aspects of health care. This investment covers new primary and community care centres, improved and upgraded facilities within hospitals, state of the art equipment for both diagnostics and the treatment of patients, new ambulances, plus major capital projects throughout Wales. Within the Welsh Government’s national plan for Health and Social Care – A Healthier Wales – a key aim is to provide better quality and more accessible health and social care services.
Sector | Project/Programme | Total scheme value (est.) | Welsh Government support (est.) | Start Date | End Date | Finance and delivery | Additional information
Health & Social Care | Welsh Ambulance Services Trust – Ongoing Vehicle replacement | 127 | 127 | 2018 | 2028 | WG funding annually subject to business case WG funding annually subject to business case Programme (SOP) has been endorsed by Welsh Government (WG) and covers annual vehicle replacement. | The Trust has an ambitious service improvement programme, modernising the way front-line services are delivered with a view to improving general efficiency. The specific aim of the fleet programme is to support and enhance the new model of operational practice and service delivery whilst generating maximum efficiency from an improved fleet.
Health & Social Care | Hywel Dda University Health Board – Cardigan, New Health and Social Care Centre | 21 | 21 | 2018 | 2019 | WG funding. Full Business Case (FBC) approved in 2018 and the new facility should be completed by the end of 2019. | The Health Board’s new facility will replace Cardigan Hospital and nearby Primary Care/GP facilities.
Health & Social Care | Velindre Hospital Redevelopment | 210 | 210 |  |  | The Health Board’s new facility will replace Cardigan Hospital and nearby Primary Care/GP facilities. | Mutual Investment Model. SOP endorsed and Outline Business Case (OBC) in development.
Health & Social Care | Aneurin Bevan University Health Board – Grange University Hospital (GUH) | 350 | 350 | 2018 | 2021 | WG funding. The FBC has been approved and work is progressing. The project is due to complete in 2021. | This major new hospital combines emergency, critical care and specialist services in the Gwent area onto one site in Torfaen. This will involve a substantial reconfiguration and remodelling of existing services and the subsequent retention of Neville Hall and Royal Gwent Hospitals as Local General Hospitals.
Health & Social Care | Cwm Taf University Health Board – Prince Charles Hospital, Merthyr Tydfil, Refurbishment, Ground and 1st Floor | 225 | 225 | 2018 | Ongoing | WG funding subject to business case approval. Phase 1a has now been completed and works have commenced on Phase 1b – completion expected in 2021. The FBC for Phase 2 is currently undergoing scrutiny. | This investment will ensure compliance with Health and Safety standards, improve service efficiency, quality and productivity, in line with the wider Cwm Taf HB clinical and financial strategic direction and redesign clinical areas, to provide flexible, safe and welcoming accommodation.
Health & Social Care | Cardiff and Vale University Health Board – Neonatal facilities at University Hospital Wales | 45 | 45 | 2016 | 2019 | WG funding. All business cases approved – phase 1 complete 2016 – phase 2 completed 2018 and phase 3 – the installation of the MRIs will be completed in Summer 2019. | The investment will see the improvement and expansion of the Neonatal facilities at UHW plus the re-provision of MRI facilities with further shell space for two additional scanners, one of which would offer a specialist cardiac MRI service.
Health & Social Care | All Wales Scheme – Primary Care Pipeline | 72 | 72 | 2018 | 2021 | WG funding. | A pipeline of 19 primary and community care projects across Wales to be delivered by 2021. The projects look to invest in a new generation of health and integrated care centres which are a key commitment in Taking Wales Forward and a cornerstone of the Health Policy in Prosperity for All. WG are now working with NHS bodies to progress the development of business cases to allow for implementation and delivery. Of 15 planned capital projects, one is complete, four will complete in 2019-20, and business cases for the others are being finalised.
Health & Social Care | Cardiff and Vale University Health Board – Reprovision of Specialist Neuro and Spinal Rehabilitation and Clinical Gerontology Services | 30 | 30 | 2019 | 2021 | WG funding. The FBC has been approved and works have now commenced on University Hospital Llandough (UHL), Cardiff Royal Infirmary (CRI) and St Davids (SDH) sites. The project is due to complete in 2021. | The programme will see facilities for specialist neuro and spinal rehabilitation services on the UHL site which would be fully integrated with the existing medical services; the centralisation and consolidation of South Cardiff Outpatient Physiotherapy, together with the Occupational Therapy (OT) and Speech and Language Therapy (SLT) services, into a single re-furbished clinic at CRI; and, the move of the elderly care Older People’s Acute and Intermediate Care (OPAIC) services to SDH.
Health & Social Care | Hywel Dda University Hospital Wales – Neonatal Facilities at Glangwilli Hospital – Phase 2 | 26 | 26 | 2018 | 2020 | WG funding. The FBC was approved in Spring 2018 – works have commenced and will be completed by 2020. | Phase 2 is intended to address the urgent areas identified within the Royal College report and to provide a safe and appropriate permanent environment for the delivery of obstetric and neonatal services at Glangwili.
Health & Social Care | Betsi Cadwaladr University Health Board – North Denbigh Community Hospital | 40 | 40 | 2020 | 2022 | WG funding. The OBC has been approved and the FBC will be submitted in early 2020. | The scheme will deliver a range of expanded and redesigned services on and around the Grade II listed Royal Alexandra Hospital site in Rhyl, Denbighshire. The new development will help to alleviate the pressure on services at Ysbyty Glan Clwyd.
Health & Social Care | Betsi Cadwaladr University Health Board – Redevelopment of the Mental Health Inpatient Unit at Ysbyty Glan Clwyd | 26 | 26 | 2021 | 2023 | WG funding. The SOC has been endorsed. The OBC is expected in early 2020 and the FBC in early 2021. The works are anticipated to complete in early 2023. | The scheme is for the re-development of the Unit for in-patient mental health patients at Ysbyty Glan Clwyd.

## Annex 2 Local Authority
Annex 2 – Welsh Local Authority Project Pipeline
The following section incorporates a collation of all Welsh local authority (LA) schemes where the total estimated value of the scheme exceeds £2m; and the scheme is currently being delivered, or planned to start in the next three years.It should be noted, due to the way some schemes are funded, there is some overlap between Welsh Government (WG) data and LA data (for example, the 21st Century Schools and Education Programme is part funded by the WG and partlyself-funded by local authorities). Figures are estimates based on most current data available and rounded to two decimal places.
Local Authority | Project/ Programme | Total Scheme Value (est £m) | Start date | End date | Finance and delivery | Additional information
Blaenau Gwent | Highway Improvement Works | 3.6 | 2018 | 2020 | £2.1m Local Authority (LA),£1.5m Welsh Government (WG). | Resurfacing of various routes throughout the Borough.Location: Various locations throughout the Borough.
Blaenau Gwent | Lime Avenue | 6.5 | 2018 | 2020 | £2.5m EU, £3.5m WG, £0.5m LA. | Create Hybrid business units on the former works site in Ebbw Vale to provide new accommodation to support the development of small and medium enterprises to enhance job creation in the area. Location: Ebbw Vale.
Blaenau Gwent | Ebbw Vale Northern Corridor | 1.1 | 2014 | 2024 | £1.1m WG/EU – Sewer Enhancement works. WG, Social Housing Grant and Private Sector Investment unknown at this stage. | Create a series of developments that complement and enhance the vibrancy of Ebbw Vale as a sustainable community. Residential development, improved economic opportunity, and leisure facilities. The Ebbw Vale Enterprise Zone Sewer Enhancement Works will enable sites along the Ebbw Vale Northern Corridor to become ready for development.Location: Ebbw Vale.
Blaenau Gwent | Cardiff Capital Region City Deal (CCRCD) | 5.5 | 2017 | 2027 | £5.54m Blaenau Gwent County Borough Council (BGCBC) capital funding contribution based on population share of £120m total LA contribution. | The total CCRCD (excluding the Metro) is £495m and encompasses ten LAs with Cardiff Council being the Lead Authority. £375m funding has been committed by UK Government and £120m is to come from the ten LAs. Projects and Programmes are currently being developed.
Blaenau Gwent | 21st Century Schools | 26 |  | 2026 | LA and WG funding – Delivery ongoing. WG funding total £19m. | Location: Various throughout the Borough.
Blaenau Gwent | Childcare | 4.1 | 2019 | 2021 | WG £4.1m | To construct early years establishments. Location: Various throughout the Borough.
Blaenau Gwent | National Digital Exploitation Centre | 4.1 | 2019 | 2021 | WG £4.1m. | Create a National Digital Exploitation Centre.Location: Ebbw Vale.
Bridgend | 21st Century Schools – Band B | 52 | 2019 | 2027 | £25m Local Authority (LA), £27m Welsh Government (WG). | Locations to be determined.
Bridgend | Street Lighting replacement | 2.5 | 2018 | 2021 | £2.5m LA (via Salix loan). | Upgrade to LED lanterns for Street Lighting columns in various locations across the Borough.
Bridgend | Enterprise Hubs | 3.5 | 2018 | 2022 | £2.3m ERDF, £1.2m LA. | Project will include refurbishment of Innovation Centre and construction of new industrial units. Construction works to commence in 2019-20.
Bridgend | Bridge Strengthening – A4061 Ogmore Valley | 2.45 | 2016 | 2020 | LA £2.45m. | Location: Ogmore Valley.
Bridgend | Extra Care Housing | 3 | 2017 | 2020 | LA £3m. | Linc is working with Bridgend Council towards the delivery of two new Extra Care schemes in the Borough. Both schemes have Residential Care facilities on the ground floor with Extra Care flats above along with communal facilities. This includes a total of 70 units, comprised of 45 extra care units and 25 residential care units. Location: Heol-yr-Ysgol, Bridgend. Bridgend Road, Maesteg.
Bridgend | Carriageway and Footway renewals | 4 | 2018 | 2020 | LA £4m. | Various Highways Infrastructure improvements across the Borough.
Bridgend | Porthcawl Resort Investment Focus | 2.5 | 2016 | 2021 | ERDF £1.6m, WG £0.3m, LA £0.6m. | Project includes the construction of a new Watersports Centre at Rest Bay, Porthcawl. In construction phase during 2019-20.
Caerphilly | Highways Improvements | 2.23 | 2019 | 2022 | Local Authority (LA) funding of £2.23m. | Enhancement limited to incorporating modern engineering techniques and practices in order to maximise life of carriageway and minimise future maintenance costs. Priority given to strategic routes; carriageways with high expenditure on temporary repairs and carriageways that generate high volume of third party claims. Works progressing.
Caerphilly | Welsh Housing Quality Standard (WHQS) | 233 | 2017 | 2020 | 2019-20 spend is likely to be £56.62m. Funded by: MRA £7.4m; Revenue contribution £17.04m and prudential borrowing £32.18m. | No actual borrowing has been undertaken for Welsh Housing Quality Standard (WHQS) as yet, Authority has internally borrowed. Works progressing.Location: Countywide.
Caerphilly | Corporate Buildings | 2.07 | 2019 | 2022 | LA £2.07m. | Corporate Asset Management to enhance/ upgrade Council buildings as part of maintenance/ improvement plans. Various small buildings/works rather than a major project. Works progressing. Location: Countywide.
Caerphilly | Mandatory Disabled Facilities Grant | 3.4 | 2019 | 2022 | LA £3.40m. | Grants to individuals to adapt private properties. 2019-20 budget anticipated to be fully expended. Location: Countywide
Caerphilly | Home Repair Grant – vulnerable persons (Private housing) | 2.34 | 2019 | 2022 | LA £2.34m. | Grants to individuals for essential or emergency repair. Works progressing. Location: Countywide.
Caerphilly | Corporate Projects | 10.53 | 2019 | 2022 | LA £10.53m. | Funding set aside for projects. Projects yet to be identified. Location: Countywide.
Caerphilly | Salix Street lighting Programme | 4.25 | 2019 | 2021 | Salix loan approved £4.14m. £110k Caerphilly County Borough Council (CCBC) own funding (streetlighting capital budget). | Scheme commenced in March 2019. Replacement of all existing street lighting across County with LED technology.
Caerphilly | European Regional Development Fund (ERDF) – Ty Du | 2.05 | 2019 | 2021 | CCBC Match £360k; WG Grant £350k; ERDF grant £1.34m. | Ty Du, Nelson has been identified as a Welsh Government Strategic Employment site.In October 2016 outline planning permission was granted to develop a major mixed use development on the Welsh Government ownedsite. The masterplan for the site comprises a mixed use development of up to 200 dwellings and upto 3.8 hectares of B1 employment floor space.An opportunity has presented itself for the Council to work jointly with WG to deliver employment units at Ty Du.
Caerphilly | ERDF – Lawns Industrial Estate – units | 2.2 | 2019 | 2021 | CCBC Match £710k; ERDF grant £1.49m. | New construction of industrial units at Lawns Industrial estate Rhymney. Overall the proposed project will focus on unlocking, over two phases, approximately 1.3 hectares of underutilised brownfield land located at the southern endof the Council owned Lawn Industrial Estate. When fully developed, the land has the potential to accommodate approximately 20 small modern business units.
Cardiff | 21st Century Schools and Education Programme Band B | 194.6 | 2019 | 2024 | Local Authority (LA)/Welsh Government (WG) per intervention rates – Estimated total cost envelope/ procurement route not yet confirmed. | WG Band B funding subject to approval, Councils own funding for a variety of schemes to improve school facilities and infrastructure in Cardiff. Location: Countywide
Cardiff | Property Asset Renewal – Schools | 25.9 | Ongoing | Ongoing | LA £25.9m – Framework/In-house Facilities Management. | To address the condition of the property stock within the Council in accordance with Directorate Asset Management plans and priority works. Location: Countywide.
Cardiff | Property Asset Renewal – Non Schools | 7 | Ongoing | Ongoing | LA £7m – Primarily use of In-house Facilities Management section. | To address the condition of the Non Schools property stock within the Council in accordance with Directorate Asset Management plans and priority works. Location: Countywide.
Cardiff | Schools Suitability and Sufficiency | 3 | Ongoing | Ongoing | LA £3m – Framework contractors. | To cater for increasing accessibility issues in schools. Make provision for pupils with accessibility needs, address rising pupil numbers and works required to improve facilities in schools that are not part of the 21st Century Schools programme. Location: Countywide.
Cardiff | Reducing Infant Class Sizes | 2.5 | 2019 | 2020 | WG £2.5m – Framework Contractors. | To create the necessary additional space required to deliver the foundation phase in reduced infant size classes.
Cardiff | Welsh Medium Education | 3.8 | 2019 | 2021 | WG £3.8m – Framework Contractors. | To support capital investments that will facilitate growth in Welsh medium education and use of the Welsh language.
Cardiff | Highways and Footways Resurfacing | 17.3 | Ongoing | Ongoing | LA £13.9m – Framework contractors. WG Grant £3.4m. | Allocation for highway and footway resurfacing and reconstruction, including addressing the condition of tree roots and tree pits on footways and implementation of dropped kerbs. Location: Countywide.
Cardiff | Highway Structures | 3.7 | Ongoing | Ongoing | LA £3.7m – External contractors on a project by project basis due to specialist requirements. | The strengthening or replacement of sub standard bridges, culverts and other highways structures as part of the Highway Infrastructure Asset Management plan. Location: Countywide.
Cardiff | Millennium Walkway | 2.2 | 2019 | 2021 | LA £2.2m – Framework contractors. | To replace the timber surface of the Millennium Walkway, which is coming to the end of its expected lifespan, with new timber or alternative materials.The walkway provides a link between Wood Street and Cowbridge Road East, along with access and egress for the Principality Stadium.
Cardiff | Street Lighting inc Energy efficiency | 8.3 | 2019 | 2021 | LA £8.3m – External contractors. | Column replacement, replacement LED residential lighting and electrical works as part of the Highway Infrastructure Asset Management plan. Location: Countywide.
Cardiff | Traffic Management, Public Transport, Telematics and Butetown Tunnel | 7.6 | Ongoing | Ongoing | LA £7.6m – Framework contractors. | Strategic and local network improvements including junction and pedestrian safety improvements,with a focus on securing match funding. Telematics infrastructure replacements required for the ongoing operation of the tunnel and transportation infrastructure. A new bus interchange in the West of the City and the design and implementation of priority transport and air quality schemes.Location: Countywide.
Cardiff | Transport grants from Welsh Government (WG) | 15.1 | Ongoing | Ongoing | WG £15.1m – Framework contractors. | Active travel, casualty reduction and other grants from WG. Grant is bid for and distributed on an annual basis so future years are estimates only. Location: Countywide.
Cardiff | Strategic Cycle Network Development | 9.8 | Ongoing | Ongoing | LA £9.8m – Framework contractors. | Implementation and match funding of the cycling strategy. Various existing cycle routes and to create network improvements or missing links between routes. They include the installation of cycle parking and network improvements as well as supporting match funding towards WG Grants and active travel. Location: Countywide.
Cardiff | Cardiff Capital Region City Deal – Council contribution to Investment Fund | 5.2 | Ongoing | Ongoing | LA £5.2m/Other LA’s/WG/HMT – Delivery Routes to be determined on a project by project basis. | Council contribution to Investment fund. Location: Regional.
Cardiff | Coastal Erosion | 2.9 | Ongoing | 2022 | LA £2.2m, WG £0.7m. | A scheme to manage flood and erosion risk at the estuary of the Rhymney River, including protection of landfill material, key road infrastructure and the Rover Way Travellers Site – Initial WG grant towards design costs. Implementation works are subject to design, estimates of total cost and successful WG grant award.
Cardiff | Roath Park Dam and Roath Park District Area | 3 | Ongoing | 2023 | LA £3m – Framework contractors. | Works are deemed required as part of the Reservoir Act 1975 following an inspection report and requirements of Natural Resources Wales.Cost is subject to option appraisal, detailed design of recommended option and impact on other features of this Grade 1 listed Historic Park. Other schemes to improve financial sustainabilityof the park and outbuildings.
Cardiff | Waste Management Infrastructure | 3.9 | Ongoing | Ongoing | LA £3.9m – External contractors. | Development of a new Household Waste Recycling Centre, Material Recycling Facility and other waste management and collection infrastructure.Expansion of the separate glass collection service citywide subject to satisfactory performance of the existing trial.
Cardiff | Solar Farm | 5.2 | Ongoing | 2019 | LA £5.2m – External contractors. | Development of a facility at former Lamby Way landfill and a further investment opportunity to provide a direct energy supply to a neighbouring organisation improving the current Solar farm viability and enabling a large 7.5MW solar farm. Location: East Cardiff.
Cardiff | New Cemetery | 2.9 | Ongoing | 2020 | LA £2.9m – External contractors. | Development of a new facility to meet requirements for burial space. Location: North Cardiff.
Cardiff | Energy Schemes | 6.7 | Ongoing | 2024 | LA £6.7m – Framework contractors. | Scheme to install energy efficiency measuresin existing Council buildings. To create infrastructure to support a district heat network. Location: Countywide.
Cardiff | Disabled Facilities Service (inc Public Housing) | 20.6 | Ongoing | Ongoing | LA £20.6m – Framework Contractors. | To provide adaptations such as showers, stairlifts and internal modifications to allow the recipient to live independently within their own home. Location: Countywide.
Cardiff | Community/Neighbourhood Regeneration | 3.5 | Ongoing | Ongoing | LA £3.5m – External Contractors. | To implement improvements to local shopping centres and the associated public realm, including accessibility improvements, with the aim of providing an enhanced retail environment and improved business activity. Improvements to the city’s oldest and worst condition housing stock including energy efficiency. Also to fund owner occupier costs of improvements to housing and boundary walls. Location: Countywide.
Cardiff | Modernising ICT to Improve Business Processes | 3.7 | Ongoing | Ongoing | LA £3.7m – External contractors/In house staff on a project by project basis. | Investment in technology projects including: Server Refresh, Resilience, Electronic DocumentManagement System, and Digitisation, allowing the Council to make business process improvements and so improve directorate service delivery. Location: Countywide.
Cardiff | Public Housing | 183.2 | 30 year business plan | Ongoing | LA £146.6m, WG Grant and Contributions £36m – External Contractors and Housing Maintenance service. | Investment in Estate regeneration, stock remodelling, maintaining Welsh Housing Quality Standards and new build programme. Location: Countywide.
Carmarthenshire | 21st Century Schools Band A | 86.7 | 2013 | 2021 | Local Authority (LA) £43.35m and Welsh Government (WG) £43.35m. | Location: Countywide.
Carmarthenshire | 21st Century Schools Band B | 129.5 | 2019 | 2026 | LA £40m and WG £89.5m. | Location: Countywide.
Carmarthenshire | Highway Improvements | 5.99 | 2018 | 2024 | LA £3m (five years) and WG Grant Funding £2.99m (2018-19 and 2019-20) – Various – in house and external contractors. | Reconstruction and resurfacing of carriageways to address backlog of repairs. Location: Countywide.
Carmarthenshire | Highway Bridge Strengthening | 2 | 2019 | 2024 | LA £2m – Various – in house and external contractors. | Construction and upgrading of highway bridges. Location: Countywide.
Carmarthenshire | Cross Hands Economic Link Road Phase 2 | 14.7 | 2015 | 2021 | LA £3.08m, Grant funding £11.62m. | New road from Black Lion Road to the A476 NE of Gorslas. The road will ease congestion at the A48 Cross Hands roundabout and the Six ways junction at Gorslas and provide direct access to the Cross Hands East Strategic Employment Site. Location: Cross Hands. SA14.
Carmarthenshire | Tywi Valley Transport Corridor Concept | 7.5 | 2015 | 2022 | LA £2.85m, Grant funding £4.65m. | Improved access for cyclists and walkers to key tourist attractions along the lower Tywi valley (Carmarthen to Llandeilo).Location: Lower Tywi valley.
Carmarthenshire | Walking and Cycling Linkages | 6.5 | 2015 | 2022 | LA £0.43m, WG Grant funding £6.07m. | Development of a network of walking and cycling linkages to improve access to employment, education and other services. Location: Countywide.
Carmarthenshire | Rural Enterprise Fund | 4 | 2016 | 2021 | LA £2m, Grant Funding £2m. | The Grant will provide assistance to enterprises and sole traders for the development of new and existing business premises. Location: Countywide.
Carmarthenshire | Transformation Commercial Property Development Fund | 6.66 | 2016 | 2021 | LA £3m, Grant Funding £3.66m. | The funding is to be made available to enable developers to meet the financial gap between the construction costs and the completed market value of the property. Location: Countywide.
Carmarthenshire | County Regeneration Fund | 22.5 | 2019 | 2024 | LA £7.5m, External funding £15m – various – in house and external contractors. | Collaboration project with private, public and third sectors working together to deliver the economic regeneration of the County’s strategic employment sites, primary town centres, market towns,valley growth zones and coastal belt. Location: Countywide.
Carmarthenshire | Swansea Bay City Deal – Llanelli Wellness Village | 40 | 2019 | 2022 | LA £40m. Potential private sector investment, but not secured. External contractors. | A £200m health and leisure project which has planning permission. The wellness and life science village in Llanelli was backed by Carmarthenshire councillors in January. £40m of public funding available. Location: Llanelli.
Carmarthenshire | Llanelli Leisure Centre | 16.5 | 2019 | 2022 | LA £12m, WG/Joint Venture £4.5m. In House design, with framework partners as contractors. | Construction of new Leisure Centre in Llanelli in conjunction with the Llanelli Wellness Village. Location: Llanelli.
Carmarthenshire | Llanelli Area Review | 7 | 2019 | 2022 | LA £7m. | Review of care provision in the Llanelli area in conjunction with the Llanelli Wellness Village. Location: Llanelli.
Carmarthenshire | Carmarthen County Museum Abergwili | 2.28 | 2015 | 2021 | LA £0.25m, Grant and other funding £2.03m. | Led by the Welsh Historic Trust the scheme will deliver improvement/enhancement works at the Carmarthenshire County Museum site and adjacent walled garden at the Bishop’s Palace. Improvements will be made to the museum out-buildings and the grounds. Location: Abergwili.
Carmarthenshire | Housing Revenue Account | 89.4 | 2019 | 2022 | LA £70.8m and WG £18.6m – In house and external contractors. | Improvements to Council housing stock over the three year period, including work to deliver the Carmarthenshire Homes Standard. Location: Countywide.
Carmarthenshire | Capitalised Maintenance | 14.6 | 2019 | 2024 | LA £14.60m – Various – in house and external contractors. | Capitalised maintenance of all Authority buildings including offices, schools and social care establishments. Location: Countywide.
Carmarthenshire | Disabled Facility Grants | 10.2 | 2019 | 2024 | LA £10.2m – External contractors and Care and Repair agency. | Statutory requirement to provide these grants under the Housing Grants, Construction and Regeneration act 1996. Location: Countywide.
Carmarthenshire | IT Strategy Developments | 2.5 | 2019 | 2024 | LA £2.5m – Led by the corporate IT section with departmental input. | Improving and maintaining IT provision within the authority in line with national requirements and the corporate IT strategy. Location: Countywide.
Carmarthenshire | Carmarthenshire Archive Relocation | 2.62 | 2016 | 2020 | LA £2.5m, Grant Funding £0.12m. External Contractors. | Re-location of archived documents to an appropriate building. Location: Countywide.
Ceredigion | Replacement Vehicle Programme | 3.5 | 2019 | 2020 | Local Authority (LA) Capital Programme. | This is a phased programme over a number of years to deliver revenue savings associated with fleet management. The entire refuse collection fleet will be replaced during 2019-20, and subsequent years’ programmes will focus on replacement of smaller vehicles, with consideration given to more sustainable/electric vehicles.
Ceredigion | Highways Refurbishment Programme | 2.1 | 2019 | 2020 | Welsh Government (WG) funded highways refurbishment programme. | There is a need for continued and ongoing investment in the highway network in order that its condition remains fit-for-purpose and itsimprovement is in accordance with the requirements of the Wellbeing of Future Generations Act (WFGA). WG has acknowledged this need/requirement through funding capital investment of refurbishmentof the highway network.
Ceredigion | Coastal Risk Management Programme | 19 | 2019 | 2020 | Two LA schemes currently included on the programme which is 75% WG funding and 25% LA funding. | Funding for the delivery of coastal erosion and flooding defence schemes at Aberaeron and Aberystwyth under the WGs Coastal Risk Management Programme.
Ceredigion | Sewage Treatment Works (STWs) Improvement Programme | 6 | 2011 | 2021 | LA £4.25m, Tai Ceredigion £1.85m – Work being delivered in packaged phases. | The Council has 27 STWs including a pumping station which are a legacy of the housing stock transfer undertaken in November 2009. The Council is upgrading all sites to Welsh Water standards and then going through the adoption process to get each one formally adopted and transferred to Welsh Water.
Ceredigion | Cylch Caron – Integrated Community Resource Centre Tregaron | 13 | 2013 | 2021 | Project finance (to be formally approved) includes remaining funding from Delivery Partner Mid Wales Housing Association (MWHA) Local Authority (LA) and Hywel Dda University Health Board (HDUHB. Total scheme value at Full Business Case (FBC) c£13m. | Cylch Caron is a Ceredigion Local Service Board priority project and led by Ceredigion County Council in partnership with the Hywel Dda University Health Board. Land purchased, Delivery Partner appointed (Mid Wales Housing Association). Construction tender process complete and draft full business case submitted for WG consideration. Location: Tregaron.
Ceredigion | 21st Century Schools – Band B | 13 | 2019 | 2024 | WG funding 65% of the programme and the rest from the LA. Projects currently being developed. | This is a phased project spanning a number of academic and financial years. This grant will be used to fund an extension and refurbishment at Aberteifi Secondary school, refurbishment of Cardigan Primary school and fund the new Dyffryn Aeron Area school.
Ceredigion | WG Capital Childcare Grant | 3.26 | 2019 | 2021 | Funding is 100% WG grant. | The Capital Childcare Grant programme aims to provide up to £200k in small grant schemes for childminders and childcare providers. The Grant will also assist with childcare provision and wrap around childcare for the new Dyffryn Aeron school, an extension to Cenarth school to provide childcare provision and wrap around childcare and a purpose new building to replace mobile provision for Henry Richard and Ffrindiau bach yr Eos, Penparcau for the current childcare provision and wrap aroundchildcare.
Conwy | 21st Century Schools Programme – Ysgol Yr Enfys | 4 | 2017 | 2019 | Welsh Government (WG) £1.87m, Local Authority (LA) £2.09m: Local Government Borrowing Initiative (LGBI) revenue support/prudential borrowing/ capital receipts. | Part of the 21st Century Schools programme. On revised target. Location: Caerhun.
Conwy | 21st Century Schools Programme – Band B – Mutual Investment Model Financed | 38.67 | 2017 | 2024 | Mutual Investment Model Financing (MIM) 81% WG Funding £29.75m and 19% LA Funding £6.98m. Land Purchase funded at 65% WG £1.26m and 35% LA £0.68m. | Capelulo, Abergele, Llanfairfechan, Towyn/Kinmel Bay, Rhos on sea, Llanddulas. All projects are in design and approval stage. Expenditure profile TBC. Includes £1.94m Land Purchase requirement at 65% WG Funding.
Conwy | 21st Century Schools Programme – Band B – Capital Financed | 4.43 | 2019 | 2024 | Traditional Capital Financing 75% WG funding for special/PRU and 65% for Mainstream. £3.05m WG grant and £1.38m LA Funding. | Deganwy, Llandudno, PRU location TBC. All projects are in design and approval stage. Expenditure profile TBC.
Conwy | Maintain/Improve Condition of County Road Network | 7.11 | 2013 | Ongoing | LA £4.21m supported borrowing, £0.07m Reserve, £1.13m Prudential Borrowing, £1.69m WG Grant. | Conwy Highways maintenance works. Improve condition of County road network and surface dressing of existing highways network.Location: Countywide.
Conwy | Projects Match Funding | 8.31 | 2013 | Ongoing | LA £8.31m match funding to lever in other funding streams. Individual contractors appointed for schemes or contributions made towards community schemes. | The Projects match funding provision is a provision which can be applied for where match funding for grants from external bodies is required. The provision can also provide funding for community groups for various projects. Location: Countywide.
Conwy | Vehicle and Plant Replacement Programme | 10.71 | 2013 | Ongoing | LA prudential borrowing £9.88m and £0.83m Conwy council capital reserve. | Location: Countywide.
Conwy | Carbon Management Plan | 2.44 | 2013 | 2019 | LA prudential borrowing £2.44m. Individual contractors appointed for work packages. | Original four year circa £2m plan to be extended. Total additional prudential borrowing funding to be confirmed.Location: Colwyn Bay Leisure Centre Combined Heat and Power Unit LED Lighting in Corporate and Education Buildings. Thermal Efficiencies in Corporate and Education Buildings, Smart meters, Street Light Lantern Replacement Renewal Energy Improvements.
Conwy | New Waste Transfer Station | 2.48 | 2017 | 2021 | £0.55m Supported Borrowing, £0.66m Prudential Borrowing, £1.26m Regional Partnership Funding. | Currently delayed whilst final details are clarified.Location: Mochdre.
Conwy | Conwy Modernisation Project | 10.5 | 2014 | 2020 | Funding is £1.10m capital receipts, £7.83m Reserves/Borrowing and £1.57m WG Invest 2 Save Loan. | Corporately managed project. This involves the office accommodation strategy for Conwy CBC to reduce the number of buildings used as office space to three key buildings fit for purpose and set up following the ‘hot desk’ model and modern work practices.Location: Countywide.
Conwy | Delivery of Adaptations in Private Sector Housing | 10.2 | 2013 | Ongoing | LA £9.61m and £0.59m WG – No contract involved. Individual grant payments to property owners for disabled facilities. Statutory requirement – adaptations to allow individuals to remain in their own homes. | Location: Countywide.
Conwy | Cultural Centre Co-locating Area Library and Archive Extension | 3.88 | 2015 | 2019 | £0.74m Supported Borrowing, £0.83m Prudential Borrowing, £0.53m Internal Match Funding, £0.5m Capital Receipts, £0.01m Section 106, £0.75m HLF grant, £0.3m Museums, Archives and Libraries Grant (MALD) grant, £0.04m WCVA grant, £0.12m Rural Community Development Fund (RCDF) grant, £0.05m Private Donations. | Location: Conwy.
Conwy | Colwyn Bay Townscape Heritage Initiative | 3 | 2013 | 2019 | WG £1.13m, HLF £0.80m, LA £0.43m, Cadw Grant £0.06m, Private Owners contributions £0.6m. Grant payments for work by individual contractors. | Private Owner’s contribution paid direct to contractors. Location: Colwyn Bay.
Conwy | Accommodation – Mochdre Building Works | 4.3 | 2015 | TBC | £2.7m Prudential Borrowing, £0.98m Capital Receipts, £0.3m Capital Reserve, £0.29m Carbon Reduction Savings, £0.04m Partner Contribution. | Project delayed. Full details and re-profile TBC.
Conwy | Parc Eirias Development Phase 2 | 2.7 | 2015 | 2020 | £0.15m Supported Borrowing, £0.62m Prudential Borrowing, £0.5m Revenue Contribution, £0.30m Collaborative Fund Grant, £0.34m WG Capital Loans for Sports Facilities Scheme, £0.05m Section106, £0.05m WRU, £0.15m VVP, £0.52m Sport Wales grant, £0.01m Betsi Cadwalader UHB. | Current approved projects complete except for Barn and Gym Flooring which is to complete in 2019-20. Further projects in development stage for 2020-21 and beyond.
Conwy | Relocation of Civic Amenity Site/ Highways Depot | 3.8 | 2017 | 2021 | £0.25m Supported Borrowing, £3.07m Unsupported Borrowing, £0.48m Capital Receipts. | Currently delayed whilst site purchase issues are clarified. Location: Llanrwst.
Conwy | Streetlighting Poles Replacement | 1.58 | 2012 | Ongoing | £1.58m Supported Borrowing. | Programmed alongside the replacement of lanterns funded from Salix loan and part of the Carbon Management Strategy. Location: Countywide.
Conwy | Programme to Strengthen Sub-Standard Bridges and Structures | 3.08 | Ongoing. Finance included from 2016/17 onwards | Ongoing programme | £3.08m Supported Borrowing. | Location: Countywide.
Conwy | Penmaen Road Employment Site | 4.03 | 2018 | 2021 | £1.5m ERDF Grant and £2.53m Prudential Borrowing. | Location: Conwy. Project ongoing with revised timetable.
Conwy | 30 Hour Child Care Grant and Welsh Medium Child Care Provision Grant | 5.43 | 2019 | 2021 | £0.30m WG grant for Small Grant Offer, £1.23m for Welsh Medium Childcare Grant Offer, £3.9m for 30 Hour Child Care Grant Offer. Funding for minor works/extensions to existing school buildings to facilitate the additional 30 hour child care offer. | Location: Llanfairtalhaiarn, Llandudno Junction, Colwyn Bay, Conwy, Llandudno, Glan Conwy, Capelulo, Llanddulas, Llanfaifechan, Kinmel Bay, Towyn.
Conwy | Venue Cymru Reconfiguration | 2.8 | 2017 | 2019 | WG TMF Funding £0.6m, ERDF Funding £0.8m, LA Internal Funding £1.4m. | Location: Llandudno.
Conwy | Coastal Risk Management at Llanfairfechan | 1.89 | 2019 | 2021 | £1.41m WG grant and £0.47m Prudential Borrowing. | Location: Llanfairfechan.
Conwy | Coastal Risk Management at Penrhyn Bay | 3.13 | 2019 | 2021 | £2.35m WG grant and £0.78m Prudential Borrowing. | Location: Penrhyn Bay.
Conwy | Colwyn Bay Waterfront Ph 2B | 14.23 | 2019 | To be confirmed but hoped to complete within 3 years of start date | £3.55m Prudential Borrowing, £1.79m Supported Borrowing, £10.5m WG grant requested. Full funding package and project timescale is in approval process. | Location: Rhos on Sea.
Conwy | Colwyn Bay Waterfront Ph 3 – North Wales Coastal Improvement Programme | 31.97 | 2019 | To be confirmed but hoped to complete within 3 years of start date | £0.12m Supported Borrowing, £2.0m Prudential Borrowing, £0.28m WG grant, £29.56m Third Party contributions TBC. Full project funding and approval ongoing. | Location: Old Colwyn.
Conwy | Flood Alleviation Schemes – Construction Phase | 2 | 2019 | 2020 | £0.21m Prudential Borrowing and £1.19m WG grant for Eldon Drive. £0.09m Prudential Borrowing and £0.51m WG grant for Maes Hyfryd. | Location: Eldon Drive, Abergele and Maes Hyfryd, Glan Conwy.
Conwy | Education Buildings Maintenance Grant | 1.42 | 2019 | 2020 | £1.42m WG grant. | Location: Countywide.
Conwy | Rectifications of Bridges and Structures Following Adverse Incidents | 4.5 | 2019 | Ongoing | £4.5m Prudential Borrowing. | Will be a programme of work to rectify infrastructure following adverse incidents/severe weather etc. Location: Countywide.
Conwy | Programme of Maintenance of Bridges and Structures | 1.14 | 2019 | 2020 | £0.40m Supported Borrowing for structures to be identified as the financial year progresses,£0.50m Supported Borrowing for A470 Overline Bridge Bearing Replacement, £0.1m WG grant for Pont Hendre Ddu Repairs, £0.15m Supported Borrowing for Coed Cochion Bridge Repairs. | Location: Countywide.
Denbighshire | 21st Century Schools – Band A | 91.41 | 2013 | 2019 | The Modernising Education programme has been included with the 21st Century Schools programme, with additional funding from Welsh Government (WG). | Six schools in the programme are completed, with building works for the remaining two scheduled to complete in 2019. Location: Countywide.
Denbighshire | 21st Century Schools – Band B | 80.5 | 2019 | 2026 | WG approval in principle. Initial feasibility works in progress. | Location: Countywide.
Denbighshire | Schools Capital Maintenance | 4.06 | 2019 | Ongoing | Ongoing works. Local Authority (LA) funding. | Location: Countywide.
Denbighshire | Highways Maintenance | 8.57 | 2019 | 2021 | Highways Maintenance programme is funded by Denbighshire County Council (DCC). An additional £2.38m has been awarded by WG for the period 2018-2021. | A new corporate plan 2017-2022 has recently been approved by the Council. Detailed development on schemes for inclusion in the plan is ongoing. Location: Countywide.
Denbighshire | East Rhyl Coastal Defence | 29.17 | 2017 | 2021 | Design stage now complete. Construction phase is subject to funding. | £29m scheme. Funding: 75% WG, 25% DCC.
Denbighshire | Housing Revenue Account (HRA) – Planned Improvements | 14.2 | 2019 | Ongoing | Assumes £2.41m Major Repairs Allowance (MRA). | Location: Countywide.
Denbighshire | Extra Care | 6 | 2014 | 2021 | Discussions are on- going at the moment between the Council and Private Sector Partners. No schemes have been approved to date. | Part of the Council’s Corporate Plan which sets out Council priorities over the next five years. £6m is Council’s contribution.
Denbighshire | Remodelling Waste Service | 14.77 | 2018 | 2021 | WG approved funding £7.9m. Design stage in progress. | Segregated kerbside weekly recycling service, along with four weekly residual waste collection.
Denbighshire | Queens Market Redevelopment, Rhyl | 5 | 2018 | 2020 | Acquisition of Queens Market by the Council in March 2019. WG/WEFO Grants totalling £5m. | Currently working up plans for the site with Development Partner.
Denbighshire | Rhyl Town Centre Contemporary Living and Independent Retail | 2.34 | 2018 | Ongoing | WG Targeted Regeneration Investment £1.32m, DCC £1.02m. | Acquisition, full redevelopment and renovation of three town centre properties to provide for business space and housing.
Denbighshire | West Rhyl Housing Project Ph 1 | 4.63 | 2018 | Ongoing | WG Targeted Regeneration Investment £0.91m, DCC £3.2m, Housing Group £0.52m. | Redevelopment and Renovation of properties in West Rhyl.
Flintshire | Leisure and Libraries buildings | 3.9 | 2015 | 2019 | LA £3.9m. | Location: Various Flintshire Leisure Centres and Libraries.
Flintshire | School Buildings R&M | 4.5 | 2016 | 2020 | LA £4.5m. | Ongoing programme c£1.5m pa to address backlog in schools R&M. Location: Countywide.
Flintshire | Investment Schemes – Education and Youth | 7.3 | 2019 | 2021 | Additional funds for WG under Reduction Infant Class Size Grant approved. | School extensions and remodelling Castell Alun High, Hope £5m. Glan Aber Primary, Bagillt £2.3m.
Flintshire | Corporate Property Maintenance | 2.4 | 2016 | 2020 | LA £2.4m. | Ongoing programme c £0.3m pa to address Statutory/Regulatory requirements. Ongoing programme c £0.3m pa to address Remediation and Maintenance backlog in corporate buildings.Location: Countywide.
Flintshire | Marleyfield Elderly Persons Home | 7 | 2020 | 2022 | LA £7m. | Location: Buckley.
Flintshire | Croes Atti Elderly Persons Home | 10 | 2021 | 2023 | LA £10m. | Location: Flint.
Flintshire | Theatre Clwyd | 25 | 2021 | 2023 | LA/WG/Arts Council for Wales (ACW) £25m. | Location: Mold.
Flintshire | Early Years Programme | 5.3 | 2020 | 2022 | WG £5.3m. | Location: Various Schools Flintshire.
Flintshire | 21st Century Schools Band B Programme | 84 | 2019 | 2024 | LA/WG £84m. | Location: Various Schools Flintshire.
Flintshire | B5129 – Proposed Bus Priority Measures and Transport Infrastructure | 4.2 | 2019 | 2021 | WG £4.2m. | Queensferry Roundabout to Denbighshire Border.
Flintshire | Cycling links, active travel and bus infrastructure | 3 | 2018 | 2020 | WG £3m. | Deeside Industrial Park.
Flintshire | Holywell Town/Greenfield Valley walking and cycling links | 2 | 2018 | 2021 | WG £2m. | Construction of active travel paths, providing links between Holywell and Greenfield facilitating access to areas of leisure and employment.
Gwynedd | 21st Century Schools – Band A | 12.73 | 2018 | 2021 | Welsh Government (WG) will meet around 50% of the total scheme cost. | The 21st Century Schools programme is an investment in strategic projects across the schools estate in each Local Authority (LA) area. Figures shown are for an addition to the original schemes which commenced in 2018.Location: Bangor.
Gwynedd | 21st Century Schools – Band B | 56.14 | 2019 | 2025 | WG will meet around 65% of the total scheme cost. | The second tranche of the 21st Century Schools programme is an investment in strategic projects across the schools estate in each LA area.Figures shown for three year period 2019-22. Location: Countywide.
Gwynedd | Housing Grants | 3.9 | 2019 | 2022 | LA £3.9m – Payments to individual property owners for disabled facilities etc. | Location: Countywide.
Gwynedd | Capitalised Repairs and Maintenance | 3.58 | 2019 | 2020 | LA £3.58m – Individual contractors appointed for work packages. | Location: Countywide.
Gwynedd | Penygroes Health and Care Hub | 3.5 | 2019 | 2023 | LA £3.5m – Individual contractors appointed for work packages. | Location: Penygroes.
Isle of Anglesey | 21st Century Schools – Band A | 33.44 | 2013 | 2021 | 50% Local Authority (LA) and 50% Welsh Government (WG) funding – Delivery ongoing. | Band A of the 21st century schools programme, focusing on four projects across the island.Location: Various Schools on Anglesey.
Isle of Anglesey | 21st Century Schools – Band B | 52.41 | 2018 | 2026 | 35% LA and 65% WG funding – Delivery ongoing. | Band B of the 21st century schools programme, focusing on six projects across the island. Location: Various Schools on Anglesey.
Isle of Anglesey | Targeted Regeneration Investment Programme (TRIP) | 3.25 | 2018 | 2021 | 70% WG, 30% Private Sector or LA. | Programme targeting empty properties to bring them back into use. Anglesey CC is the lead body for Anglesey and Gwynedd.
Isle of Anglesey | Housing Revenue Account – Various schemes | 13.79 | Ongoing | Ongoing | MRA Grant – £2.65m HRA – £11.14m –Delivery ongoing. | There are a number of schemes involved with the HRA including Planned Refurbishment of Council Dwellings, Acquisition of Existing Properties and Public Sector Adaptations. The HRA budget varies from year to year. Location: Anglesey.
Isle of Anglesey | Strategic Employment Sites | 3.87 | 2017 | 2021 | ERDF – £2.27m, WG – £1.6m. | Provision of new Industrial units. Location: Holyhead.
Merthyr Tydfil | 21st Century Schools Band A | 18.82 | 2013 | 2020 | Local Authority (LA) and Welsh Government (WG) funding. | Location: Merthyr Tydfil.
Merthyr Tydfil | 21st Century Schools Band B | 53.61 | 2020 | 2026 | LA and WG funding. | Location: Merthyr Tydfil.
Merthyr Tydfil | Riverside Project | 13.65 | 2014 | 2020 | £6.95m LA, £6.7m WG. | Location: Merthyr Tydfil.
Merthyr Tydfil | Highways Improvement | 4.13 | 2019 | 2023 | £4.13m LA. | Location: Merthyr Tydfil – Countywide.
Merthyr Tydfil | Disabled Facilities Grants | 3.4 | 2019 | 2023 | £3.4m LA. | Location: Merthyr Tydfil – Countywide.
Merthyr Tydfil | Town Centre Regeneration Programme | 11.28 | 2019 | 2023 | £0.78m LA. £10.5m External funding. | Location: Merthyr Tydfil.
Merthyr Tydfil | Cyfarthfa Park Heritage | 28.62 | 2019 | 2023 | £1.62m LA. £27m External funding. | Location: Merthyr Tydfil.
Merthyr Tydfil | Vibrant and Viable Places | 7.55 | 2019 | 2023 | £1.55m LA. £6m External funding. | Location: Merthyr Tydfil.
Merthyr Tydfil | Bus Station | 10.65 | 2019 | 2023 | £0.65m LA. £10m External funding. | Location: Merthyr Tydfil.
Merthyr Tydfil | Infrastructure Projects | 1.68 | 2019 | 2023 | £1.68m LA. | Location: Merthyr Tydfil – Countywide.
Merthyr Tydfil | Various Land and Buildings | 5.26 | 2019 | 2023 | £5.26m LA. | Location: Merthyr Tydfil – Countywide.
Monmouthshire | Monmouth Comprehensive – 21st Century Schools | 45.8 | 2015 | 2020 | Delivery ongoing. 2015-16 £3.99m, 2016-17 £5.89m, 2017-18 £22.88m, | Monmouth Comprehensive. Funded by Capital Receipts, Prudential Borrowing and Welsh Government (WG) 21st Century Schools Matched Funding.
Monmouthshire | Caldicot Comprehensive – 21st Century Schools | 38.1 | 2015 | 2019 | Delivery ongoing. 2015-16 £4.24m, 2016-17 £20.33m, 2017-18 £11.38m, | Caldicot Comprehensive school. Funded by Capital Receipts, Prudential Borrowing and WG 21st Century Schools Matched Funding.
Monmouthshire | Property Maintenance | 7.72 | 2018 | 2022 | £1.93m pa. Combination of Local Authority (LA) funding and General Capital Grant. | Maintenance and improvement of the existing Property asset base. Location: Countywide.
Monmouthshire | Infrastructure Maintenance | 8.96 | 2018 | 2022 | £2.24m pa. LA and WG funding. Works will be procured mainly through the South East Wales Framework contract. | Maintenance and improvement of the existing Property asset base. Location: Countywide.
Neath Port Talbot | Cefn Saeson Comprehensive | 29 | 2019 | 2021 | Local Authority (LA) and Welsh Government (WG). (21st Century Schools). | A new build English-medium school for 900 pupils aged 11-16 years to replace an existing secondary school assessed as building condition category D. The new build school will continue to serve the existing catchment as well as deliver specialist provision, admitting pupils from across the County Borough.
Neath Port Talbot | Abbey Primary | 9.2 | 2019 | 2021 | LA and WG. (21st Century Schools). | A new build English-medium school for 450 pupils (incl. Nursery) on a single site to replace the existing buildings located over three sites. It hosts a specialist assessment centre for Early Years pupils from across the County Borough. The new build school would include this specialist provision. The school will continue to serve its current catchment area.
Neath Port Talbot | Harbourside Strategic Employment Site | 5 | 2019 | 2020 | Funded by European Convergence Grant and LA funding. | The development will include the construction of a road transport network and establish new employment sites to act as a catalyst for economic and physical regeneration in the former industrial area.
Neath Port Talbot | Neath Town Centre Regeneration – Phase 2 | 12.5 | 2018 | 2021 | LA funding. | This project is the second phase in the development of Neath Town Centre and will include space for retail units and a leisure centre. Preparation work started.
Neath Port Talbot | Flood/Coastal Project Aberavon | 5.3 | 2018 | 2022 | Local Authority funding and Coastal Erosion Welsh Government Grant. | A coastal risk management scheme to reduce the risk from coastal erosion to properties, including a care home. It will also safeguard and enhance the promenade and access to Aberavon Beach. Design work underway.
Neath Port Talbot | Former Plaza Cinema | 6.5 | 2019 | 2021 | Local Authority funding and Building for the Future (BFF) Welsh Government Grant. | Re-development of the derelict Plaza Cinema site located in Port Talbot town centre – to build a facility that will create jobs and growth and contribute to the tackling poverty agenda. It will provide flexible business facilities (office/meeting/training rooms etc) as well as a multi purpose area for the community, and a cafe/training kitchen facility. Design work underway.
Neath Port Talbot | Former Crown Building, Neath | 6.2 | 2019 | 2020 | Local Authority funding, Targeted Regeneration Investment Programme (TRI) Welsh Government Grant and WG Loan. | Acquisition and redevelopment of the former Crown Foods site in Neath. This proposal will deliver significant investment and job creation within the County Borough. This project is being developed as a Strategic Hub for the Valleys. Site purchased March 2019, development works started immediately after purchase.
Newport | 21st CenturySchools – Band A | 11 | 2014 | 2019 | LA £5.5m, WG £5.5m funding – Delivery ongoing. Some contractors appointed, other schemes in design phase. | Nursery Provision complete; Primary Provision complete; Autism Spectrum Disorder (ASD). Provision almost complete, Demountables and Reorganisation ongoing. £4m diverted to Welsh Medium Secondary project. Location: Newport various.
Newport | 21st CenturySchools – Band B | 70 | 2018 | 2025 | LA £24.5m and WG £45.5m grant funding. | Approval for grant funding of the overall grant funding given 2018.
Newport | Welsh Medium Primary School | 5.8 | 2019 | 2024 | WG grant funding. | To provide further provision of Welsh medium primary education in Newport.
Newport | Renovation Grants (Disabled facilities) | 1.3 |  | Ongoing | LA – Tendered as individual contracts, as specific schemes are identified. Approx. £1.3m p.a. adjusted for slippage when necessary. | Authority operates option of agency scheme for householders. Location: Newport various.
Newport | Asset Management Programme | 1.5 |  | Ongoing | LA – Tendered as individual contracts, as specific schemes are identified. | Capitalised maintenance of all LA buildings. Location: Newport various.
Newport | Newport Station Footbridge | 3 | 2018 | 2022 | WG grant funding (indicative). | To build an unsegregated, shared use Active Travel Bridge over the main railway line. Location: Newport – Devon Place to Queensway.
Newport | Street lighting LED | 3.2 | 2018 | 2019 | LA funding. | To replace all streetlighting in Newport to LEDs. Location: Newport, various.
Pembrokeshire | 21st Century Schools Includes Band A | 121.59 | 2012 | 2021 | Band A Welsh Government (WG) 50%. Local Authority (LA) 50%. Combination of in-house and external professional services. Combination of traditional procurement and design and build. Delivery ongoing. | Location: Countywide.
Pembrokeshire | 21st Century Schools Band B | 106.4 | 2018 | 2025 | Band B 65%/75% (WG, LA) 35%/25%. Combination of in-house and external professional services. Combination of traditional procurement and design and build. Awaiting approval for Band B. | Location: Countywide.
Pembrokeshire | PFI – Voluntary Buy Out | 6.34 | 2019 | 2021 | LA £6.34m. | Voluntary termination in order to generate savings. Location: Pembroke Dock.
Pembrokeshire | Haverfordwest Highway, Traffic and Car Park improvements | 1.99 | 2012 | 2020 | Section 106 £0.03m, LA £1.7m. External design. Traditional procurement. Delivery of phase 1 complete. Phase 2 underway. | Road layout, car park improvements. Location: Haverfordwest.
Pembrokeshire | Fishguard Highways Improvement | 3.98 | 2016 | 2020 | WG £2.53m, LA £1.45m. | Provision of new link road in town centre which will enable redevelopment of land. Location: Fishguard.
Pembrokeshire | Transport Highways Maintenance Grant | 2.12 | 2018 | 2020 | WG funded. | Programme of works identified from SLA backlog to be completed in house in 2019-20.
Pembrokeshire | Local Transport Fund, Road Safety, Safe Routes in Communities | 2.75 | 2019 | 2020 | WG £2.52m, Pembrokeshire County Council £0.23m. | Various projects to create specific areas/routes currently deemed as high risk.
Pembrokeshire | Withybush Food Park | 2.03 | 2018 | 2020 | ERDF £1m. LA £1.03m. Design and build contract. | The creation of small scale food business units and incubator units for micro businesses in the food sector. Location: Haverfordwest.
Pembrokeshire | Waste Service Review – Vehicles | 5.66 | 2018 | 2020 | Welsh Government (WG)/Waste and Resources Action Programme WRAP £2.63m, LA £3.03m. | Scheme for the delivery of waste and recycling services to residents and businesses in the authority area. Location: Countywide.
Pembrokeshire | Waste Service Review – Equipment | 3.34 | 2018 | 2020 | WRAP £0.01m, LA £3.24m. | Scheme for the delivery of waste and recycling services to residents and businesses in the authority area. Location: Countywide.
Pembrokeshire | Workforce Transformation | 6.4 | 2019 | 2020 | LA £2.5m. | Transformational restructure of the Authorities staffing structure that have resulted in redundancy costs which will be funded from Capital Receipts.
Pembrokeshire | IT Development | 2.6 | 2019 | 2022 | LA £2.6m. | Improving and maintaining IT provision within corporate IT strategy.
Pembrokeshire | Replacement of Vehicle and Plant | 5.07 | 2019 | 2022 | LA £5.07m. | Rolling programme of vehicle replacement. Traditional procurement. Location: Countywide.
Pembrokeshire | Housing Revenue Account | 59.26 | 2018 | 2022 | WG Major Repairs Allowance £12m, LA £47.26m. | Improvements to Council housing stock. Five new build developments. Location: Countywide.
Powys | 21st Century Schools – Band A | 67.57 | 2013 | 2019 | Local Authorities (LAs) and Welsh Government (WG) funding. Contractor appointed on New Welsh Medium School. Other projects at Outline Business Case stage. | Scheme – New Welsh Medium School Location: Newtown Scheme – Gwernyfed Primary Schools. Location: Hay on Wye, Clyro and Talgarth Llyswen and Llangors. Scheme – Brecon High School. Location: Brecon. Scheme – Glantwymyn Refurbishment. Location: Glantwymyn. Scheme – Welshpool Review. Location: Welshpool Scheme Machynlleth School.
Powys | 21st Century Schools – Band B | 113 | 2019 | 2025 | LA and WG funding to be confirmed. | Locations to be confirmed.
Powys | Major School Improvements | 7.54 | 2013 | Ongoing | LA funding. | Location: Countywide.
Powys | Highway Improvements | 15.8 | 2017 | 2020 | LA funding. | Location: Countywide.
Powys | Structural Maintenance (Roads) | 7.3 | 2014 | 2019 | LA funding. | Scheme to ensure the roads are maintained to an agreed standard. Location: Countywide.
Powys | Housing Energy Efficiency Measures | 2.63 | 2017 | 2020 | Housing Revenue Account funding. | Location: Countywide.
Powys | Recycling Centre | 4.05 | 2017 | 2019 | LA £0.28m Supported Borrowing, £2.99m Prudential Borrowing and £0.05m Capital Receipts, WG Grant £0.74m. | Location: Abermule.
Powys | Disabled Facility Grants | 7.4 | Ongoing | Ongoing | LA Supported Borrowing. Delivery Grant Applicant Tender. | Location: Countywide.
Powys | Replacement of Vehicle and Plant | 16.79 | 2013 | Ongoing | LA funding. | Location: Countywide.
Powys | Welsh Housing Quality Standard | 42.92 | 2013 | 2021 | LA £20.42m Prudential Borrowing, Reserves £11.4m WG £11.1m. Delivery: Existing Frameworks. | Scheme Programme to upgrade Council dwellings under existing framework contracts Location: Countywide.
Powys | Housing Improvements | 3.5 | 2015 | 2020 | Housing Revenue Account funding. | Scheme to improve Older Persons Council dwellings. Location: Countywide.
Powys | Housing Repurchase and New Build | 12.13 | 2015 | 2025 | Housing Revenue Account funding. | Scheme to increase the number of Council dwellings by 250. Location: Countywide.
Powys | Housing Communal Works | 3.16 | 2018 | 2020 | Housing Revenue Account funding. | Location: Countywide.
Powys | Fleet Depot | 3.94 | 2016 | 2020 | LA Prudential Borrowing. | Location: Llandrindod Wells
Powys | ICT Strategy | 4.05 | Ongoing | Ongoing | LA funding. | Various LA related projects such as the new finance system at county hall in Llandrindod Wells and the IT infrastructure system which is at all County Offices. Location: Countywide.
Powys | Leisure Centres | 2 | 2019 | 2023 | LA funding. | Refurbish Leisure Centres.
Powys | Regeneration Fund | 2.07 | 2016 | Ongoing | LA funding. | Various projects throughout the LA. Location: Countywide.
Rhondda Cynon Taf | 21st Century Schools | 173 | 2013 | 2020 | Funding Sources: Prudential Code £86.5m, Welsh Government (WG) Grant £86.5m. Delivery Status: Ongoing delivery. | 11 schemes: Aberdare School and Sports Centre, Y Pant Comprehensive, Treorchy Primary, Cwmaman and The Rhondda review which includes Tonyrefail, Tonypandy, Treorchy Secondary, Porth County, Cymmer Primary, Llwyncelyn and YGG Tonyrefail. Location: Aberdare, Pontyclun, Treorchy, Porth, Tonyrefail and Tonypandy.
Rhondda Cynon Taf | Roof Renewal | 2.1 | 2019 | 2022 | Funding Source: Local Authority (LA) £2.1m. Delivery Status: Ongoing delivery via tendered contractors. | Eight roof schemes in schools allocated for 2019-20.Cwmclydach Primary School, Park Lane Special School, Caegarw Primary School, Darrenlas Primary School, Bryncelynnog Comprehensive, Penywaun Primary School, Aberdare Park Primary School, Cwmdare Primary School. Location: Countywide.
Rhondda Cynon Taf | Highways Improvements | 19.57 | 2019 | 2022 | Funding Sources: LA £17.07m, WG Grant £2.5m. Delivery Status: Combination of in-house provision and LA framework contractors. | Planned programme of highway improvement works. Location: Countywide.
Rhondda Cynon Taf | Transportation Infrastructure | 11.91 | 2019 | 2022 | Funding Source: LA £11.91m. | Major schemes inc: Porth Park and Ride, A4119 Coedely Dualling, Mountain Ash Cross Valley Link, Llanharan Bypass and Making Better Use works. Location: Countywide.
Rhondda Cynon Taf | Structures | 6.49 | 2019 | 2022 | Funding Sources: LA £6.49m. Delivery Status: Schemes are at various stages of design, tender, delivery. | Schemes: Aberaman, Tyntyla footbridge, Brook St. Bridge, St.Albans Bridge and advance preparation over various areas within the county. Location: Countywide.
Rhondda Cynon Taf | Taff Vale Development | 50.87 | 2017 | 2021 | Funding Sources: WG/Welsh European Fund Office (WEFO) Grant £12.27m, LA £38.60m. Delivery Status: Ongoing delivery by contractor. | Redevelopment of Taff Vale site. Location: Pontypridd.
Rhondda Cynon Taf | Disabled Facilities Grants/Adaptations | 12 | 2019 | 2022 | Funding Source: LA £12m. Delivery Status: Ongoing delivery via LA framework contractors. | Works of adaptation for disabled residents living in their own home. Location: Countywide.
Rhondda Cynon Taf | Empty Property Grant Scheme | 2.2 | 2019 | 2022 | Funding Source: LA £2.2m. Delivery Status: Ongoing delivery via LA framework contractors. | Returning empty properties into use has a significant positive impact for the community by providing valuable accommodation but also improving the street scene and enhancing the neighbourhood’s environmental and social conditions.
Rhondda Cynon Taf | Modernisation Programme (Adults) | 6.59 | 2019 | 2022 | Funding Source: LA £6.59m. Delivery Status: Ongoing delivery via LA framework contractors. | Investment in Adult Care Programme including Extra Care Facility and Supported Living.
Rhondda Cynon Taf | Vehicles | 9.14 | 2019 | 2022 | Funding Source: LA £9.14m. Delivery Status: Ongoing. | Ongoing replacement programme of fleet vehicles via LA framework of suppliers. Location: Countywide.
Rhondda Cynon Taf | Waste Strategy | 5.87 | 2019 | 2021 | Funding Source: LA £3.65m. Other contribution £2.22m. Delivery Status: Ongoing. | Investment in Materials Recovery Facility.
Rhondda Cynon Taf | Welsh Medium Capital Grant | 3.57 | 2019 | 2020 | Funding Source: WG £3.57m. Delivery Status: Ongoing. | Increasing Welsh Medium Provision 11 schemes: YGG Aberdar, Ysgol Llamhari, YGG Evan James, YGG Abercynon, YGGG Llantrisant, YGG Ynyswen. Location: Aberdare, Pontyclun, Pontypridd, Mountain Ash and Treorchy.
Rhondda Cynon Taf | Robertstown Development | 4.96 | 2019 | 2020 | Funding Source: LA £2.69m, WEFO/WG £2.27m. | Developing modern business accommodation at Robertstown, Aberdare.
Rhondda Cynon Taf | Coed Ely Development | 3.53 | 2019 | 2020 | Funding Source: LA £1.21m, WEFO/WG £2.32m. | Developing modern business accommodation at Coed Ely, Tonyrefail.
Swansea | 21st Century Schools (Band A) | 51.46 | 2014 | 2020 | Local Authority (LA) and Welsh Government (WG) funding – Final scheme has commenced delivery, following contractor issues. Mainly external contractors with some in-house projects. | Location: Countywide.
Swansea | 21st Century Schools (Band B) | 149.95 | 2018 | 2025 | Initial Band B schemes are being developed, with some schemes commencing in 2019-20. | Location: Countywide.
Swansea | Highways Capital Maintenance | 17.7 | 2019 | 2023 | LA funding utilising external and in-house contractors. | Location: Countywide.
Swansea | Pipehouse wharf depot replacement | 2.43 | 2016 | TBC | LA funded £2.43m. | Progressing site options.
Swansea | Tir John refuse tip closure and remedial works | 7.25 | 2014 | 2027 | LA £7.25m – capping elements ongoing. | Location: St Thomas, Swansea, SA1 8NS.
Swansea | Buildings Capital Maintenance | 19 | 2019 | 2023 | LA funded utilising external and in-house contractors. | Location: Countywide.
Swansea | Swansea City Centre Redevelopment (City Deal schemes – Phase 1) | 24.2 | 2016 | 2021 | Arena preliminary works on-site commenced with contractor and awaiting cost certainty. Funded by City and County of Swansea (CCS) and City Deal. | Location: Swansea SA1.
Swansea | Swansea City Centre Redevelopment (City Deal schemes – Phase 2) | 3.2 | 2018 | TBC | Development phase funded by CCS. | Location: Countywide.
Swansea | Kingsway Infrastructure development | 12.2 | 2017 | 2021 | Scheme being delivered. Funded by CCS and Welsh European Funding Office (WEFO). | Location: Swansea
Swansea | Hafod-Morfa Copperworks Powerhouse | 5 | 2018 | 2023 | LA match and National Lottery Heritage Fund funding secured. | Location: Swansea, Hafod-Morfa Copperworks site.
Swansea | Disabled Facilities Grants and Other Improvement grants/loans | 20.8 | 2019 | 2023 | LA funding – various contractors. | Minor works to third party properties and property loan schemes.
Swansea | Agile and Mobile digital transformation programme | 10 | 2017 | 2022 | LA funding. | Location: Swansea.
Swansea | Leisure Centre improvements (Freedom Leisure contract) | 4 | 2018 | 2020 | LA funding. | Location: Countywide.
Swansea | Housing Revenue Account schemes | 225.75 | 2019 | 2023 | LA and WG funding – various external and internal contractors. | Improvements to council dwellings and external facilities to achieve WHQS and More Homes programme. Location: Countywide.
Torfaen | 21st Century Schools | 86.08 | 2013 | 2020 | Local Authority (LA) and Welsh Government (WG) funding – Delivery ongoing. Contractor appointed for phase 1b – construction of three new primary schools which have been completed, the redevelopment of two primary schools - completed. Building a new secondary school and post 16 centre - underway. | Location: Countywide.
Torfaen | Welsh Medium Primary School | 6 | 2019 | 2021 | Building of a new Welsh medium primary school funded by Welsh Government.
Torfaen | Adventure Triangle Scheme | 2.5 | 2019 | 2021 | Funded by European Regional Development Fund (ERDF) and TMF. | Collaborative scheme with Caerphilly CBC to regenerate the Mon and Brecon Canal.
Torfaen | Highways Infrastructure | 3 | 2019 | 2019 | A mixture of core funding, additional highways grant from WG and specific transport grant schemes. | Highways maintenance across the borough and specific schemes such as Safe Routes in Communities Initiative (SRIC).
Torfaen | The British Redevelopment | 3.7 | 2017 | 2021 | WG, Vibrant and Viable Places (VVP) funding and Torfaen core funding. | Redevelopment of an old coalfield site.
Vale of Glamorgan | Victorian Schools | 2.17 | 2014 | 2019 | Local Authority (LA) Funding £2.17m – Delivery Ongoing. | Location: Victorian schools across the Vale of Glamorgan.
Vale of Glamorgan | 21st Century Schools Band B | 134.94 | 2018 | 2024 | LA, Welsh Government (WG) and Section106 funding – Contractor to be agreed. | Location: Various locations across the Vale of Glamorgan.
Vale of Glamorgan | Schools asset renewal | 5.24 | 2019 | 2024 | LA and Section106 funding. | Location: Various locations across the Vale of Glamorgan.
Vale of Glamorgan | Five Mile Lane | 25.8 | Ongoing | Ongoing | WG and LA funded scheme. | Location: Five Mile Lane.
Vale of Glamorgan | Visible Services Asset Renewal | 6.24 | 2019 | 2024 | LA £5.79m – Contractor to be agreed. Includes Additional Highways Refurbishment Grant LA £758k and £749k. | Location: Various locations across the Vale of Glamorgan. Includes Highways Improvements, and annual Coast and Flood Protection.
Vale of Glamorgan | Disabled Facility Grants | 5.95 | 2019 | 2024 | LA £5.95m – Multiple Contractors. | Location: Various locations across the Vale of Glamorgan.
Wrexham | 21st Century Schools Programme – Gwersyllt Primary School | 3.2 | 2018 | 2020 | Local Authority (LA) £1.6m and Welsh Government (WG) £1.6m funding. | Extension to school to merge Infants and Juniors in one building. Location: Wrexham.
Wrexham | 21st Century Schools Programme – Band B | 36.66 | 2019 | 2026 | LA £10.25m, Diocese £2.42m, WG £23.99m. | New Schools, Extension and Refurbishments across Faith, Welsh and English medium schools at a variety of locations across the County. SOP approved July 2018.
Wrexham | Housing Revenue Account Council dwellings upgrade | 160.7 | Ongoing | 2023 | WG £30.3m, £107.3m prudential borrowing LA £23.1m – Delivery ongoing – multiple contractors. | Upgrades to Council dwellings include central heating, re-roofing, electrical work, kitchens, bathrooms and other major repairs. Location: Countywide.
Wrexham | Disabled Facilities Grants | 4.7 | Ongoing | 2023 | LA supported borrowing – Delivery ongoing – multiple contractors. | Statutory requirement – property adaptations to allow individuals to remain in their own homes e.g. showers, stairlifts, internal modifications. Location: Countywide.
Wrexham | Highways Structural Maintenance | 5 | Ongoing | 2023 | LA £4.3m and WG £0.7m – Delivery ongoing – multiple contractors. | Location: Countywide.
Wrexham | Property Asset Improvements | 3 | 2019 | 2020 | LA supported borrowing – Delivery ongoing – multiple contractors. | To address the major issues identified as requiring capital investment to maintain property assets to a satisfactory standard.
Wrexham | Childcare Offer Schemes | 4.6 | 2019 | 2021 | WG £4.6m Childcare Offer grant – delivery ongoing. | To support the authority to provide sufficient childcare places to meet demand. Location: Countywide.

## Annex 3 Private Sector
Annex 3 – Private Sector Project Pipeline
As part of our work to develop a complete picture of strategic infrastructure investment across Wales, the following section contains a collation of private sector investment from the Energy, Water and Rail sectors. Whilst the schemes presented here are priority investments and have a high probability of being delivered, they do not represent any formal commitment from the companies or their partners included below.
Water
Sector | Project/Programme | Total scheme value (est.£m) | Welsh Government support (est.£m) | Start Date | End Date | Finance and delivery | Additional information
Water - DVW | Integrated network investments to improve water quality and resilience across DVW’s supply area | 17 | Private sector investment, no Welsh Government (WG) funding expected. | Ongoing | Ongoing | Private sector led investment. | Decommissioning legacy treatment works and replacing it with new mains and pumping stations.
Water - DVW | Service reservoirs | 9 | Private sector investment, no WG funding expected. | Ongoing | Ongoing | Private sector led investment. | Replacement of three service reservoirs in Wrexham (1 No.) and Llangollen (2 No.) and refurbishment of other reservoirs.
Water - DVW | Pipe replacement | 4 | Private sector investment, no WG funding expected. | Ongoing | Ongoing | Private sector led investment. | Replacing 7.5 miles/year of pipes to reduce the number of bursts and provide a resilient supply for customers.
Water - DVW | Oerog Springs – refurbishment | 1 | Private sector investment, no WG funding expected. | Ongoing | Ongoing | Private sector led investment. | Upgrading treatment works to enhance the quality of water to customers in Llangollen.
Water - DVW | Wrexham pumping station upgrade | 1 | Private sector investment, no WG funding expected. | Ongoing | Ongoing | Private sector led investment. | Refurbishment of Wrexham pumping station to maintain a resilient supply of water to 45,000 customers in Wrexham.
Water - DVW | Ongoing maintenance of other operational assets | 1 | Private sector investment, no WG funding expected. | Ongoing | Ongoing | Private sector led investment. | General maintenance to ensure the assets continue to perform their duty.
Water - DVW | Treatment works upgrades | 0.5 | Private sector investment, no WG funding expected. | Ongoing | Ongoing | Private sector led investment. | Improvements in treatment processes.
Water - Severn Trent | Severn Trent Investment Schemes (Powys) | 85 | N/A | 2015 | 2020 | Water and Sewerage Company Combined Investment Scheme. | Combined investment programme for the Severn Trent area in Powys. Includes three schemes relating to the Elan Valley Aqueduct.
Water - Dŵr Cymru Welsh Water | Collecting, Storing and Transferring Raw Water | 65.9 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | The purpose of this investment is to improve raw water storage, quality and security of supply and to comply with legislative obligations including: the National Environment Programme, the Eels Regulations, Water Framework Directive and duties contained within the Water Industry Act 1991.
Water - Dŵr Cymru Welsh Water | Treating Water for Public Health | 85.1 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | The purpose of this investment is to ensure compliance with drinking water standards and safeguard public health by undertaking work at various treatment works to improve the process, leading to improved drinking water quality and to provide a stable service. The investment will also help meet statutory obligations under Drinking Water Regulations.
Water - Dŵr Cymru Welsh Water | Delivering a Reliable Supply of Safe Drinking Water | 239.5 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | Investment in the infrastructure in Welsh Water’s distribution area are required to meet the needs of the growing population and safeguard levels of existing service. Works will include improving the condition of trunk and distribution mains to reduce burst pipes and discolouration and will improve reliability and serviceability. Installation and replacement of water meters, bulk meters and data loggers are designed to improve the accuracy and visibility of the network flow data.
Water - Dŵr Cymru Welsh Water | Collecting Wastewater to Protect Health | 54.1 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | Investment is designed to enhance waste water assets in order to cope with the capacity required by a growing population. It will also ensure that first time sewerage applications are assessed and delivered where appropriate.
Water - Dŵr Cymru Welsh Water | Transferring and Treating Wastewater to protect the Environment | 235.4 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | This investment is designed to deliver improvements to assets to meet Water Framework Directive and conservation drivers (as determined in the National Environment programme). Work planned at water treatment works will reduce the impact of our activities on the environment. Improvements to assets will help meet Bathing Water and Shellfish Water directive water quality requirements, by reducing spills and overflows from the sewerage network and will help ensure that the company is able to maintain compliance with regulatory permits. Installation of monitors and impact investigation programmes will ensure that future investment is based on sound evidence and sustainable technologies. Sewer maintenance and rehabilitation will reduce the number of properties experiencing flooding from the sewer network and will minimise the environmental impact of discharges from the network.
Water - Dŵr Cymru Welsh Water | Treating Used Water to Protect the Environment | 93 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | Investment in wastewater treatment works is required to protect public health and ensure compliance with regulatory permits, addressing operational, pollution and health and safety risks and also increase capacity to accommodate growth, as indicated by Local Planning Authorities. Investment in Outfall rehabilitation schemes will contribute to ensuring that discharges have no adverse impact on the environment and that the company complies with permits.
Water - Dŵr Cymru Welsh Water | Managing environmental impacts in the Loughor Estuary and Burry Port area | 77 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | This is a programme to control the frequency and duration of spills from the sewer network to mitigate the environmental impact on coastal waters in the Loughor Estuary and Burry Port area, including designated shellfish waters and conservation areas and to meet objectives set out in the National Environment Programme.
Water - Dŵr Cymru Welsh Water | Safely Disposing of Sewage Sludge and Generating Renewable Energy | 143.2 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | Investment is needed to ensure the sustainable management of sewage sludge, to reduce operational costs and, comply with regulatory requirements. Investment in energy efficiency schemes to increase renewable energy generation, improve energy efficiency, reduce operational carbon and provide operational cost savings.
Water - Dŵr Cymru Welsh Water | Safeguarding Resilience | 16.6 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | Investment in emergency planning and risk management programmes to ensure compliance with the Security (Emergency Measures) Direction, to support resilience of essential water and environmental services, reduce the risk of serviceability failure at sites which are at risk of flooding and coastal erosion and minimise response times in the event of a major incident occurring.
Water - Dŵr Cymru Welsh Water | Strategic Planning, Research and Cross- company Activities | 109.6 | N/A | 2017 | 2020 | Financed through Welsh Water by customers, capital markets and bank finance. Delivery through the company’s in-house and supply chain resources. | Investment in enabling infrastructure such as transportation, IT systems, laboratories and facilities in order to maintain asset serviceability, asset value and compliance with regulatory requirements. This also includes additional investment to safeguard health and safety for our employees, fulfil obligations to the community through education, conservation and access and deliver research, development and innovation projects.
Energy | Small Modular Reactors/ Advanced Modular Reactors | 1500 | N/A | 2013 | 2033 | Initial pump priming will likely be required by WG with increasing private sector involvement and ownership once successful technology vendor(s) is chosen. | Potential for the delivery of first-of-a-kind new nuclear facilities at Trawsfynydd under consideration.
Energy | Onshore Wind | 100 | N/A | 2019 | 2025 | Onshore still excluded from Contract for Difference (CfD) mechanism. Some consented projects now built but others remain stranded following exclusion from revenue support mechanisms (CfD/ROC). Some signs that onshore may be re-admitted to future auctions (2019+) but not guaranteed. May be structured as “non-CfD” subsidy or some form of Power Purchase funding route. Developers becoming more positive recently evidence on increasing “shared ownership” projects (Jan-Mar 18) to increase Welsh benefit. | All projects will be under WG consenting powers (currently grid connections remain with UK). Over 2GW of commercial scale wind projects previously identified as achievable in Wales. Regeneris estimated around £1.1m per MW spend in development/construction phase of which 35% of this spend will be retained locally. Dialogue continues with developers and stakeholders.
Energy | Solar | 35 | N/A | 2018 | Ongoing | Private sector led. Large scale solar project (70MW) approved in Anglesey (Nov 17). Driven by PPAs rather than subsidy schemes. | Previous shift to small scale projects now seems to be moving back towards very large scale ground mounted projects to give lowest cost per MW benefits of scale £4.5m investment in Monmouthshire solar farm and £3m Flintshire LED.
Energy | Energy from Waste – Parc Adfer | 180 |  | 2017 | 2020 | Ten procurement projects, incorporating residual waste and anaerobic digestion for food waste, providing over 75MW are proposed, consented or under construction. Private sector investment with 23 year loan from Green Investment Bank/Siemens. WG Funding £5.56m revenue pa (25 years). The Parc Adfer funding is funding to support the five North Wales Local Authority’s and covers the 25 year life of the project. | The construction phase for the new £180m energy- from-waste facility for North Wales (Parc Adfer) started at the beginning of 2017 and will take an estimated three years to complete. Once operations commence in 2019, post-recycled residential and business waste from five North Wales partnership authorities will be diverted from landfill to generate clean and sustainable energy for local homes nd businesses. Parc Adfer will also be capable of providing heat and steam to local industry and nearby homes, an opportunity Wheelabrator Technologies is actively pursuing with local authorities and the Welsh Government. The facility aims to use local suppliers wherever possible through the construction and operational phases.
Energy | Hydro Pumped Storage | 250 | N/A | 2014 | 2019+ | Private sector led. Glyn Rhonwy project has received development consent. Financing now a challenge after changes to embedded generation compensation payments, project currently paused. Based on outline figures, the project is expected to cost approximately £200m. Dinorwig have announced £50m upgrade to two of the existing four turbines which will further extend the life of the installation. | Single proposal in North Wales for a pumped Single proposal in North Wales for a pumped it is understood further sites have been identified for schemes of similar scale. Storage clearly critical to grid balancing with more intermittent renewables but battery projects seem favoured.
Energy | Marine Energy – Wave and Tidal Stream | 200 | European Structural Fund Programmes 2014-2020 | 2014 | 2020 | Private sector led projects part funded by the 2014-2020 European Structural Fund Programme. €100m to increase the number of wave and tidal energy devices being tested in Welsh waters and off the Welsh coast, including multi-device array deployments, thereby establishing Wales as a centre for marine energy production. Morlais progressing consenting of zone. Grid infrastructure will only follow in 2019 if device developers have a CfD or an Innovation Power Purchase Agreement or some other route to market for their projects. The Marine Energy Council is currently in discussion with BEIS and Treasury to find a way forward for this technology. | Tidal Energy Ltd went into administration on 17 October 2016. DeltaStream technology development project did achieve its primary objective and has provided a significant amount of learning to the sector and the local supply chain. Marine energy projects are being delivered by Minesto, Marine Power Systems and Wave-tricity supported by EU funding. Morlais (West Anglesey) tidal demonstration zone has attracted ten tidal stream developers and has been awarded £4.5m of EU and £200k Welsh government funds. The Menter Môn Morlais scheme has been set up to help accelerate the development and commercialisation of multiple tidal stream technologies in the Crown Estate awarded Morlais Demonstration Zone. Wave Hub are undertaking a technical and commercial feasibility study of the south Pembrokeshire wave demonstration zone and have been successful in gaining consent for its phase 1 demonstration zones which are for testing small devices and apparatus for six months, they are now working on phase 2 which are for larger devices.
Energy | Western Power Distribution (WPD) | 90 | N/A | 2015 | 2023 | Private sector led investment. | RIIO Business Plan approved by OFGEM. Covers WPD’s South Wales region.
Energy | Scottish Power Electricity Networks | 855.8 | N/A | 2015 | 2023 | Private sector led investment. | Investment covers SP Manweb region.
Energy | Swansea Bay City Deal | TBC | WG/WEFO funding expected | 2018 | 2023 | A mixture of private and public sector funding. | There are a number of strands within the City Deal that have an energy component, including Pembroke Marine and Homes as Power Stations.
Energy | Cardiff Capital Region | TBC | WG/WEFO funding expected | 2018 | 2023 | A mixture of private and public sector funding. | There are a number of strands within the City Deal that have an energy component, including the Innovation and Housing themes.
Energy | Smart Living | 10 | Small levels of pump priming development with some projects to initialize smart innovative solutions. Smart Living Project Board. | 2015 | Ongoing | Working at regional and LA level to develop Wales-wide proposals for Smart Living drawing on a range of funding sources needed. Creating an innovative learning platform to inform future policy and attract smart innovative solutions to Wales. Smart Living Technical Group established bringing expertise and horizon scanning for innovative solutions to inform Wales. Supplemented by initiation of the Hydrogen and Associated Green Gases Reference Group. To-date demonstrators have attracted £15m investment and supplementary support of £30m from UK and private innovation sources. | Within an approved Smart Living Framework a first wave of seven demonstrator projects have been initiated covering different learning opportunities. Demonstrators include: • the Medium Voltage Direct Current (Angle DC) pilot in Anglesey being taken forward by Scottish Power Energy Networks to improve management and control of capacity of the local networks • Bridgend County Borough Council working with the Energy Technologies Institute and now the Energy Systems Catapult piloting and demonstrating Smart Systems and Heat using new technologies, systems and processes applied to heat.
Energy | Local Energy | TBC | TBC | 2010 | Ongoing | WG Local Energy Service provides advice, support and enabling funding to encourage the development of small scale and distributed generation of energy (electricity and heat). It is supporting the projects in development for the ERDF funded programme. 16 community scale projects have now been constructed and are operational in Wales, with WG support, providing an estimated lifetime return of £18m. However reduction in Feed in Tariffs mean developments without pre-accreditation are much less likely to go ahead. Work is under way to develop business models that work in a subsidy free environment. Likely to need a patient capital approach as projects are viable over longer term. WG Local Energy Fund provides access to approx £5m recycling capital. WG has published targets for 1GW of locally owned electricity generation by 2030. Currently 397MW of electricity and 177MW of heat capacity is locally owned.
Energy | Local Energy – Small Scale Renewables | 25 | Up to 15 ERDF. | 2018 | Ongoing | Private sector, third sector and public sector led projects. | One operation has been approved, committing £6.5m ERDF. Earlier in 2017 a ‘Call’ for proposals in the ERDF Small Scale Renewables Specific Objective, was conducted with significant interest generated. Nine operations were invited into ‘business planning’ and are currently in development. These proposals will seek to deliver investment of up to £9m ERDF, delivering the relevant indicators and wider community benefits across a mix of technologies, including solar, PV, battery, hydro and geothermal.
Energy | Gas | 1500 | N/A | 2015 | Ongoing | Private sector led projects. | A number of nationally significant infrastructure projects are being considered by the Planning Inspectorate, totalling around 1.5GW. Should these schemes be granted development consent, they could cumulatively comprise investment of £1.5bn.
Network Rail | Great Western Main Line electrification to South Wales | 2800 |  | Ongoing | Ongoing |  | Completion of the electrification scheme to Cardiff.
Network Rail | Wales Route renewal plans for Control Period 6 (2019-24) | 1700 |  | Ongoing | Ongoing |  | Renewal of railway assets including signalling, track, structures and other assets, including the renewal or refurbishment of almost 250 miles of track and the renewal of a Grade II listed viaduct at Barmouth.
Network Rail | Access for All Funding for Wales | 35 |  | Ongoing | Ongoing |  | To provide improved accessibility at 11 stations across the route, with match funding from the Welsh Government.