## INTRODUCTION
Annex 10: Options appraisal template (worked example)
Background: This spreadsheet provides a worked example of the Options Appraisal template using a fictituous example of a capital project. Example Project: Within a specific area a Local Authority has responsibility for two schools; Schools A and B. Both schools are in need of repair and are nearing full capacity. Other schools in nearby adjacent areas are also nearing full capacity. A Strategic Outline Case (SOC) is drafted to facilitate a project that will address both the maintenance and provision issues at Schools A and B. A long list of options has been considered in collaboration with key stakeholders and narrowed down to the following shortlist of options.
Shortlisted Options
OPTION 1: Do Minimum – Basic Refurbishment with Minor Extension In this option, the Local Authority will repair (or partly refurbish) Schools A and B and provide minor extensions to School A to accommodate the anticipated growth in pupil numbers.
OPTION 2: Refurbish and extend School A and close School B In this option, School B will be closed and School A will be fully refurbished and extended to accommodate the predicted growth in pupil numbers.
OPTION 3: New-build on a single site In this option, both Schools A and B will be combined via a new build on a single site. A potential site has been identified and closure of Schools A and B has been deemed possible following discussions with key stakeholders.

## DCF SUMMARY SHEET
DISCOUNTED CASHFLOW (DCF) SUMMARY SHEET
Discounted Cashflow (DCF) Summary Sheet |  | Inc. Optimism Bias |  | Excl. Optimism Bias
Option No. | Option Name/Description | NPC (£m) | EAC (£m) | NPC (£m) | EAC (£m)
Option 1: | Do Minimum – Basic Refurbishment with Minor Extension | 52.7869 | 2.773 | 50.6163 | 2.659
Option 2: | Refurbish and extend School A and close School B | 57.5125 | 3.0213 | 53.8432 | 2.8285
Option 3: | New-build on a single site | 78.3387 | 2.9389 | 73.9522 | 2.7743
Option (...) | Add options as necessary … | … | … | … | …
DCF = Discounted Cashflow
NPC = Net Present Cost
EAC = Equivalent Annual Cost
Note on D11: In some instances a Do Nothing option may clearly be unacceptable. This situation is rare, but might occur, for example, if there is a statutory obligation to be met. If a Do Nothing option is clearly unacceptable, then a Do Minimum option must be considered.

## OPTION 1 - DO MINIMUM
OPTION 1: | Do Minimum – Basic Refurbishment with Minor Extension
In this option, the Local Authority will repair (or partly refurbish) Schools A and B and provide minor extensions to School A to accommodate the anticipated growth in pupil numbers.
Appraisal Period | 30 | Year '0' must be counted as a valid year (eg, 0-29 years = 30 years)
| Sum of | 1st year |  |  |  | 5th year |  |  |  |  | 10th year |  |  |  |  | 15th year |  |  |  |  | 20th year |  |  |  |  | 25th year |  |  |  |  | 30th year |  |  |  |  | 35th year |  |  |  |  | 40th year |  |  |  |  | 45th year |  |  |  |  | 50th year |  |  |  |  | 55th year |  |  |  |  | 60th year
| Cashflows | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
£m | bar: 1st year 2012 0 to 60th year 2071 59
ASSUMPTIONS
CASHFLOWS (Please read comments) | [61 empty] | The basic assumptions underlying each cost line in the economic appraisals should be recorded below
PROPERTY & OPPORTUNITY COST
Opening Value | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | e.g. based on recent property valuation and estimated value of surrounding land
Transactions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Residual Value | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL PROPERTY & OPP. COSTS | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
-
CAPITAL COST (examples provided - not exhaustive) | [61 empty] | -
Initial Capital Costs | 14 | 3.5 | 7 | 2.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Optimism bias | 2.2512 | 0.5628 | 1.1256 | 0.402 | 0.1608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Lifecycle Costs | 6.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Other Capital Costs | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL CAPITAL | 23.0512 | 4.3628 | 8.4256 | 3.202 | 1.4608 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
REVENUE COST (examples provided - not exhaustive)
Salaries | 34.3 | 1.1 | 1.1 | 1.1 | 1.1 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Building Running Costs | 10.55 | 0.3 | 0.3 | 0.5 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Other Revenue Costs | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL REVENUE | 45.25 | 1.5 | 1.5 | 1.7 | 1.55 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
-
TOTAL COST (Cap & Rev) | 70.3012 | 10.8628 | 9.9256 | 4.902 | 3.0108 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.9 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.9 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | 1.7 | -1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
-
Discounted Cashflow | 52.7869 | 10.8628 | 9.59 | 4.5761 | 2.7156 | 1.4815 | 1.4314 | 1.383 | 1.3362 | 1.291 | 1.3941 | 1.2052 | 1.1644 | 1.125 | 1.087 | 1.0502 | 1.0147 | 0.9804 | 0.94725 | 0.91521 | 0.9883 | 0.85436 | 0.82547 | 0.79756 | 0.77059 | 0.74453 | 0.71935 | 0.69502 | 0.67152 | 0.64881 | -0.47937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Net Present Cost (NPC) | 52.7869
Equivalent Annual Cost (EAC) | 2.773
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Disount Rate |  | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3%
Discount Factor |  | 1 | 0.96618 | 0.93351 | 0.90194 | 0.87144 | 0.84197 | 0.8135 | 0.78599 | 0.75941 | 0.73373 | 0.70892 | 0.68495 | 0.66178 | 0.6394 | 0.61778 | 0.59689 | 0.57671 | 0.5572 | 0.53836 | 0.52016 | 0.50257 | 0.48557 | 0.46915 | 0.45329 | 0.43796 | 0.42315 | 0.40884 | 0.39501 | 0.38165 | 0.36875 | 0.35628 | 0.3459 | 0.33583 | 0.32605 | 0.31655 | 0.30733 | 0.29838 | 0.28969 | 0.28125 | 0.27306 | 0.2651 | 0.25738 | 0.24989 | 0.24261 | 0.23554 | 0.22868 | 0.22202 | 0.21555 | 0.20928 | 0.20318 | 0.19726 | 0.19152 | 0.18594 | 0.18052 | 0.17527 | 0.17016 | 0.1652 | 0.16039 | 0.15572 | 0.15119
Annuity Factor |  | 1 | 1.9662 | 2.8997 | 3.8016 | 4.6731 | 5.5151 | 6.3286 | 7.1145 | 7.874 | 8.6077 | 9.3166 | 10.0016 | 10.6633 | 11.3027 | 11.9205 | 12.5174 | 13.0941 | 13.6513 | 14.1897 | 14.7098 | 15.2124 | 15.698 | 16.1671 | 16.6204 | 17.0584 | 17.4815 | 17.8904 | 18.2854 | 18.667 | 19.0358 | 19.392 | 19.7379 | 20.0738 | 20.3998 | 20.7164 | 21.0237 | 21.3221 | 21.6118 | 21.893 | 22.1661 | 22.4312 | 22.6886 | 22.9384 | 23.1811 | 23.4166 | 23.6453 | 23.8673 | 24.0828 | 24.2921 | 24.4953 | 24.6926 | 24.8841 | 25.07 | 25.2505 | 25.4258 | 25.596 | 25.7612 | 25.9216 | 26.0773 | 26.2285
Years | 30
EAC Calculation |  | 0: 1; 1: 0.96618; 2: 0.93351; 3: 0.90194; 4: 0.87144; 5: 0.84197; 6: 0.8135; 7: 0.78599; 8: 0.75941; 9: 0.73373; 10: 0.70892; 11: 0.68495; 12: 0.66178; 13: 0.6394; 14: 0.61778; 15: 0.59689; 16: 0.57671; 17: 0.5572; 18: 0.53836; 19: 0.52016; 20: 0.50257; 21: 0.48557; 22: 0.46915; 23: 0.45329; 24: 0.43796; 25: 0.42315; 26: 0.40884; 27: 0.39501; 28: 0.38165; 29: 0.36875
Sum of Discount Factors | 19.0358
NPC (excl. Optimism Bias) | 50.6163 | 10.3 | 8.5024 | 4.2008 | 2.5705 | 1.4815 | 1.4314 | 1.383 | 1.3362 | 1.291 | 1.3941 | 1.2052 | 1.1644 | 1.125 | 1.087 | 1.0502 | 1.0147 | 0.9804 | 0.94725 | 0.91521 | 0.9883 | 0.85436 | 0.82547 | 0.79756 | 0.77059 | 0.74453 | 0.71935 | 0.69502 | 0.67152 | 0.64881 | -0.47937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EAC (excl. Optimism Bias) | 2.659
Note on B7: Appraisal Period: The appraisal period should normally equate to the intended period of use of the asset(s). This is the period over which the asset can be used for the specific purpose that it has been provided for. An appraisal period of 29 years (i.e. 30 years when counting year zero) is commonplace for refurbishment options. An appraisal period of 59 years (i.e. 60 years when counting year zero) is commonplace for new build options. These values are not set in stone however, and therefore, can be adjusted to the specific characteristics of the project at hand.
Note on C7: This is a refurbishment option, and therefore the appraisal period is set at 30 years.
Note on B14: Scope of Cashflows: The appraisal should attempt to capture all direct and indirect implications of the investment/option. Total (as opposed to change in) property, capital and revenue costs should be presented. Price/cost Base: This should be common for all costs, which should be presented in real terms or current prices (i.e. at today's general price level). Where particular prices are expected to increase at significantly higher or lower rate than inflation, the relative price change should be calculated. Examples where relative prices changes may be material to an appraisal include, high technology products (where prices may be expected to fall in real terms); fuel prices (where the resource supply is scarce); and wages (where productivity growth is expected to lead to wage increase above general inflation). Sign Convention: Costs positive, benefits negative. Timing: As per timing of implementation and expenditure of cashflows. Exclude Transfer Payments: These should be excluded from the appraisal. A transfer payment is one for which no good or service is obtained in return. Transfer payments may change the distribution of income or wealth, but do not give rise to direct economic costs. Taxes, redundancy payments, and capital charges are all examples of transfer payments that should be exluded from an economic appraisal. Exclude Sunk Costs: These are the costs of goods and services that have already been incurred and are therefore irrevocable. They should be excluded from the appraisal. From an appraisal viewpoint, the costs that matter are those upon which decisions can stil be made. However, this includes the opportunity costs of continuing to tie up resources that have already been paid for - see the comments in this speardhseet covering 'Property and Oppurtunity Costs' for more information on this aspect of the appraisal.
Note on B16: Principle: The property (land, buildings and major equipment) implications of any option should be reflected in the Discounted Cashflow analysis in accordance with the opportunity costs of the property or properties - irrespective of whether property is bought, sold or transferred, rented or used by the public sector. The opportunity costs of any asset reflect the value of the asset when used in its best alternative activity and is reflected in current market prices. If within an option a property is rented by the public sector, the rental costs will be reflected in annual revenue costs (rather than reflected in capital costs). please note that where a property is rented to another public sector organisation, the income associated with the rental is excluded from revenue estimates as this represents a transfer payment between public sector organisations. Project appraisers need to ensure that all property and opportunity cost values are assessed appropriately. The “property and opportunity” lines in this spreadsheet distinguish between “opening” values, “transactions” within the appraisal period and “residual” values. Opening Value: In the "opening value" row, opening values are included in year zero - as positive numbers. Transactions: In this row, property purchases, receipts and other transactions are included in the anticipated year of purchase, sale or transfer - positive numbers for purchase and transfers into the scheme and negative numbers for sale and transfers out. All transactions, whether they are cash sales/purchases or transfers to other public sector organisations should be entered in the “transactions” category. Residual Value: Residual values are included in the last year of the discount period - as negative numbers.
Note on B17: Opening Value: This is included in order to represent the opportunity cost of continuing to use the asset(s) in the way proposed by the option. The opportunity cost of any asset is reflected in the value of the asset when put to its best alternative activity/use. This is usually reflected in current market prices. In this option Schools A and B are kept in use and therefore the opening values of the land/properties/equipment in use by both schools are included in year zero - as positive numbers. As an illustrative example, the land is valued at £3m and the properties/equipment involved valued at £2m (approx. £1m per school) - and therfore an opening value of £5m is recorded in the first year of the appraisal for this option. See also HMT Green Book, page 20, para 5.14: "Costs should be expressed in terms of relevant opportunity costs. It is important to explore what opportunities may exist. An example of an opportunity is to use land in a different, more valuable, way than in its current use." [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B18: Transactions: This line is inluded to record the value of any transactions, i.e. property that is bought and sold during the lifetime of the option. In this option Schools A and B remain in use and therefore no additional land (or property) transactions into the overall estate are anticipated, so this row is left blank.
Note on B19: Residual Value: In some appraisals of investment options, the period of the appraisall will be less than the economic life of the property involved. The economic life is the period up to the point when major refurbishment is required for the asset to continue in use. In these cases, the value of an asset which has a disposal value at the end of the appraisal period should be accounted for by subtracting its residual value from the cashflow in the final year of the appraisal. The residual value can be taken as the lower of net asset value after deducting accumulated depreciation or expected market value. In this option the land upon which the properties are situated is assumed to have a residual value that equals its initial valuation of £3m. The buildings/equipment are assumed to have a residual value of zero as by the 30th year they have reached the end of their useful economic lives. Therefore, when taken together, a residual value of £3m is inlcuded in the final year of the appraisal. The £3m is recorded as a negative number (as it represents a benefit). See also HMT Green Book, page 20, para 5.22: "Even where an appraisal covers the full expected period of use of an asset, the asset may still have some residual value, in an alternative use within an organisation, in a second-hand market, or as scrap.These values should be included, and tested for sensitivity, as it may be difficult to estimate the future residual value at the present time". [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B23: Capital Cost: Example capital costs are provided here. Please include additional rows as necessary.
Note on B24: Initial Capital Costs: Remeber to exclude VAT and inflation. And exclude contingency allowance if reflected in the risk analysis (if not, include the contingency allowance).
Note on B25: Optimism Bias: Please see HM Treasury's Supplementary Guidance on Optimism Bias, avilable at: [https://www.gov.uk/government/publications/green-book-supplementary-guidance-optimism-bias] A worked example showing how to calculate an allowance for optimism bias has been provided in the tab marked, 'OPTIMISM BIAS'. In the example, project appraisers have determined that the building works required under the Do Minimum option fall within the category of 'Standard Buildings' (see the HM Treasury Guidance referred to above for more detail on whether or not your project is a 'Standard' or 'Non-Standard' building). An adjustment of 14% for the remaining optimism bias has been applied to the Do Minimum option. The optimism bias adjustment is applied to the inital capital costs of the build. Optimism bias can also apply to works duration, revenue costs, and anticipated benefits. However, it is unlikely in practice that quantified adjustment can be made for optimism bias to these specific project paramaters due to a lack of evidence upon which to base such assumptions. Given this, the HMT Green Book recommends that sensitivty analysis should be used to assess the effects of underestimating revenue costs and over estimating benefits. Sensitivty analysis becomes increasingly imoprtant at the Outline Business Case (OBC) stage when the robustness of the ranking of options is tested. As the business case develops, the level of optimism bias remaining should diminsh as there is less scope for the project's output specification to change, and action can be taken to mitigate the factors contibuting to optimism. HMT Green Book, page 29, para 5.61: "There is a demonstrated, systematic, tendency for project appraisers to be overly optimistic. This is a worldwide phenomenon that affects both the private and public sectors. Many project parameters are affected by optimism – appraisers tend to overstate benefits, and understate timings and costs, both capital and operational." [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B26: Life-Cycle Costs: In addition to the initial capital costs of a scheme, economic appraisals will also reflect the life-cycle investment associated with an option. Life-cycle costs are the costs required to maintain the building throughout its life, usually for a period of 60 years for new build options and 30 years for refurbishment options (see the appraisal periods row above). Life-cycle costs will include capital costs in respect of buildings refurbishment, upgrade and replacement and the costs of replacing equipment. As with initial capital costs, assessments of life-cycle costs should exclude VAT and inflation (unless prices are expected to increase at significantly higher or lower rate than general inflation - see coment on the 'CASHFLOWS' row above for more detail on this).
Note on B27: Other Capital Costs: In addition to the capital costs incurred as a consequence of the option, any capital investment required to maintain the existing estate in appropriate condition until the building works are complete, should also be included within the appraisal. The amount of transition period investment will vary according to the option under consideration and with the length of the implementation period. In this option, for example, there may need to be some temporary accommodation provided whilst Schools A and B are refurbished and School A is extended.
Note on B32: Revenus Costs: Example revenue costs are provided here. Please include additional rows as necessary. ‘Revenue costs’ is the term used to describe the operating costs of a service or scheme. Revenue costs should be assessed at a constant price base, consistent with the price base adopted in respect of land/property values and capital costs (usually current “real” prices). To be consistent with capital cost assessments and non-financial appraisals, the total revenue cost of the service/scheme in question will be included in the appraisal and not just the additional costs/savings of the proposed change.
Note on B33: Salaries: No wage increases are anticipated under this option, although the total wage bill for the two schools rises following the completion of the works as new staff are taken due to an increase pupil numbers.
Note on B34: Building Running Costs: Running costs should include the costs of running the school(s), inclusive of ongoing buildings (revenue) maintenance, heat, light and power and business rates. Building related running costs will take account of the proposed design and other buildings characteristics, as well as other factors that will affect the different elements of these costs. Given that a building's maintenance costs need to be consistent with life-cycle costs, and because the cost of maintaining new buildings will not necessarily reflect historic maintenance costs, professional advice should be sought with respect to buildings related running costs and their relationship to life-cycle costs (although please note that life-cycle costs fall under capital costs, whereas building running costs fall under revenue costs).
Note on B35: Other Revenue Costs: The revenue implications of the transition years prior to the full implementation of the option/scheme will need be consistent with the implementation programme (and associated capital costs), as well as with any changes in practice and personnel that will be brought about in advance of moving to the new school (and the costs or savings associated with this). Revenue costs during 'transitional' years should include the following non-recurrent costs (i.e., the three “Ds”): • Double running costs associated with the implementation of the option/scheme; • Decanting costs associated with the implementation of the option/scheme; and • Development/change costs, inclusive of the implications of new employment and any change management required to deliver the new service (such as, retraining for new roles). They will, however, exclude: • Redundancy payments (as these represent transfer payments within the public sector).
Note on B47: Discount Rate: This is used to adjust for the timing of incidence of costs by discounting them to obtain their present values. The current HM Treasury Green Book discount rate is 3.5% for years 0-30 and 3.0% for years 31-75. See HMT Green Book, Annex 6, page 97: [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]

## OPTION 2
OPTION 2: | Refurbish and Extend School A and close School B
In this option, School B will be closed and School A will be fully refurbished and extended to accommodate the predicted growth in pupil numbers.
Appraisal Period | 30 | Year '0' must be counted as a valid year (eg, 0-29 years = 30 years, 0-59 years = 60 years)
| Sum of | 1st year |  |  |  | 5th year |  |  |  |  | 10th year |  |  |  |  | 15th year |  |  |  |  | 20th year |  |  |  |  | 25th year |  |  |  |  | 30th year |  |  |  |  | 35th year |  |  |  |  | 40th year |  |  |  |  | 45th year |  |  |  |  | 50th year |  |  |  |  | 55th year |  |  |  |  | 60th year
| Cashflows | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
£m | bar: 1st year 2012 0 to 60th year 2071 59
ASSUMPTIONS
CASHFLOWS (Please read comments) | [61 empty] | The basic assumptions underlying each cost line in the economic appraisals should be recorded below
PROPERTY & OPPORTUNITY COST
Opening Value | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | e.g. based on recent property valuation and estimated value of surrounding land
Transactions | -0.9 | 0.1 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Residual Value | -3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL PROPERTY & OPP. COSTS | 1 | 5.1 | 0 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
-
CAPITAL COST (examples provided - not exhaustive) | [61 empty] | -
Initial Capital Costs | 23.5 | 11 | 7 | 3 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Optimism bias | 3.7788 | 1.7688 | 1.1256 | 0.4824 | 0.402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Lifecycle Costs | 4.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Other Capital Costs | 0.6 | 0.2 | 0.2 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL CAPITAL | 32.1788 | 13.1688 | 8.5256 | 3.7824 | 3.202 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.5 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
REVENUE COST (examples provided - not exhaustive)
Salaries | 29.1 | 1.1 | 1.1 | 1.1 | 1.1 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Building Running Costs | 7.79 | 0.3 | 0.3 | 0.5 | 0.45 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Other Revenue Costs | 0.8 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL REVENUE | 37.69 | 1.6 | 1.6 | 1.8 | 1.75 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
-
TOTAL COST (Cap & Rev) | 70.8688 | 19.8688 | 10.1256 | 5.5824 | 4.952 | 0.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.69 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.29 | 1.69 | 1.29 | 1.29 | 1.29 | 1.29 | 1.39 | 1.29 | 1.29 | 1.29 | 1.29 | -1.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
-
Discounted Cashflow | 57.5125 | 19.8688 | 9.7832 | 5.2112 | 4.4664 | 0.25272 | 1.0861 | 1.0494 | 1.0139 | 0.97964 | 1.24 | 0.91451 | 0.88358 | 0.8537 | 0.82483 | 0.79694 | 0.76999 | 0.74395 | 0.71879 | 0.69449 | 0.87906 | 0.64831 | 0.62639 | 0.6052 | 0.58474 | 0.60876 | 0.54586 | 0.5274 | 0.50957 | 0.49233 | -0.66743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Net Present Cost (NPC) | 57.5125
Equivalent Annual Cost (EAC) | 3.0213
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59
Disount Rate |  | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3%
Discount Factor |  | 1 | 0.96618 | 0.93351 | 0.90194 | 0.87144 | 0.84197 | 0.8135 | 0.78599 | 0.75941 | 0.73373 | 0.70892 | 0.68495 | 0.66178 | 0.6394 | 0.61778 | 0.59689 | 0.57671 | 0.5572 | 0.53836 | 0.52016 | 0.50257 | 0.48557 | 0.46915 | 0.45329 | 0.43796 | 0.42315 | 0.40884 | 0.39501 | 0.38165 | 0.36875 | 0.35628 | 0.3459 | 0.33583 | 0.32605 | 0.31655 | 0.30733 | 0.29838 | 0.28969 | 0.28125 | 0.27306 | 0.2651 | 0.25738 | 0.24989 | 0.24261 | 0.23554 | 0.22868 | 0.22202 | 0.21555 | 0.20928 | 0.20318 | 0.19726 | 0.19152 | 0.18594 | 0.18052 | 0.17527 | 0.17016 | 0.1652 | 0.16039 | 0.15572 | 0.15119
Annuity Factor |  | 1 | 1.9662 | 2.8997 | 3.8016 | 4.6731 | 5.5151 | 6.3286 | 7.1145 | 7.874 | 8.6077 | 9.3166 | 10.0016 | 10.6633 | 11.3027 | 11.9205 | 12.5174 | 13.0941 | 13.6513 | 14.1897 | 14.7098 | 15.2124 | 15.698 | 16.1671 | 16.6204 | 17.0584 | 17.4815 | 17.8904 | 18.2854 | 18.667 | 19.0358 | 19.392 | 19.7379 | 20.0738 | 20.3998 | 20.7164 | 21.0237 | 21.3221 | 21.6118 | 21.893 | 22.1661 | 22.4312 | 22.6886 | 22.9384 | 23.1811 | 23.4166 | 23.6453 | 23.8673 | 24.0828 | 24.2921 | 24.4953 | 24.6926 | 24.8841 | 25.07 | 25.2505 | 25.4258 | 25.596 | 25.7612 | 25.9216 | 26.0773 | 26.2285
Years | 30
EAC Calculation |  | 0: 1; 1: 0.96618; 2: 0.93351; 3: 0.90194; 4: 0.87144; 5: 0.84197; 6: 0.8135; 7: 0.78599; 8: 0.75941; 9: 0.73373; 10: 0.70892; 11: 0.68495; 12: 0.66178; 13: 0.6394; 14: 0.61778; 15: 0.59689; 16: 0.57671; 17: 0.5572; 18: 0.53836; 19: 0.52016; 20: 0.50257; 21: 0.48557; 22: 0.46915; 23: 0.45329; 24: 0.43796; 25: 0.42315; 26: 0.40884; 27: 0.39501; 28: 0.38165; 29: 0.36875
Sum of Discount Factors | 19.0358
NPC (excl. Optimism Bias) | 53.8432 | 18.1 | 8.6957 | 4.7609 | 4.1038 | 0.25272 | 1.0861 | 1.0494 | 1.0139 | 0.97964 | 1.24 | 0.91451 | 0.88358 | 0.8537 | 0.82483 | 0.79694 | 0.76999 | 0.74395 | 0.71879 | 0.69449 | 0.87906 | 0.64831 | 0.62639 | 0.6052 | 0.58474 | 0.60876 | 0.54586 | 0.5274 | 0.50957 | 0.49233 | -0.66743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EAC (excl. Optimism Bias) | 2.8285
Note on B7: Appraisal Period: The appraisal period should normally equate to the intended period of use of the asset(s). This is the period over which the asset can be used for the specific purpose that it has been provided for. An appraisal period of 29 years (i.e. 30 years when counting year zero) is commonplace for refurbishment options. An appraisal period of 59 years (i.e. 60 years when counting year zero) is commonplace for new build options. These values are not set in stone however, and therefore, can be adjusted to the specific characteristics of the project at hand.
Note on C7: This is a refurbishment/extension option, and therefore the appraisal period is set at 30 years.
Note on B14: Scope of Cashflows: The appraisal should attempt to capture all direct and indirect implications of the investment/option. Total (as opposed to change in) property, capital and revenue costs should be presented. Price/cost Base: This should be common for all costs, which should be presented in real terms or current prices (i.e. at today's general price level). Where particular prices are expected to increase at significantly higher or lower rate than inflation, the relative price change should be calculated. Examples where relative prices changes may be material to an appraisal include, high technology products (where prices may be expected to fall in real terms); fuel prices (where the resource supply is scarce); and wages (where productivity growth is expected to lead to wage increase above general inflation). Sign Convention: Costs positive, benefits negative. Timing: As per timing of implementation and expenditure of cashflows. Exclude Transfer Payments: These should be excluded from the appraisal. A transfer payment is one for which no good or service is obtained in return. Transfer payments may change the distribution of income or wealth, but do not give rise to direct economic costs. Taxes, redundancy payments, and capital charges are all examples of transfer payments that should be exluded from an economic appraisal. Exclude Sunk Costs: These are the costs of goods and services that have already been incurred and are therefore irrevocable. They should be excluded from the appraisal. From an appraisal viewpoint, the costs that matter are those upon which decisions can stil be made. However, this includes the opportunity costs of continuing to tie up resources that have already been paid for - see the comments in this speardhseet covering 'Property and Oppurtunity Costs' for more information on this aspect of the appraisal.
Note on B16: Principle: The property (land, buildings and major equipment) implications of any option should be reflected in the Discounted Cashflow analysis in accordance with the opportunity costs of the property or properties - irrespective of whether property is bought, sold or transferred, rented or used by the public sector. The opportunity costs of any asset reflect the value of the asset when used in its best alternative activity and is reflected in current market prices. If within an option a property is rented by the public sector, the rental costs will be reflected in annual revenue costs (rather than reflected in capital costs). please note that where a property is rented to another public sector organisation, the income associated with the rental is excluded from revenue estimates as this represents a transfer payment between public sector organisations. Project appraisers need to ensure that all property and opportunity cost values are assessed appropriately. The “property and opportunity” lines in this spreadsheet distinguish between “opening” values, “transactions” within the appraisal period and “residual” values. Opening Value: In the "opening value" row, opening values are included in year zero - as positive numbers. Transactions: In this row, property purchases, receipts and other transactions are included in the anticipated year of purchase, sale or transfer - positive numbers for purchase and transfers into the scheme and negative numbers for sale and transfers out. All transactions, whether they are cash sales/purchases or transfers to other public sector organisations should be entered in the “transactions” category. Residual Value: Residual values are included in the last year of the discount period - as negative numbers.
Note on B17: Opening Value: This is included in order to represent the opportunity cost of continuing to use the asset(s) in the way proposed by the option. The opportunity cost of any asset is reflected in the value of the asset when put to its best alternative activity/use. This is usually reflected in current market prices. In this option Schools A and B are kept in use initially and therefore the opening values of the land/properties/equipment in use by both schools are included in year zero - as positive numbers. As an illustrative example, the land is valued at £3m and the properties/equipment involved valued at £2m (approx. £1m per school) - and therfore an opening value of £5m is recorded in the first year of the appraisal for this option. See also HMT Green Book, page 20, para 5.14: "Costs should be expressed in terms of relevant opportunity costs. It is important to explore what opportunities may exist. An example of an opportunity is to use land in a different, more valuable, way than in its current use." [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B18: Transactions: This line is inluded to record the value of any transactions, i.e. property that is bought and sold during the lifetime of the option. In this option Schools A and B remain in use initially, however, additional land is purchased to accommodate the extension to School A at a cost of £0.1m. This figure is inlcuded as a 'transaction' when the additional land is purchased - which occurs during the first year of the appraisal. When the extension to School A is complete, School B - both its land and buildings - are sold for £1m. This figure appears as a negative number (thus representing a benefit) in the 5th year of the project when the sale takes place.
Note on B19: Residual Value: In some appraisals of investment options, the period of the appraisall will be less than the economic life of the property involved. The economic life is the period up to the point when major refurbishment is required for the asset to continue in use. In these cases, the value of an asset which has a disposal value at the end of the appraisal period should be accounted for by subtracting its residual value from the cashflow in the final year of the appraisal. The residual value can be taken as the lower of net asset value after deducting accumulated depreciation or expected market value. In this option the land upon which the properties are situated is assumed to have a residual value that equals its initial valuation of £3m, plus the £0.1m for the land initially purchased for the extension of School A. The buildings/equipment remaining at School A at the end of the appraisal are assumed to have residual value of zero as by the final year of the appraisal they will have reached the end of their useful economic lives. Therefore, only a residual value of £3.1m is inlcuded in the final year of the appraisal. The £3.1m is recorded as a negative number (as it represents a benefit). See also HMT Green Book, page 20, para 5.22: "Even where an appraisal covers the full expected period of use of an asset, the asset may still have some residual value, in an alternative use within an organisation, in a second-hand market, or as scrap.These values should be included, and tested for sensitivity, as it may be difficult to estimate the future residual value at the present time". [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B23: Capital Cost: Example capital costs are provided here. Please include additional rows as necessary.
Note on B24: Initial Capital Costs: Remeber to exclude VAT and inflation. And exclude contingency allowance if reflected in the risk analysis (if not, include the contingency allowance).
Note on B25: Optimism Bias: Please see HM Treasury's Supplementary Guidance on Optimism Bias, avilable at: [https://www.gov.uk/government/publications/green-book-supplementary-guidance-optimism-bias] A worked example showing how to calculate an allowance for optimism bias has been provided in the tab marked, 'OPTIMISM BIAS'. In the example, project appraisers have determined that the building works required under 'Option 2' fall within the category of 'Standard Buildings' (see the HM Treasury Guidance referred to above for more detail on whether or not your project is a 'Standard' or 'Non-Standard' building). An adjustment of 14% for the remaining optimism bias has been applied to 'Option 2'. The optimism bias adjustment is applied to the inital capital costs of the build. (This adjustment is the same as that applied in the case of the Do Minimum option, however, in practice, a different independent adjustment should be applied to each option individually - as some options will inherently be more risky than others). Optimism bias can also apply to works duration, revenue costs, and anticipated benefits. However, it is unlikely in practice that quantified adjustment can be made for optimism bias to these specific project paramaters due to a lack of evidence upon which to base such assumptions. Given this, the HMT Green Book recommends that sensitivty analysis should be used to assess the effects of underestimating revenue costs and over estimating benefits. Sensitivty analysis becomes increasingly imoprtant at the Outline Business Case (OBC) stage when the robustness of the ranking of options is tested. As the business case develops, the level of optimism bias remaining should diminsh as there is less scope for the project's output specification to change, and action can be taken to mitigate the factors contibuting to optimism. HMT Green Book, page 29, para 5.61: "There is a demonstrated, systematic, tendency for project appraisers to be overly optimistic. This is a worldwide phenomenon that affects both the private and public sectors. Many project parameters are affected by optimism – appraisers tend to overstate benefits, and understate timings and costs, both capital and operational." [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B26: Life-Cycle Costs: In addition to the initial capital costs of a scheme, economic appraisals will also reflect the life-cycle investment associated with an option. Life-cycle costs are the costs required to maintain the building throughout its life, usually for a period of 60 years for new build options and 30 years for refurbishment options (see the appraisal periods row above). Life-cycle costs will include capital costs in respect of buildings refurbishment, upgrade and replacement and the costs of replacing equipment. As with initial capital costs, assessments of life-cycle costs should exclude VAT and inflation (unless prices are expected to increase at significantly higher or lower rate than general inflation - see coment on the 'CASHFLOWS' row above for more detail on this).
Note on B27: Other Capital Costs: In addition to the capital costs incurred as a consequence of the option, any capital investment required to maintain the existing estate in appropriate condition until the building works are complete, should also be included within the appraisal. The amount of transition period investment will vary according to the option under consideration and with the length of the implementation period. In this option, for example, there may need to be some temporary accommodation provided at Schools A whilst it is refurbished and extended.
Note on B32: Revenus Costs: Example revenue costs are provided here. Please include additional rows as necessary. ‘Revenue costs’ is the term used to describe the operating costs of a service or scheme. Revenue costs should be assessed at a constant price base, consistent with the price base adopted in respect of land/property values and capital costs (usually current “real” prices). To be consistent with capital cost assessments and non-financial appraisals, the total revenue cost of the service/scheme in question will be included in the appraisal and not just the additional costs/savings of the proposed change.
Note on B33: Salaries: No wage increases are anticipated under this option, although the total wage bill falls following the completion of the works at School A and the closure of School B.
Note on B34: Building Running Costs: Running costs should include the costs of running the school(s), inclusive of ongoing buildings (revenue) maintenance, heat, light and power and business rates. Building related running costs will take account of the proposed design and other buildings characteristics, as well as other factors that will affect the different elements of these costs. Given that a building's maintenance costs need to be consistent with life-cycle costs, and because the cost of maintaining new buildings will not necessarily reflect historic maintenance costs, professional advice should be sought with respect to buildings related running costs and their relationship to life-cycle costs (although please note that life-cycle costs fall under capital costs, whereas building running costs fall under revenue costs).
Note on B35: Other Revenue Costs: The revenue implications of the transition years prior to the full implementation of the option/scheme will need be consistent with the implementation programme (and associated capital costs), as well as with any changes in practice and personnel that will be brought about in advance of moving to the new school (and the costs or savings associated with this). Revenue costs during 'transitional' years should include the following non-recurrent costs (i.e., the three “Ds”): • Double running costs associated with the implementation of the option/scheme; • Decanting costs associated with the implementation of the option/scheme; and • Development/change costs, inclusive of the implications of new employment and any change management required to deliver the new service (such as, retraining for new roles). They will, however, exclude: • Redundancy payments (as these represent transfer payments within the public sector).
Note on B47: Discount Rate: This is used to adjust for the timing of incidence of costs by discounting them to obtain their present values. The current HM Treasury Green Book discount rate is 3.5% for years 0-30 and 3.0% for years 31-75. See HMT Green Book, Annex 6, page 97: [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]

## OPTION 3
OPTION 3: | New-build on a Single Site
In this option, both Schools A and B will be combined via a new build on a single site. A potential site has been identified and closure of Schools A and B has been deemed possible following discussions with stakeholders.
Appraisal Period | 63 | Year '0' must be counted as a valid year (eg, 0-29 years = 30 years, 0-59 years = 60 years)
| Sum of | 1st year |  |  |  | 5th year |  |  |  |  | 10th year |  |  |  |  | 15th year |  |  |  |  | 20th year |  |  |  |  | 25th year |  |  |  |  | 30th year |  |  |  |  | 35th year |  |  |  |  | 40th year |  |  |  |  | 45th year |  |  |  |  | 50th year |  |  |  |  | 55th year |  |  |  |  | 60th year |  |  | 63rd year
| Cashflows | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
£m | bar: 1st year 2012 0 to 63rd year 2074 62
ASSUMPTIONS
CASHFLOWS (Please read comments) | [64 empty] | The basic assumptions underlying each cost line in the economic appraisals should be recorded below
PROPERTY & OPPORTUNITY COST
Opening Value | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | e.g. based on recent property valuation and estimated value of surrounding land
Transactions | -1.8 | 3 | 0 | 0 | 0 | -4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Residual Value | -3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | …
-
TOTAL PROPERTY & OPP. COSTS | 0.2 | 8 | 0 | 0 | 0 | -4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | -
-
CAPITAL COST (examples provided - not exhaustive) | [64 empty] | -
Initial Capital Costs | 28 | 12 | 10.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Optimism bias | 4.5024 | 1.9296 | 1.6884 | 0.8844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
Lifecycle Costs | 17.95 | 0.2 | 0.2 | 0.2 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.8 | 0.3 | 0.3 | 0.3 | …
Other Capital Costs | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL CAPITAL | 50.9524 | 14.1296 | 12.3884 | 6.5844 | 0.65 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.8 | 0.15 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.8 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.8 | 0.3 | 0.3 | 0.3 | -
REVENUE COST (examples provided - not exhaustive)
Salaries | 61.63 | 1.1 | 1.1 | 1.1 | 1.1 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | 0.97 | …
Building Running Costs | 21.3 | 0.3 | 0.3 | 0.3 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | 0.34 | …
Other Revenue Costs | 0.9 | 0 | 0 | 0 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | …
-
TOTAL REVENUE | 83.83 | 1.4 | 1.4 | 1.4 | 2.34 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | 1.31 | -
-
TOTAL COST (Cap & Rev) | 134.9824 | 23.5296 | 13.7884 | 7.9844 | 2.99 | -3.34 | 1.46 | 1.46 | 1.46 | 1.46 | 2.11 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 2.11 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 2.11 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 2.11 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 1.46 | 2.11 | 1.46 | 1.61 | 1.61 | 1.61 | 1.61 | 1.61 | 2.11 | 1.61 | 1.61 | 1.61 | 1.61 | 1.61 | 1.61 | 1.61 | 2.11 | 1.61 | 1.61 | 1.61 | 1.61 | 1.61 | 1.61 | 2.11 | 1.61 | 1.61 | -1.39 | -
-
Discounted Cashflow | 78.3387 | 23.5296 | 13.3221 | 7.4535 | 2.6968 | -2.9106 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.5482 | 1.035 | 1 | 0.9662 | 0.93353 | 0.90196 | 0.87146 | 1.2168 | 0.81352 | 0.78601 | 0.75943 | 0.73375 | 0.70893 | 0.68496 | 0.95643 | 0.63942 | 0.61779 | 0.5969 | 0.57672 | 0.55722 | 0.53837 | 0.75175 | 0.50502 | 0.49031 | 0.47603 | 0.46216 | 0.4487 | 0.43563 | 0.61124 | 0.41062 | 0.43962 | 0.42682 | 0.41439 | 0.40232 | 0.3906 | 0.49699 | 0.36818 | 0.35745 | 0.34704 | 0.33693 | 0.32712 | 0.31759 | 0.30834 | 0.39233 | 0.29064 | 0.28218 | 0.27396 | 0.26598 | 0.25823 | 0.25071 | 0.319 | 0.23632 | 0.22944 | -0.19231 | -
Net Present Cost (NPC) | 78.3387
Equivalent Annual Cost (EAC) | 2.9389
|  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
Disount Rate |  | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3.5% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3%
Discount Factor |  | 1 | 0.96618 | 0.93351 | 0.90194 | 0.87144 | 0.84197 | 0.8135 | 0.78599 | 0.75941 | 0.73373 | 0.70892 | 0.68495 | 0.66178 | 0.6394 | 0.61778 | 0.59689 | 0.57671 | 0.5572 | 0.53836 | 0.52016 | 0.50257 | 0.48557 | 0.46915 | 0.45329 | 0.43796 | 0.42315 | 0.40884 | 0.39501 | 0.38165 | 0.36875 | 0.35628 | 0.3459 | 0.33583 | 0.32605 | 0.31655 | 0.30733 | 0.29838 | 0.28969 | 0.28125 | 0.27306 | 0.2651 | 0.25738 | 0.24989 | 0.24261 | 0.23554 | 0.22868 | 0.22202 | 0.21555 | 0.20928 | 0.20318 | 0.19726 | 0.19152 | 0.18594 | 0.18052 | 0.17527 | 0.17016 | 0.1652 | 0.16039 | 0.15572 | 0.15119 | 0.14678 | 0.14251 | 0.13836
Annuity Factor |  | 1 | 1.9662 | 2.8997 | 3.8016 | 4.6731 | 5.5151 | 6.3286 | 7.1145 | 7.874 | 8.6077 | 9.3166 | 10.0016 | 10.6633 | 11.3027 | 11.9205 | 12.5174 | 13.0941 | 13.6513 | 14.1897 | 14.7098 | 15.2124 | 15.698 | 16.1671 | 16.6204 | 17.0584 | 17.4815 | 17.8904 | 18.2854 | 18.667 | 19.0358 | 19.392 | 19.7379 | 20.0738 | 20.3998 | 20.7164 | 21.0237 | 21.3221 | 21.6118 | 21.893 | 22.1661 | 22.4312 | 22.6886 | 22.9384 | 23.1811 | 23.4166 | 23.6453 | 23.8673 | 24.0828 | 24.2921 | 24.4953 | 24.6926 | 24.8841 | 25.07 | 25.2505 | 25.4258 | 25.596 | 25.7612 | 25.9216 | 26.0773 | 26.2285 | 26.3753 | 26.5178 | 26.6561
Years | 63
EAC Calculation |  | 1 | 0.96618 | 0.93351 | 0.90194 | 0.87144 | 0.84197 | 0.8135 | 0.78599 | 0.75941 | 0.73373 | 0.70892 | 0.68495 | 0.66178 | 0.6394 | 0.61778 | 0.59689 | 0.57671 | 0.5572 | 0.53836 | 0.52016 | 0.50257 | 0.48557 | 0.46915 | 0.45329 | 0.43796 | 0.42315 | 0.40884 | 0.39501 | 0.38165 | 0.36875 | 0.35628 | 0.3459 | 0.33583 | 0.32605 | 0.31655 | 0.30733 | 0.29838 | 0.28969 | 0.28125 | 0.27306 | 0.2651 | 0.25738 | 0.24989 | 0.24261 | 0.23554 | 0.22868 | 0.22202 | 0.21555 | 0.20928 | 0.20318 | 0.19726 | 0.19152 | 0.18594 | 0.18052 | 0.17527 | 0.17016 | 0.1652 | 0.16039 | 0.15572 | 0.15119 | 0.14678 | 0.14251 | 0.13836
Sum of Discount Factors | 26.6561
NPC (excl. Optimism Bias) | 73.9522 | 21.6 | 11.6908 | 6.6279 | 2.6968 | -2.9106 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.5482 | 1.035 | 1 | 0.9662 | 0.93353 | 0.90196 | 0.87146 | 1.2168 | 0.81352 | 0.78601 | 0.75943 | 0.73375 | 0.70893 | 0.68496 | 0.95643 | 0.63942 | 0.61779 | 0.5969 | 0.57672 | 0.55722 | 0.53837 | 0.75175 | 0.50502 | 0.49031 | 0.47603 | 0.46216 | 0.4487 | 0.43563 | 0.61124 | 0.41062 | 0.43962 | 0.42682 | 0.41439 | 0.40232 | 0.3906 | 0.49699 | 0.36818 | 0.35745 | 0.34704 | 0.33693 | 0.32712 | 0.31759 | 0.30834 | 0.39233 | 0.29064 | 0.28218 | 0.27396 | 0.26598 | 0.25823 | 0.25071 | 0.319 | 0.23632 | 0.22944 | -0.19231
EAC (excl. Optimism Bias) | 2.7743
Note on B7: Appraisal Period: The appraisal period should normally equate to the intended period of use of the asset(s). This is the period over which the asset can be used for the specific purpose that it has been provided for. An appraisal period of 29 years (i.e. 30 years when counting year zero) is commonplace for refurbishment options. An appraisal period of 59 years (i.e. 60 years when counting year zero) is commonplace for new build options. These values are not set in stone however, and therefore, can be adjusted to the specific characteristics of the project at hand.
Note on C7: This is a new build option and therefore the appraisal period is set at 63 years (which assumes a build time of 3 years, plus a useful economic life of 60 years).
Note on B14: Scope of Cashflows: The appraisal should attempt to capture all direct and indirect implications of the investment/option. Total (as opposed to change in) property, capital and revenue costs should be presented. Price/cost Base: This should be common for all costs, which should be presented in real terms or current prices (i.e. at today's general price level). Where particular prices are expected to increase at significantly higher or lower rate than inflation, the relative price change should be calculated. Examples where relative prices changes may be material to an appraisal include, high technology products (where prices may be expected to fall in real terms); fuel prices (where the resource supply is scarce); and wages (where productivity growth is expected to lead to wage increase above general inflation). Sign Convention: Costs positive, benefits negative. Timing: As per timing of implementation and expenditure of cashflows. Exclude Transfer Payments: These should be excluded from the appraisal. A transfer payment is one for which no good or service is obtained in return. Transfer payments may change the distribution of income or wealth, but do not give rise to direct economic costs. Taxes, redundancy payments, and capital charges are all examples of transfer payments that should be exluded from an economic appraisal. Exclude Sunk Costs: These are the costs of goods and services that have already been incurred and are therefore irrevocable. They should be excluded from the appraisal. From an appraisal viewpoint, the costs that matter are those upon which decisions can stil be made. However, this includes the opportunity costs of continuing to tie up resources that have already been paid for - see the comments in this speardhseet covering 'Property and Oppurtunity Costs' for more information on this aspect of the appraisal.
Note on B16: Principle: The property (land, buildings and major equipment) implications of any option should be reflected in the Discounted Cashflow analysis in accordance with the opportunity costs of the property or properties - irrespective of whether property is bought, sold or transferred, rented or used by the public sector. The opportunity costs of any asset reflect the value of the asset when used in its best alternative activity and is reflected in current market prices. If within an otion a property is rented by the public sector, the rental costs will be reflected in annual revenue costs (rather than reflected in capital costs). Where property is rented to other public sector organisations, the income associated with the rental is excluded from revenue estimates as this represents a transfer payment between public sector organisations. Project appraisers need to ensure that all property and opportunity cost values are assessed appropriately. The “property and opportunity” lines in this spreadsheet distinguish between “opening” values, “transactions” within the appraisal period and “residual” values. All transactions, whether they are cash sales/purchases or transfers to other public sector bodies will be entered in the “transactions” category.
Note on B17: Opening Value: This is included in order to represent the opportunity cost of continuing to use the asset(s) in the way proposed by the option. The opportunity cost of any asset is reflected in the value of the asset when put to its best alternative activity/use. This is usually reflected in current market prices. In this option Schools A and B are initally kept in use (whilst the new school is built) and therefore the opening values of the land/properties/equipment in use by both schools are included in year zero of the appraisal - as positive numbers. As an illustrative example, the land is valued at £3m and the properties/equipment involved valued at £2m (approx. £1m per school) - and therfore an opening value of £5m is recorded in the first year of the appraisal for this option. See also HMT Green Book, page 20, para 5.14: "Costs should be expressed in terms of relevant opportunity costs. It is important to explore what opportunities may exist. An example of an opportunity is to use land in a different, more valuable, way than in its current use." [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B18: Transactions: This line is inluded to record the value of any transactions, i.e. property that is bought and sold during the lifetime of the option. In this option land is purchased, at a cost of £3m, in order to build the new school building. This is recorded as a 'transaction' in the year the land is purchased, which is year 0 of the appraisal. If the land was already in the Local Authority's ownership, its value would be recorded in the 'opening value' row above. Once Schools A and B have closed and the pupils moved to the new school, the Local Authority decides to sell both sites. This yields a receipt of approximately £4.8m (after accounting for a slight reduction in the base year valuation of the land/buildings and the transfer of the existing equipment to the new school). The receipt of £4.8m is recorded in Year 4 when the sales of both sites takes place. (The receipt is displayed as a negative number as it represents a benefit).
Note on B19: In some appraisals of investment options the period of the appraisall will be less than the economic life of the property involved. The economic life is the period up to the point when major refurbishment is required for the asset to continue in use. In these cases, the value of an asset which has a disposal value at the end of the appraisal period should be accounted for by subtracting its residual value from the cashflow in the final year of the appraisal. The residual value can be taken as the lower of net asset value after deducting accumulated depreciation or expected market value. In this option the value of the land upon which the new school has been built is assumed to have a residual value that equals its initial cost of £3m. The residual value of the new building and its equipment is assumed to be zero as they have have reached the end of their useful economic lives by the 63rd year of the appraisal. A residual value of £3m only is therefore included in the final year of the appraisal. This is included as a negative number as it represents a benefit. See HMT Green Book, page 20, para 5.22: "Even where an appraisal covers the full expected period of use of an asset, the asset may still have some residual value, in an alternative use within an organisation, in a second-hand market, or as scrap.These values should be included, and tested for sensitivity, as it may be difficult to estimate the future residual value at the present time". [http://www.hm-treasury.gov.uk/data_greenbook_index.htm]
Note on B23: Capital Cost: Example capital costs are provided here. Please include additional rows as necessary.
Note on B24: Initial Capital Costs: Remeber to exclude VAT and inflation. And exclude contingency allowance if reflected in the risk analysis (if not, include the contingency allowance).
Note on B25: Optimism Bias: Please see HM Treasury's Supplementary Guidance on Optimism Bias, avilable at: [https://www.gov.uk/government/publications/green-book-supplementary-guidance-optimism-bias] A worked example showing how to calculate an allowance for optimism bias has been provided in the tab marked, 'OPTIMISM BIAS'. In the example project appraisers have determined that the building works required under 'Option 3' fall within the category of 'Standard Buildings' (see the HM Treasury Guidance referred to above for more detail on whether or not your project is a 'Standard' or 'Non-Standard' building). An adjustment of 14% for the remaining optimism bias has been applied to 'Option 3'. The optimism bias adjustment is applied to the inital capital costs of the build. (This adjustment is the same as that applied in the case of the Do Minimum option, however, in practice, a different independent adjustment should be applied to each option individually - as some options will inherently be more risky than others). Optimism bias can also apply to works duration, revenue costs, and anticipated benefits. However, it is unlikely in practice that quantified adjustment can be made for optimism bias to these specific project paramaters due to a lack of evidence upon which to base such assumptions. Given this, the HMT Green Book recommends that sensitivty analysis should be used to assess the effects of underestimating revenue costs and over estimating benefits. Sensitivty analysis becomes increasingly imoprtant at the Outline Business Case (OBC) stage when the robustness of the ranking of options is tested. As the business case develops, the level of optimism bias remaining should diminsh as there is less scope for the project's output specification to change, and action can be taken to mitigate the factors contibuting to optimism. HMT Green Book, page 29, para 5.61: "There is a demonstrated, systematic, tendency for project appraisers to be overly optimistic. This is a worldwide phenomenon that affects both the private and public sectors. Many project parameters are affected by optimism – appraisers tend to overstate benefits, and understate timings and costs, both capital and operational." [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]
Note on B26: Life-Cycle Costs: In addition to the initial capital costs of a scheme, economic appraisals will also reflect the life-cycle investment associated with an option. Life-cycle costs are the costs required to maintain the building throughout its life, usually for a period of 60 years for new build options and 30 years for refurbishment options (see the appraisal periods row above). Life-cycle costs will include capital costs in respect of buildings refurbishment, upgrade and replacement and the costs of replacing equipment. As with initial capital costs, assessments of life-cycle costs should exclude VAT and inflation (unless prices are expected to increase at significantly higher or lower rate than general inflation - see coment on the 'CASHFLOWS' row above for more detail on this).
Note on B27: Other Capital Costs: In addition to the capital costs incurred as a consequence of the option, any capital investment required to maintain the existing estate in appropriate condition until the building works are complete, should also be included within the appraisal. The amount of transition period investment will vary according to the option under consideration and with the length of the implementation period. In this option, for example, there may need to be some temporary accommodation provided at Schools A whilst it is refurbished and extended.
Note on B32: Revenus Costs: Example revenue costs are provided here. Please include additional rows as necessary. ‘Revenue costs’ is the term used to describe the operating costs of a service or scheme. Revenue costs should be assessed at a constant price base, consistent with the price base adopted in respect of land/property values and capital costs (usually current “real” prices). To be consistent with capital cost assessments and non-financial appraisals, the total revenue cost of the service/scheme in question will be included in the appraisal and not just the additional costs/savings of the proposed change.
Note on B33: Salaries: No wage increases above general inflation anticipated for this example.
Note on B34: Building Running Costs: Running costs should include the costs of running the school(s), inclusive of ongoing buildings (revenue) maintenance, heat, light and power and business rates. Building related running costs will take account of the proposed design and other buildings characteristics, as well as other factors that will affect the different elements of these costs. Given that a building's maintenance costs need to be consistent with life-cycle costs, and because the cost of maintaining new buildings will not necessarily reflect historic maintenance costs, professional advice should be sought with respect to buildings related running costs and their relationship to life-cycle costs (although please note that life-cycle costs fall under capital costs, whereas building running costs fall under revenue costs).
Note on B35: Other Revenue Costs: The revenue implications of the transition years prior to the full implementation of the option/scheme will need be consistent with the implementation programme (and associated capital costs), as well as with any changes in practice and personnel that will be brought about in advance of moving to the new school (and the costs or savings associated with this). Revenue costs during 'transitional' years should include the following non-recurrent costs (i.e., the three “Ds”): • Double running costs associated with the implementation of the option/scheme; • Decanting costs associated with the implementation of the option/scheme; and • Development/change costs, inclusive of the implications of new employment and any change management required to deliver the new service (such as, retraining for new roles). They will, however, exclude: • Redundancy payments (as these represent transfer payments within the public sector).
Note on B47: Discount Rate: This is used to adjust for the timing of incidence of costs by discounting them to obtain their present values. The current HM Treasury Green Book discount rate is 3.5% for years 0-30 and 3.0% for years 31-75. See HMT Green Book, Annex 6, page 97: [https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent]

## OPTIMISM BIAS
OPTIMISM BIAS There is a demonstrated, systematic, tendency for project appraisers to be overly optimistic. To redress this tendency appraisers should make explicit, empirically based adjustments to the estimate of a project’s costs, benefits, and duration. It is recommended that these adjustments should be based on data from past projects or similar projects elsewhere, and adjusted for the unique characteristics of the project in hand. This spreadsheet provides an example of how to calculate an adjustment for optimism bias, which is then applied to the initial capital expenditure of a specific option that is under appraisal. A separate and disctinct assessment of optimism bias should be completed for each indiviudal option. Spreadsheet users are strongly encouraged to refer to the HM Treasury’s supplementary guidance on optimism bias; available at: https://www.gov.uk/government/publications/green-book-supplementary-guidance-optimism-bias Appraisers must determine the extent to which factors contrbuting to optimism bias have been mitigtated. For guidance on how to do this, please read the comment attached to the 'MITIGATION FACTOR' cell below.
Optimism Bias - Upper Bound Guidance for Building Projects
CAPITAL EXPENDITURE
|  | Non-standard Buildings | Standard Buildings
| Upper Bound optimism Bias (%) (1) | 51% | 24% | MITIGATION FACTOR | Managed Optimism Bias |  | Rationale Behind Chosen Degree of Mitigation (or reason for exclusion of contributory factor)
[5 empty] | Non-Standard Building | Standard Building
Contributory Factors to Upper Bound Optimism Bias (%) (2) (3)
Procurement | Complexity of Contract Structure | 1% |  | 0 | 0 | 0 | …
| Late Contractor Involvement in Design | 2% | 2% | 0.3 | 0.006 | 0.006 | …
| Poor Contractor Capabilities | 5% | 9% | 0.6 | 0.03 | 0.054 | …
| Government Guidelines |  |  |  | 0 | 0 | …
| Dispute and Claims Occurred | 11% | 29% | 0.3 | 0.033 | 0.087 | …
| Information Management |  |  |  | 0 | 0 | …
| Other (Specify) |  |  |  | 0 | 0 | …
Project Specific | Design Complexity | 3% | 1% | 0.3 | 0.009 | 0.003 | …
| Degree of Innovation | 9% | 4% | 0.3 | 0.027 | 0.012 | …
| Environmental Impact |  |  |  | 0 | 0 | …
| Other (Specify) | 5% |  | 0 | 0 | 0 | …
| Inadequacy of the Business Case | 23% | 34% | 0.2 | 0.046 | 0.068 | …
| Large No. of Stakeholders |  |  |  | 0 | 0 | …
Client Specific | Funding Availability |  |  |  | 0 | 0 | …
| Project Management Team | 2% | 1% | 0.6 | 0.012 | 0.006 | …
| Poor Project Intelligence | 6% | 2% | 0.5 | 0.03 | 0.01 | …
| Other (Specify) | 2% | 1% | 0.2 | 0.004 | 0.002 | …
Environment | Public Relations |  | 2% | 0.7 | 0 | 0.014 | e.g. key stakeholders recently consulted / included in option generation
| Site Characteristics | 1% | 2% | 0.7 | 0.007 | 0.014 | e.g. full site evaluation recently undertaken
| Permits / Consents / Approvals | 1% |  |  | 0 | 0 | …
| Other (Specify) | 3% |  |  | 0 | 0 | …
External Influences | Political |  |  |  | 0 | 0 | …
| Economic | 13% | 11% | 0.5 | 0.065 | 0.055 | …
| Legislation / Regulations | 7% | 3% | 0.3 | 0.021 | 0.009 | …
| Technology | 5% |  |  | 0 | 0 | …
| Other (Specify) | 2% |  |  | 0 | 0 | …
| Remaining Optimism Bias | 36.72% | 16.08% |  | 0.29 | 0.34
(1) Note that these are only indicative starting values for calculating optimism bias contributions, because a project’s optimism bias profile will change during its project life cycle.
(2) Contributions from each area are expressed as a % of the recorded optimism bias. Note: The sum of individual percentages contributions in each column may not add up to 100% due to rounding errors.
(3) As noted above, see the Appendix in the HM Treasury's Supplementary Guidance for more detail on the issues surrounding these contributory factors in order to help you assess the level to which they have been mitigated .
(4) A more advanced optimism bias calculator is available as part of the Northern Ireland Guide to Expenditure Appraisal and Evaluation [see: http://www.dfpni.gov.uk/index/finance/eag/eag_resources/eag-optimism-bias-calculator.htm]
Note on H11: The extent to which a contributory factor has been mitigated can be reflected by a mitigation factor, which should be recorded in the relevant cells in this column. The mitigation factor has a value of between 0.0 and 1.0. A value of 0.0 means that a contributory factor is not mitigated at all and a value of 1.0 means that the contributory factor has been fully mitigated. Values between 0.0 and 1.0 represent partial mitigation. A table is provided opposite to record the rationale behind the chosen degree of mitigation. If a contributory factor is not deemed to be relevant to the speficic project in hand, a mitigation factor of 1.0 should be recorded for that factor, however the reasoning behind the decision to dismiss that factor should be recorded in the table opposite (and based on firm evidence).
Note on D41: Once a 'building-type' has been selected and it has been determined the extent to which the factors contirbuting to optimism bias have been mitigated, the initial capital expenditure of an option is adjusted to inlcude the remaining bias. (e.g. if the remaining optimism bias after mitigation is 16% and the initial capital expenditure of a project in Year 0 = £3m and in Year 1 = £4m, the optimism bias adjustment that should be included in row 25 of that option's spreadsheet is equal to, Year 0 = £3m * 16% = £0.48m and Year 1 = £4m * 16% = £0.64m). If an option's proposals inlcude a mixture of both standard and non-standard buildings, spreadsheet users should refer to the optimism bias calculator provided in the Northern Ireland Guide to Expenditure Appraisal and Evaluation, as it includes an additional function to adjust for a mixture of standard and non-standard buildings (see the Northern Ireland Optimism Bias Calculator for Building Projects, available at: [http://www.dfpni.gov.uk/index/finance/eag/eag_resources/eag-optimism-bias-calculator.htm] ).

## QUICK REFERENCE
GENERAL PRINICIPLES OF AN ECONOMIC APPRAISAL - QUICK REFERENCE
PRINCIPLES | INCLUDE / EXCLUDE | TREATMENT
GENERAL:
Price/cost base | - | - Common for all elements of costs
- Current prices
- Where there is sound evidence of variations from CPI, the difference will be reflected in the base costings (e.g. % adjustments to MIPS), otherwise the impact of inflation is considered in risk analysis
Sunk costs | Exclude | -
Opportunity costs | Include | Most commonly reflected in property values
Transfer payments:
· Taxes | Exclude | -
· Redundancy payments | Exclude | -
· Capital charges | Exclude | -
Avoided costs | Include | Reflect in “do minimum” option only
Scope of costs | - | - All direct and indirect implications of the investment
- Total (as opposed to change) property, capital and revenue costs
Optimism bias | Include
Sign convention | - | Costs positive, benefits negative
PROPERTY VALUES / OPPORTUNITY COSTS:
Property in Local Authority use | Include
Property bought and sold by Local Authority | Include
Other property transactions (transfers between public sector bodies) | Include
Property rented | Include | Include in revenue costs
CAPITAL COSTS:
Initial capital costs | Include | - Exclude VAT, inflation (subject to guidance on cost/price base above) and contingency allowance if reflected in the risk analysis
- Include adjustment for optimism bias
-Timing as per timing of implementation and expenditure cash flows
Life-cycle costs | Include | - Exclude VAT, inflation (subject to guidance on cost/price base above) and contingency allowance if reflected in the risk analysis
- Consistent with initial capital costs and on-going buildings related running costs
Transition period capital | Include | - Exclude VAT, inflation (subject to guidance on cost/price base above) and contingency if reflected in the risk analysis
- Timing as per timing of implementation and expenditure cash flows
Equipment | Include | - Where purchased, include in life-cycle costs
- Where leased or less than £5,000, include in revenue costs
ANNUAL REVENUE COSTS:
General | Varies | Include:
· All relevant revenue costs
· Annual savings attributable to the investment (see forecast savings below)
· Net income contribution from non-public sector bodies (see net (income) contribution below)
Exclude:
· VAT
· Net income contribution from public sector bodies (see net (income) contribution below)
· Capital charges
· Inflation (subject to above guidance on price/cost base above)
Salaries | Include | Consider and assess explicitly, impact of:
· Future levels of provision
· Future model of education
· Key differences across options
PRINCIPLES | INCLUDE / EXCLUDE | TREATMENT
Buildings related running costs | Include | - Reflect design and other buildings related impacts on revenue cost
- Consistent with initial capital costs and life-cycle costs
Forecast savings | Include | Reflected in assessment of revenue costs
Net (Income) contribution | Varies | - Include net income from non-public sector bodies
- Exclude net income from public sector bodies
Transition years | Include | - Include revenue costs required to deliver the service
- Also include (the 3 “Ds”):
· Double running costs
· Decanting costs
· Development/change costs
Exclude:
· Redundancy costs
DISPLACEMENT COSTS:
Displacement costs | Investigate and include where necessary | - Reflect all cost implications (property, capital and revenue and to public/private sectors) as appropriate
- Ensure like for like comparison across options
APPRAISAL PERIOD / TIMESCALES:
Appraisal period | - | - New build options – construction period plus 60 years operational life.
- Refurbishment options - 25-30 years
- Appraisal of different new build/refurbishment options, use NPC residual value method
Start date | - | Planned start date for Discounted Cashflow common for all options
Completion date | - | Planned completion date, as determined by implementation programme and consistent with capital cash flows
Property cash flows | Include | As determined by timing of property use, purchase and sale:
· Open and residual values at end beginning and end of discount period respectively
· Purchase and receipt to reflect timing of purchase/sale
· Other property transactions (transfers within the public sector) to reflect timing of transaction
Capital cash flows | Include | - Initial capital, as determined by capital cash flows, plus optimism bias
- Life-cycle and transition period capital
Revenue cash flows | Include | - As determined by plans for transition period and scheme implementation programme
Note on B66: Costs falling on other organisations and other parts of the public sector will need to be assessed separately and included within the Discounted Cashflow analysis. These are referred to as “externalities” and include the wider (external) capital and service implications of an investment. “Displacement costs” is also a term used to describe the costs that are incurred by one party as a consequence of the activities of another. Displacement costs result from the development of a scheme by one organisation that results in the displacement of service activity, and hence costs, to another or others (whether or not this is intended) - in this sense, the costs are “displaced” elsewhere in the public sector. They arise because activity that was once undertaken by the organisation sponsoring the investment will transfer elsewhere within the public sector as a consequence. An extreme version of displacement is represented by complete “dispersal” options, in which all service activity and the majority, if not all, the costs are displaced from one organisation to another (or others). Costs to the public sector that is incurred as a consequence of the transfer of workload/provision to the private sector will also be included as a displacement cost. Displaced costs can have property, capital and revenue components, depending on the magnitude of the activity displaced as a consequence of the scheme and implications for other service providers of delivering this activity. It is often convenient to summarise displaced costs in revenue terms - either, on the basis of the multiple of assessed unit costs (average or marginal) and the units of displaced activity, or, an assessment of the total costs of providing the displaced services. Alternatively, the different cost elements (property, capital investment and revenue) will be considered separately, if the displaced volumes are assessed to have capacity implications.

## USEFUL LINKS
USEFUL LINKS:
* | HM Treasury Green Book
https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent
* | Five Case Model Guidance
https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-governent
* | Capital Investment Manual: Business Case Guide (written for hospital buildings but the principles are common to all capital investment projects)
http://webarchive.nationalarchives.gov.uk/20130107105354/http://www.dh.gov.uk/en/Publicationsandstatistics/Publications/PublicationsPolicyAndGuidance/DH_4119896
* | The Generic Economic Model for Capital Investment in Health (see in particular the principles guide to the model at Outline Business Case stage)
http://webarchive.nationalarchives.gov.uk/+/www.dh.gov.uk/en/Aboutus/Procurementandproposals/Publicprivatepartnership/Privatefinanceinitiative/GenericeconomicmodelPFIschemes/DH_4016193
* | HM Treasury Supplementary Guidance on Optimism Bias
https://www.gov.uk/government/publications/green-book-supplementary-guidance-optimism-bias
* | Calculating the Adjustment for Optimism Bias for Health Projects (provides a useful explanation of the relationship between optimism bias, contingencies and risk)
http://webarchive.nationalarchives.gov.uk/+/www.dh.gov.uk/en/Aboutus/Procurementandproposals/Publicprivatepartnership/Privatefinanceinitiative/GenericeconomicmodelPFIschemes/DH_4016193
* | Option Appraisal - Building Our Future: Scotland's School Estate
http://www.scotland.gov.uk/Publications/2004/05/19436/38224
* | Northern Ireland Guide to Expenditure Appraisal and Evaluation
http://www.dfpni.gov.uk/eag
* | Good Practice Guide: Learning Lessons from Post-Project Evaluation (written for health projects but general principles apply)
http://webarchive.nationalarchives.gov.uk/+/www.dh.gov.uk/en/Aboutus/Procurementandproposals/Publicprivatepartnership/Privatefinanceinitiative/Learninglessonsfrompostprojectevaluation/DH_4016498